## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bharatpur to Accommodate FHTC | SM/11534 | Augmentation | Acceptance cum work order for Sinking of 1(one) no. 300mm x 200 mm. dia. Tube well 250 mtr deep by D.R. method with UPVC pipe & strainer having 300mm dia 36 mtr. Long housing pipe & 200 mm dia 30 mtr. long filter at Bharatpur water supply scheme under Bongaon Sub-Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000363/2022-2023 | 2241/BD | 28/07/2022 | 27/08/2022 | MONDAL ENTERPRISE. (BARASAT) | 14.32 | 12.4 | 86.6 | 1
2 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bharatpur to Accommodate FHTC | SM/11534 | Augmentation | Construction of Boundary wall at 2nd T/W site for Augmentation of Bharatpur Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000568/2023-2024 | 613/Bon | 08/08/2023 | 29/08/2023 | ONKAR ENTERPRISE. | 4.08 | 0 | 0 | 0
3 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bharatpur to Accommodate FHTC | SM/11534 | Augmentation | Construction of Approach Road Head Work at site for Augmentation of Bharatpur Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000639/2023-2024 | 622/Bon | 08/08/2023 | 20/08/2023 | SAMBHU RAY CHOWDHURY. | 1.51 | 0.74 | 48.69 | 100
4 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bharatpur to Accommodate FHTC | SM/11534 | Augmentation | Formal work order for laying of DI/UPVC distribution pipe line and Providing Functional House Hold Tap Connection (FHTC) for Augmentation of Bharatpur Water Supply Scheme under Bongaon Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000773/2022-2023 | 3470/BD | 01/12/2022 | 01/03/2023 | ONKAR ENTERPRISE. | 140.49 | 140.43 | 99.95 | 1
5 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bharatpur to Accommodate FHTC | SM/11534 | Augmentation | Acceptance cum work order for Construction of 150 cum. capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile, pile cap & Soil Investigation within command area for Augmentation of Bharatpur Water Supply Scheme under Bongaon Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000884/2023-2024 | 2793/BD | 12/09/2023 | 11/09/2024 | B.M.ENGINEERING. & CONSTRUCTION. | 91.92 | 22.21 | 24.16 | 0
6 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bharatpur to Accommodate FHTC | SM/11534 | Augmentation | Construction of Approach Road at 2ndT/W site for Augmentation of Bharatpur Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000968/2023-2024 | 556/Bon | 18/07/2023 | 02/08/2023 | GHOSH CONSTRUCTION. | 0.92 | 0.46 | 49.99 | 100
7 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bharatpur to Accommodate FHTC | SM/11534 | Augmentation | Acceptance cum work order for Renovation and repairing of Boundary wall at Head Work site for Augmentation of Bharatpur Water Supply Scheme, Bongaon Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001742/2023-2024 | 538/BD | 21/02/2024 | 06/04/2024 | LAXMEE ENTERPRISE | 7.27 | 3.59 | 49.43 | 100
8 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bharatpur to Accommodate FHTC | SM/11534 | Augmentation | Route Survey, Design Drawing & Preparation of DPR for Bharatpur Water Supply Scheme in Bongaon Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002773/2021-2022 | 126/Bon | 18/02/2022 | 05/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 2.98 | 2.98 | 100 | 1
9 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bharatpur to Accommodate FHTC | SM/11534 | Augmentation | Repairing & Renovation of 01No. Pump House and allied works at Bharatpur water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002938/2021-2022 | 633/BON | 31/12/2021 | 21/01/2022 | GHOSH CONSTRUCTION. | 1.26 | 1.2 | 95.24 | 1
10 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bharatpur to Accommodate FHTC | SM/11534 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000097/2022-2023 | 3666/BD | 13/12/2022 |  | Resource Division | 7.57 | 0 | 0 | 0
11 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bharatpur to Accommodate FHTC | SM/11534 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000118/2022-2023 | 3692/BD | 14/12/2022 |  | Resource Division | 0.41 | 0 | 0 | 0
12 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Bharatpur to Accommodate FHTC | SM/11534 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Replacement) under Bharatpur W/S Scheme, Patua W/S Scheme (P/H-I & II) & Chaital W/S Scheme (P/H -I & II) District of 24 Pgs. (N). NIET No. 24 of EE/EMD of 2022-23 (Sl. No.- 04) |  |  | ORD/000824/2022-2023 | 31/EMD | 03/01/2023 | 02/02/2023 | M/S P.P. ELECTRICALS | 74.67 | 0 | 0 | 0
Total | [13 empty] | 347.4 | 184 | 52.96