## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Sangrampur to accommodate FHTC | SM/11605 | Augmentation | Enhancement of GST for providing Functional Household Tap Connection (FHTC) in connection with JJM and Jal Swapna Programme within command area of Sangrampur WS Scheme |  |  | BILL/00831/2024-2025 | null | 10/09/2024 |  | H.I.ENTERPRISE. | 34.82 | 0 | 0 | 0
2 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Sangrampur to accommodate FHTC | SM/11605 | Augmentation | Formal work order for Laying of DI/UPVC distribution system pipeline and Providing FHTC (Functional Household Tap Connection)for augmentation of Sangrampur water supply scheme in Basirhat-I block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000681/2022-2023 | 3196/BD | 01/11/2022 | 30/01/2023 | H.I.ENTERPRISE. | 654.07 | 622.19 | 95.13 | 83
3 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Sangrampur to accommodate FHTC | SM/11605 | Augmentation | Construction of AIRP for Sangrampur Ground Water Based Water Supply Scheme at Basirhat Bolck. | Assistant Engineer | Junior Engineer | ORD/001132/2015-2016 | 3406/BD | 04/08/2015 | 02/08/2020 | MONDAL PRECISION PVT.LTD | 61.62 | 0 | 0 | 10
4 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Sangrampur to accommodate FHTC | SM/11605 | Augmentation | Acceptance cum work order for Design, Construction & Commissioning of Arsenic cum Iron removable Plant (AIRP) capable of reducing Raw water arsenic and iron concentration up to applicable limit on the basis of the departmental process drawing including 3(three) months Trial Run and 9 (nine) months Operation & maintenance for Sangrampur Ground Water Based Water Supply Scheme at Basirhat-I Bolck in the District of North 24 Pgs. under Barasat Division, P.H.E. Dte.(Capacity- 126.80M3). | Assistant Engineer | Junior Engineer | ORD/001149/2015-2016 | 3406/BD | 04/08/2015 | 31/01/2016 | MONDAL PRECISION PVT.LTD | 124.99 | 15.31 | 12.25 | 80
5 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Sangrampur to accommodate FHTC | SM/11605 | Augmentation | Acceptance cum work order for construction of CWR at Sangrampur W/S scheme under Basirhat Sub-Division, P.H.E. Dte. under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001165/2021-2022 | 333/BD | 02/02/2022 | 19/03/2022 | MD AMIRUL MOLLA. | 5.2 | 4.49 | 86.5 | 1
6 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Sangrampur to accommodate FHTC | SM/11605 | Augmentation | Route Survey, Design Drawing & DPR Preparation for SANGRAMPUR Water Supply Scheme in Basirhat-I Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002895/2021-2022 | 195/BHT SD | 28/02/2022 | 15/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.84 | 4.84 | 100 | 1
7 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Sangrampur to accommodate FHTC | SM/11605 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000003/2023-2024 | 1101/BD | 06/04/2023 |  | Resource Division | 92.65 | 0 | 0 | 0
8 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Sangrampur to accommodate FHTC | SM/11605 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000072/2023-2024 | 1659/BD | 05/06/2023 |  | Resource Division | 10.04 | 0 | 0 | 0
9 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Sangrampur to accommodate FHTC | SM/11605 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000136/2022-2023 | 3811/BD | 23/12/2022 |  | Resource Division | 83.52 | 0 | 0 | 0
10 | NORTH 24 PARAGANAS |  | Central Drilling | Augmentation of ground water based piped water supply scheme for Sangrampur to accommodate FHTC | SM/11605 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 17/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
11 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Sangrampur to accommodate FHTC | SM/11605 | Augmentation | New Service Connectio for Sangrampur W/S Scheme |  |  | BILL/00012/2022-2023 | 96/EMD | 29/11/2022 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.46 | 0 | 0 | 0
12 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Sangrampur to accommodate FHTC | SM/11605 | Augmentation | Providing outdoor Illumination arrangement at P.H. - High Lift under Sangrampur W/S Scheme, Dist 24pgs(N). |  | Junior Engineer | ORD/000040/2023-2024 | 1328/EMSD-I | 31/05/2023 | 15/06/2023 | DAS ENTERPRISE (BARANAGAR) | 2.21 | 2.18 | 98.76 | 100
13 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Sangrampur to accommodate FHTC | SM/11605 | Augmentation | Supply & Installation of Automatically Controlled Diaphragm type Chlorinator at PH-H/L under Sangrampur (AIRP) W/S Scheme under Eastern Mechanical Sub-Division-I, PHE Dte. Dist. 24 Pgs. (N). |  | Junior Engineer | ORD/000041/2023-2024 | 1329/EMSD-I | 31/05/2023 | 20/06/2023 | T.N. BANERJEE | 2.99 | 0 | 0 | 0
14 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Sangrampur to accommodate FHTC | SM/11605 | Augmentation | New service connection charge for Sangrampur |  |  | VCH/003340/2022-2023 | null | 14/11/2022 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.46 | 0 | 0 | 0
Total | [13 empty] | 22423.62 | 649.01 | 2.89