## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Itinda Panitor to accommodate FHTC | SM/11626 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Itinda Panitor water supply scheme in Basirhat-I Block under Barasat Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/001119/2022-2023 | 429/BD | 13/02/2023 | 14/05/2023 | ALOK ENTERPRSE. (A UNIT OF SAKET TREXIM PVT.LTD) | 662.31 | 182.01 | 27.48 | 24
2 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Itinda Panitor to accommodate FHTC | SM/11626 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000153/2023-2024 | 4414/BD | 10/11/2023 |  | Resource Division | 18.48 | 0 | 0 | 0
3 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Itinda Panitor to accommodate FHTC | SM/11626 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000197/2022-2023 | 857/BD | 20/03/2023 |  | Resource Division | 190.23 | 0 | 0 | 0
4 | NORTH 24 PARAGANAS |  | Central Drilling | Augmentation of ground water based piped water supply scheme for Itinda Panitor to accommodate FHTC | SM/11626 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 270 Mtrs. Depth) by utilising Departmental Machineries for Itinda Panitar W/S Scheme (T/W-I) , Basirhat-I Block under North 24 Pgs. District, Central Drilling Division, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000168/2023-2024 | 117/CDD | 17/04/2023 | 17/05/2023 | SUNRISE ENGINEERING CORPORATION | 19.94 | 0 | 0 | 0
5 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Itinda Panitor to accommodate FHTC | SM/11626 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied electro- mechanical works and chlorinator(in connection with Aug. work related to FHTC) at Pump House No.II under Itindapanitor W/S Scheme District of 24 Pgs. (N) |  |  | ORD/001894/2022-2023 | 6387 / EMD | 14/08/2022 | 13/09/2022 | RAJLAXMI ELECTRICAL WORKS | 13.04 | 9.48 | 72.72 | 1
6 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Itinda Panitor to accommodate FHTC | SM/11626 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I (Replacement) under Itinda-Panitor W/S Scheme District of 24 Pgs. (N). (SM/11626) NIET No.- 19 of EE/EMD of 2022-23 (Sl. No.- 11) |  |  | ORD/002035/2022-2023 | 6386/ EMD | 14/08/2022 | 13/09/2022 | GLACIER ENGINEERING CO. | 13.04 | 8.22 | 63.06 | 1
Total | [13 empty] | 917.05 | 199.72 | 21.78