## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Ghona to accommodate FHTC | SM/11627 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and Providing FHTC (Functional Household Tap Connection ) by augmentation for Ghona water supply scheme in Basirhat-II Block of North 24 Parganas District under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000685/2022-2023 | 3184/BD | 01/11/2022 | 30/01/2023 | SHIBU BISWAS. | 179.98 | 117.11 | 65.07 | 85
2 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Ghona to accommodate FHTC | SM/11627 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000144/2022-2023 | 3821/BD | 23/12/2022 |  | Resource Division | 27.91 | 0 | 0 | 0
3 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Ghona to accommodate FHTC | SM/11627 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000160/2023-2024 | 4405/BD | 10/11/2023 |  | Resource Division | 3.08 | 0 | 0 | 0
4 | NORTH 24 PARAGANAS |  | Central Drilling | Augmentation of ground water based piped water supply scheme for Ghona to accommodate FHTC | SM/11627 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 17/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
Total | [13 empty] | 21550.74 | 117.11 | 0.54