## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Matiagachha to accommodate FHTC | SM/11667 | Augmentation | Acceptance cum work order for Repairing and renovation works of 200 cum. capacity 20mtr. Staging height R.C.C. Over Head water Reservoir for Augmentation of Matiagachha Water Supply Scheme, Habra-II Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000010/2024-2025 | 1535/BD | 07/06/2024 | 22/07/2024 | B.S.ENTERPRISE. (BASIRHAT) | 13.15 | 6.55 | 49.84 | 100
2 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Matiagachha to accommodate FHTC | SM/11667 | Augmentation | Formal work order fior Laying of DI rising main, UPVC distribution pipe line and Providing Functional Household Tap Connection for augmentation of Matiagacha Water Supply Scheme under Bongaon Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000033/2023-2024 | 1356/BD | 04/05/2023 | 02/08/2023 | M/S R.K. ENTERPRISE | 231.73 | 114.33 | 49.34 | 80
3 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Matiagachha to accommodate FHTC | SM/11667 | Augmentation | Acceptance cum work order for Repairing of Boundary wall and Construction of Approach Road at Head Work site & 2nd Pump House site under Augmentation of Matiagachha Water Supply Scheme, Habra-II Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001746/2023-2024 | 563/BD | 22/02/2024 | 07/04/2024 | M/S SANDHYA CONSTRUCTION | 9.88 | 4.93 | 49.93 | 100
4 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Matiagachha to accommodate FHTC | SM/11667 | Augmentation | Route Survey, Design Drawing & DPR Preparation for Matiagacha W/S Scheme in Habra - II Block under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002763/2021-2022 | 128/HAB | 16/03/2022 | 26/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.35 | 3.27 | 97.43 | 1
5 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Matiagachha to accommodate FHTC | SM/11667 | Augmentation | Repairing & Renovation of 01No. Pump House and allied works at Matiagacha water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002937/2021-2022 | 530/BON | 03/11/2021 | 24/11/2021 | KAMAL HALDER. | 2.52 | 2.5 | 99.18 | 1
6 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Matiagachha to accommodate FHTC | SM/11667 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000007/2023-2024 | 1252/BD | 25/04/2023 |  | Resource Division | 8.28 | 0 | 0 | 0
7 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Matiagachha to accommodate FHTC | SM/11667 | Augmentation | Payment of invoice bill for new service connection at PH-III under Matiagacha W/S Scheme. |  |  | BILL/04811/2023-2024 | BP-303-23-24 | 04/03/2024 |  | W.B.S.E.D.C.L. (GANGANAGAR C.C.C.) | 3.94 | 0 | 0 | 0
8 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Matiagachha to accommodate FHTC | SM/11667 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No. II under Matigacha (Block:-Barasat-II) W/S Scheme District of 24 Pgs. (N) N.I.E.T No. 27 of EE / EMD of 2022-2023 (2022_PHED_431015_28) |  |  | ORD/001888/2023-2024 | 6731/EMD | 28/11/2023 | 28/12/2023 | M.D. ENTERPRISE | 10.69 | 0 | 0 | 0
9 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Matiagachha to accommodate FHTC | SM/11667 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I & II Matiagacha (Block-Habra II) W/S Scheme and Pump House No.I & II Ashudi W/S scheme District of 24 Pgs. (N) |  |  | ORD/001915/2023-2024 | 6738/EMD | 29/11/2023 | 29/12/2023 | M/S S.R. ENTERPRISE | 42.55 | 0 | 0 | 0
Total | [13 empty] | 326.08 | 131.58 | 40.35