## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Bajitpur Zone-I to accommodate FHTC | SM/11756 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Bajitpur Zone-I B water supply scheme in Baduria Block under Barasat Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000004/2023-2024 | 1124/BD | 11/04/2023 | 10/07/2023 | SHIBU BISWAS. | 209.36 | 142.53 | 68.08 | 82
2 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Bajitpur Zone-I to accommodate FHTC | SM/11756 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of (Bajitpur Zone-I A) water supply scheme in Baduria Block under Barasat Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000133/2023-2024 | 1709/BD | 08/06/2023 | 06/09/2023 | UTPAL CONSTRUCTION & CO. | 356.76 | 58.78 | 16.48 | 42
3 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Bajitpur Zone-I to accommodate FHTC | SM/11756 | Augmentation | Acceptance cum work order for Sinking of 1 no. 300 mm. x 200 mm. big dia. 300 mtr deep tubewell by D.R. Rig method using PVC pipe & strainer having 300 mm dia. 36 mtr. long filter for Augmentation of Bajitpur Zone-IB water supply scheme in Baduria Block of Basirhat Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000987/2023-2024 | 2802/BD | 12/09/2023 | 12/10/2023 | DHELA BABA ENTERPRISE | 21.53 | 0 | 0 | 0
4 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Bajitpur Zone-I to accommodate FHTC | SM/11756 | Augmentation | Acceptance cum work order for Renovation of Arsenic cum Iron Removal Plant at Bazitpur zone - I W/S Scheme including increasing the height of back wash water tank at Baduria Block under Basirhat Sub Division, PHE Dte. Capacity- 91.50 Cum/hr. | Assistant Engineer |  | ORD/002027/2023-2024 | 928/BD | 15/03/2024 | 14/05/2024 | RITE WATER SOLUTIONS (I) PVT.LTD. | 21.65 | 0 | 0 | 0
5 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Bajitpur Zone-I to accommodate FHTC | SM/11756 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000020/2023-2024 | 1242/BD | 25/04/2023 |  | Resource Division | 95.52 | 0 | 0 | 0
6 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Bajitpur Zone-I to accommodate FHTC | SM/11756 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000060/2023-2024 | 1625/BD | 01/06/2023 |  | Resource Division | 9.22 | 0 | 0 | 0
7 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Bajitpur Zone-I to accommodate FHTC | SM/11756 | Augmentation | New connection charges for P.H. No.-I under Bajitpur Uttarpara |  |  | BILL/00011/2022-2023 | 121/EMD | 30/12/2022 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.73 | 0 | 0 | 0
8 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Bajitpur Zone-I to accommodate FHTC | SM/11756 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electrio-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Zone-I) (Replacement) under Bajitpur W/S Scheme & Bamangachi W/S Scheme (P/H-I, II, III & IV) District of 24 Pgs. (N). NIET No.- 24 of EE/EMD of 2022-23 (Sl. No. -01) |  |  | ORD/000822/2022-2023 | 29/EMD | 03/01/2023 | 02/02/2023 | SUNRISE ENGINEERING CORPORATION | 67.59 | 0 | 0 | 100
Total | [13 empty] | 782.36 | 201.31 | 25.73