## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Gokulpur to accommodate FHTC | SM/11759 | Augmentation | Formal work order for Laying of UPVC distribution pipe line and Providing FHTC (Functional Household Tap Connection ) by augmentation for Gokulpur water supply scheme in Swarupnagar block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001245/2022-2023 | 1039/BD | 31/03/2023 | 29/06/2023 | UTPAL CONSTRUCTION & CO. | 411.53 | 280.33 | 68.12 | 70
2 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Gokulpur to accommodate FHTC | SM/11759 | Augmentation | Route Survey, Design Drawing & DPR Preparation for Gokulpur Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002757/2021-2022 | 448/ BHTSD | 23/03/2022 | 20/08/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.32 | 4.32 | 100 | 1
3 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Gokulpur to accommodate FHTC | SM/11759 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000012/2023-2024 | 1243/BD | 25/04/2023 |  | Resource Division | 15.85 | 0 | 0 | 0
4 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Gokulpur to accommodate FHTC | SM/11759 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000191/2022-2023 | 605/BD | 23/02/2023 |  | Resource Division | 20.7 | 0 | 0 | 0
5 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Gokulpur to accommodate FHTC | SM/11759 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Replacement) under Daora, Diara & Gokulpur W/S Scheme, District of 24 Pgs. (N). NIET No. 24 of EE/EMD of 2022-23 (Sl. No.- 07) | Assistant Engineer | Junior Engineer | ORD/000828/2022-2023 | 34/EMD | 03/01/2023 | 02/02/2023 | AHALYA ENGINEERING WORKS | 70.02 | 0 | 0 | 76
Total | [13 empty] | 522.42 | 284.65 | 54.49