## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Dakshin Bhebia Zone-II to accommodate FHTC | SM/12277 | Augmentation | Damage of road namely Kharampur Uttar Amtala More Bhabhanipur Dakshin Chimta bhabanipur Ghat (Strenthening & improvement of RIDF road from Ghuni Banstala to Bailani Bazar |  |  | BILL/00851/2024-2025 | null | 11/09/2024 |  | EXECUTIVE ENGINEER (HPIU), WBSRDA ,BARASAT DIVISION | 35.17 | 0 | 0 | 0
2 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Dakshin Bhebia Zone-II to accommodate FHTC | SM/12277 | Augmentation | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line, Construction of 700 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap and providing Functional Household Tap Connection in connection with Augmentaion of Dakshin Bhebia water supply scheme (Zone-II), Hasnabad Block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000780/2023-2024 | 2592/BD | 28/08/2023 | 22/08/2024 | H.I.ENTERPRISE. | 1098.89 | 559.38 | 50.9 | 69
3 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Dakshin Bhebia Zone-II to accommodate FHTC | SM/12277 | Augmentation | Acceptance cum work order for Restoration of 225 mm dia. UPVC pipe line due to construction of drain at Kharampur more within Dakshin Bhebia W/S Scheme (Z-II), Hasnabad block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001298/2023-2024 | 1420/HSD | 06/11/2023 | 13/11/2023 | SARKAR ENTERPRISE | 0.92 | 0 | 0 | 100
4 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Dakshin Bhebia Zone-II to accommodate FHTC | SM/12277 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000119/2023-2024 | 4173/BD | 30/10/2023 |  | Resource Division | 37.95 | 0 | 0 | 0
5 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Dakshin Bhebia Zone-II to accommodate FHTC | SM/12277 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000166/2023-2024 | 4559/BD | 01/12/2023 |  | Resource Division | 74.49 | 0 | 0 | 0
6 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Dakshin Bhebia Zone-II to accommodate FHTC | SM/12277 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000239/2022-2023 | 912/BD | 22/03/2023 |  | Resource Division | 163.73 | 0 | 0 | 0
7 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Dakshin Bhebia Zone-II to accommodate FHTC | SM/12277 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.III (Chimta)(Rep.) and IV(New) (Zone-II) under Dakshin Bhebia W/S Scheme District of 24 Pgs. (N) |  |  | ORD/001291/2023-2024 | 4941/EMD | 18/08/2023 | 17/09/2023 | ESENCE ENGINEERING CONCERN | 26.47 | 0 | 0 | 0
Total | [13 empty] | 1437.6 | 559.38 | 38.91