## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Dakshin Chatra Zone-I to accommodate FHTC | SM/12568 | Augmentation | Road Restoration work |  |  | BILL/00857/2024-2025 | null | 12/09/2024 |  | EXECUTIVE ENGINEER-II, P.W.D,BARASAT DIVN | 76.63 | 0 | 0 | 0
2 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Dakshin Chatra Zone-I to accommodate FHTC | SM/12568 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Dakshin Chatra Zone-I water supply scheme in Baduria Block under Barasat Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000023/2023-2024 | 1210/BD | 20/04/2023 | 19/07/2023 | ALOK ENTERPRSE. (A UNIT OF SAKET TREXIM PVT.LTD) | 971.71 | 360.63 | 37.11 | 38
3 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Dakshin Chatra Zone-I to accommodate FHTC | SM/12568 | Augmentation | Supply of Sluice valve (200 mm) including construction of Sluice valve chamber for Augmentation of Dakshin Chatra Zone-I Water Supply Scheme under Basirhat Sub Division , P.H.E. Dte. under Barasat Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000075/2024-2025 | 928/BHTSD | 24/05/2024 | 31/05/2024 | ROHAN MONDAL. | 0.97 | 0 | 0 | 0
4 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Dakshin Chatra Zone-I to accommodate FHTC | SM/12568 | Augmentation | Laying of HDPE pipe line and Repairing of DI pipelines including supply of Sluice valve (200 mm) for interconnection of AIRP under Augmentation work of Dakshin Chatra Zone-I Water Supply Scheme under Basirhat Sub Division , P.H.E. Dte. under Barasat Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000079/2024-2025 | 929/BHTSD | 24/05/2024 | 31/05/2024 | S.R.M. ENTERPRISE. | 1 | 0 | 0 | 0
5 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Dakshin Chatra Zone-I to accommodate FHTC | SM/12568 | Augmentation | Dismantling of a dilapidated Room due to construction of Bio Eco Tech Plant at the Head Work site of Dakshin Chatra Zone - I Water Supply Scheme under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000093/2024-2025 | 942/BHTSD | 24/05/2024 | 31/05/2024 | N.R.ENTERPRISE. | 0.97 | 0 | 0 | 0
6 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Dakshin Chatra Zone-I to accommodate FHTC | SM/12568 | Augmentation | Hiring Diesel Luxury Car on daily basis (for 06 months from 01.01.2023 to 30.06.2023) for the office use of the Assistant Engineer, Basirhat Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001343/2022-2023 | 1420 /BHTSD | 30/12/2022 | 29/06/2023 | OM ENTERPRISE | 0.86 | 2.33 | 271.36 | 100
7 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Dakshin Chatra Zone-I to accommodate FHTC | SM/12568 | Augmentation | Formal work order for In-Situ Bio Eco Tech Based Ground Water Treatment Plant for Arsenic & Iron Contaminated Areas of Dakshin Chatra Zone-I Water Supply Scheme under BAduria Block of North 24 Parganas District on Pilot basis & subsequent O & M for 15(Fifteen) years. | Assistant Engineer | Junior Engineer | ORD/001358/2016-2017 | 96/BD | 13/01/2017 | 02/02/2017 | UNITED WATERS INDIA PVT LTD. | 1640.17 | 31.24 | 1.9 | 65
8 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Dakshin Chatra Zone-I to accommodate FHTC | SM/12568 | Augmentation | Route Survey, Design Drawing & DPR Preparation for DAKSHIN CHATRA ZONE -1 Water Supply Scheme in Baduria Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001979/2021-2022 | 351/BHTSD | 14/03/2022 | 29/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.95 | 4.95 | 100 | 1
9 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Dakshin Chatra Zone-I to accommodate FHTC | SM/12568 | Augmentation | Additional Survey work for DPR Preparation for DAKSHIN CHATRA ZONE -1 Water Supply Scheme in Baduria Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001980/2021-2022 | 352/BHTSD | 14/03/2022 | 29/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 1.38 | 1.36 | 98.73 | 1
10 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Dakshin Chatra Zone-I to accommodate FHTC | SM/12568 | Augmentation | Continuation Work for Hiring Diesel Luxury Car on daily basis for the office use of the Assistant Engineer, Basirhat Sub-Division P.H.E. Dte. (Period: 01.01.2024 to 30.06.2024 for Six Month) | Assistant Engineer | Junior Engineer | ORD/002197/2023-2024 | 1290/BHTSD | 29/12/2023 | 28/06/2024 | DEB KUMAR DAS. | 0.86 | 1.51 | 174.74 | 100
11 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Dakshin Chatra Zone-I to accommodate FHTC | SM/12568 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000023/2023-2024 | 1254/BD | 25/04/2023 |  | Resource Division | 260.28 | 0 | 0 | 0
12 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Dakshin Chatra Zone-I to accommodate FHTC | SM/12568 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000063/2023-2024 | 1632/BD | 01/06/2023 |  | Resource Division | 48.44 | 0 | 0 | 0
13 | NORTH 24 PARAGANAS |  | Central Drilling | Augmentation of ground water based piped water supply scheme for Dakshin Chatra Zone-I to accommodate FHTC | SM/12568 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 17/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 7.49 | 0.04 | 11
14 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Dakshin Chatra Zone-I to accommodate FHTC | SM/12568 | Augmentation | Providing power distribution arrangement with allied works at P.H.No- I ,Zone-I of Dakshin Chatra Ground water based W/S Scheme under EMD ,PHE Dte.in 24Pgs(N). | Assistant Engineer | Junior Engineer | ORD/001801/2023-2024 | 6459/EMD | 02/11/2023 | 02/12/2023 | PIONEER ELECTRICALS | 12.91 | 5 | 38.7 | 100
15 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Dakshin Chatra Zone-I to accommodate FHTC | SM/12568 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No II (Rep.) (Zone-I and II) under Dakshin Chatra W/S Scheme District of 24 Pgs. (N) |  |  | ORD/001911/2023-2024 | 6734/EMD | 29/11/2023 | 29/12/2023 | CONCORD ENGINEERING | 26.08 | 0 | 0 | 0
Total | [13 empty] | 24386.95 | 414.51 | 1.7