## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Shimla Durgapur to accommodate FHTC | SM/12569 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and Providing Functional Household Tap Connection for Augmentation of Simla Durgapur Zone-I water supply scheme in Baduria Block under Barasat Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000037/2023-2024 | 1355/BD | 04/05/2023 | 02/08/2023 | CHANCHAL ENTERPRISE & CO. | 300.04 | 184.34 | 61.44 | 71
2 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Shimla Durgapur to accommodate FHTC | SM/12569 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Simla Durgapur (Zone-II)water supply scheme in Baduria Block under Barasat Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000158/2023-2024 | 1717/BD | 08/06/2023 | 06/09/2023 | UTPAL CONSTRUCTION & CO. | 446.82 | 129.09 | 28.89 | 48
3 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Shimla Durgapur to accommodate FHTC | SM/12569 | Augmentation | Acceptance cum work order for Sinking of 1 no. 300 mm. x 200 mm. big dia. 300 mtr deep tubewell by D.R. Rig method using PVC pipe & strainer having 300 mm dia. 36 mtr. long filter for Augmentation of Shimla Durgapur Zone-II water supply scheme in Baduria Block of Basirhat Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer |  | ORD/001003/2023-2024 | 2804/BD | 12/09/2023 | 12/10/2023 | SAHA CONSTRUCTION & CO | 21.53 | 0 | 0 | 0
4 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Shimla Durgapur to accommodate FHTC | SM/12569 | Augmentation | Route Survey, Design Drawing & DPR Preparation for SIMLA DURGAPUR Water Supply Scheme in Baduria Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001995/2021-2022 | 376/BHTSD | 16/03/2022 | 31/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.96 | 4.96 | 100 | 1
5 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Shimla Durgapur to accommodate FHTC | SM/12569 | Augmentation | Additional survey work for DPR Preparation for SIMLA DURGAPUR Water Supply Scheme in Baduria Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002897/2021-2022 | 377/BHTSD | 16/03/2022 | 31/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 1.66 | 1.65 | 99.06 | 1
6 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Shimla Durgapur to accommodate FHTC | SM/12569 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000026/2023-2024 | 1247/BD | 25/04/2023 |  | Resource Division | 49.35 | 0 | 0 | 0
7 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Shimla Durgapur to accommodate FHTC | SM/12569 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000062/2023-2024 | 1626/BD | 01/06/2023 |  | Resource Division | 44.17 | 0 | 0 | 0
8 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Shimla Durgapur to accommodate FHTC | SM/12569 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000070/2023-2024 | 1647/BD | 02/06/2023 |  | Resource Division | 13.76 | 0 | 0 | 0
9 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Shimla Durgapur to accommodate FHTC | SM/12569 | Augmentation | New Service Connection for PH No.-under Simla Durgapur |  |  | BILL/00008/2022-2023 | 128/EMD | 09/01/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.46 | 0 | 0 | 0
10 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Shimla Durgapur to accommodate FHTC | SM/12569 | Augmentation | Supply delivery installation and commissioning of electro-mechanical machineries in connection with installation of IARP in Shimla-Durgapur W/S Scheme under EMD, PHE Dte. Dist. 24 Pgs N |  |  | ORD/000068/2013-2014 | 2398/EMD | 31/12/2013 | 31/03/2014 | WEST BENGAL ENGINEERING CO. | 24.24 | 0 | 0 | 100
11 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Shimla Durgapur to accommodate FHTC | SM/12569 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I, II and III (Rep.) under Shimla-Durgapur W/S Scheme and Aturia W/S Scheme District of 24 Pgs. (N) |  |  | ORD/001164/2023-2024 | 4814/EMD | 09/08/2023 | 08/09/2023 | ORIENTAL ENGINEERING CO. | 78.18 | 0 | 0 | 0
12 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Shimla Durgapur to accommodate FHTC | SM/12569 | Augmentation | New connection charges for Simladurgapur W/s scheme. Memo no. 1006507278/Quot/03 |  |  | VCH/003379/2022-2023 | null | 21/11/2022 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.46 | 0 | 0 | 0
Total | [13 empty] | 991.64 | 320.05 | 32.27