## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandpur to accommodate FHTC. | SM/13313 | Augmentation | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line and providing Functional Household Tap Connection in connection with Augmentation of Chandpur water supply scheme (Zone-I), Hasnabad Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000007/2023-2024 | 1150/BD | 13/04/2023 | 12/07/2023 | M/S NIRMAN CONSTRUCTION. | 318.37 | 81.44 | 25.58 | 36
2 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandpur to accommodate FHTC. | SM/13313 | Augmentation | Acceptance cum work order for Construction of switch room cum chlorine room with sanitary and water supply arrangement including plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No.-2 (Size-3.60x3.00 mtr.) for Augmentation of Chandpur w/s scheme (Z-II), Hasnabad block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000078/2023-2024 | 1429/BD | 11/05/2023 | 10/07/2023 | PRITAM MUKHOPADHYAY. | 17.32 | 8.57 | 49.49 | 85
3 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandpur to accommodate FHTC. | SM/13313 | Augmentation | Formal work order for Construction of 150 Cum capacity 20 mtr staging height R.C.C Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap in connection with Augmentation of Chandpur water supply scheme (Zone-I), Hasnabad Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000337/2024-2025 | 2329/BD | 16/08/2024 | 16/08/2025 | GOPINATH ENTERPRISES | 100.59 | 0 | 0 | 0
4 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandpur to accommodate FHTC. | SM/13313 | Augmentation | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line and Providing Functional Household Tap Connection in Connection with Augmentation of Chandpur water supply scheme (Zone-II), Hasnabad Block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001066/2022-2023 | 402/BD | 09/02/2023 | 10/05/2023 | MONDAL & CO. (BASIRHAT). | 318.72 | 275.33 | 86.39 | 60
5 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandpur to accommodate FHTC. | SM/13313 | Augmentation | Formal work order for Construction of 500 cum capacity 20 mtr staging height R.C.C Over Head Reservoir as per Deptt. design, drawing & specification including bored pile with pile cap in connection with Augmentation of Chandpur water supply scheme (Zone-II), Hasnabad Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001096/2023-2024 | 2866/BD | 20/09/2023 | 19/09/2024 | MONDAL & CO. (BASIRHAT). | 202.58 | 35.29 | 17.42 | 75
6 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandpur to accommodate FHTC. | SM/13313 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 300 mtr deep Tubewell by D.R. Rig method at PH No.-1 & 2 with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Chandpur w/s scheme (Z-II), Hasnabad block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/001180/2022-2023 | 793/BD | 13/03/2023 | 12/04/2023 | M/S RAJPATH CONSTRUCTION. | 42.88 | 10.84 | 25.27 | 100
7 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandpur to accommodate FHTC. | SM/13313 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.-1 & 2 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Chandpur w/s scheme (Z-I), Hasnabad block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001664/2023-2024 | 294/BD | 30/01/2024 | 15/03/2024 | M/S K.P.PAL. | 51.76 | 11.52 | 22.25 | 100
8 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandpur to accommodate FHTC. | SM/13313 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000164/2023-2024 | 4511/BD | 28/11/2023 |  | Resource Division | 26.12 | 0 | 0 | 0
9 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandpur to accommodate FHTC. | SM/13313 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000237/2022-2023 | 928/BD | 22/03/2023 |  | Resource Division | 55.9 | 0 | 0 | 0
10 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandpur to accommodate FHTC. | SM/13313 | Augmentation | Quotation for Service Connection Charges for PH- I, Zone-II under Chandpur W/S Scheme in the district of North 24 Pgs. |  |  | BILL/04692/2023-2024 | BP-287-23-24 | 21/02/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 7.55 | 0 | 0 | null
11 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandpur to accommodate FHTC. | SM/13313 | Augmentation | Quotation for Service Connection Charges for PH- II, Zone-II under Chandpur W/S Scheme in the district of North 24 Pgs. |  |  | BILL/04693/2023-2024 | BP-288-23-24 | 21/02/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.58 | 0 | 0 | null
12 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandpur to accommodate FHTC. | SM/13313 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I & II (Rep.) under Talsa and adj. mouzas W/S Scheme and Talsa W/S Scheme with Pump House No-I under Chandpur (Block-Hasnabad) W/S Scheme District of 24 Pgs. (N) | Assistant Engineer | Junior Engineer | ORD/001175/2023-2024 | 4803/EMD | 09/08/2023 | 08/09/2023 | M/S S.R. ENTERPRISE | 60.76 | 0 | 0 | 80
13 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandpur to accommodate FHTC. | SM/13313 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sinkinng Tube Well in connection to Accommodate FHTC at Pump House No.-I , II Zone-II under Chandpur ground water based water supply scheme under Block_ Hasnabad Dist. - North 24 Parganas under EMD, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002817/2023-2024 | 805/EMD | 11/03/2024 | 10/04/2024 | UNIVERSAL ENTERPRISES | 24.76 | 10.78 | 43.53 | 0
Total | [13 empty] | 1228.9 | 433.77 | 35.3