## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based Bamangachi PWSS to accommodate FHTC | SM/13468 | Augmentation | Engagement of Sluice Valves Operator for Bamangachhi Water Supply Scheme under Barasat Sub Division P.H.E. Dte. Period for 01/07/2024 to 31/12/2024 = 6 months = 184 days. |  | Junior Engineer | ORD/000052/2024-2025 | 270/BSD | 28/06/2024 | 25/12/2024 | DEBRAJ ENTERPRISE | 1.49 | 0 | 0 | 0
2 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based Bamangachi PWSS to accommodate FHTC | SM/13468 | Augmentation | Different works in connection with Augmentation Bamangachi PWSS (1st Tubewell - Pump House, Boundary Wall & Service Road). | Assistant Engineer | Junior Engineer | ORD/000427/2024-2025 | 559/BSD | 09/09/2024 | 29/09/2024 | SANTU GHOSH. | 4.87 | 0 | 0 | 0
3 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based Bamangachi PWSS to accommodate FHTC | SM/13468 | Augmentation | Different works in connection with Augmentation Bamangachi PWSS (2nd Tubewell - Pump House, Boundary Wall & Service Road). | Assistant Engineer | Junior Engineer | ORD/000428/2024-2025 | 560/BSD | 09/09/2024 | 29/09/2024 | TALUKDER & CO. | 4.64 | 0 | 0 | 0
4 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based Bamangachi PWSS to accommodate FHTC | SM/13468 | Augmentation | Preparation of DPR in connection of augumentation of Bamangachhi Water Supply Scheme under Barasat Sub Division, P.H.E. Dte. Sl. No.-02 | Assistant Engineer | Junior Engineer | ORD/000604/2022-2023 | 657/BSD | 18/08/2022 | 17/09/2022 | RADIANT | 3 | 1.36 | 45.25 | 100
5 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based Bamangachi PWSS to accommodate FHTC | SM/13468 | Augmentation | Formal work order for construction of 250 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap and laying of Rising main & distribution pipe line by DI & UPVC and providing FHTC for Augmentaion of Bamangachhi water supply scheme under Barasat Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000772/2023-2024 | 2650/BD | 01/09/2023 | 26/08/2024 | S.S.ENTERPRISE. (BAMANGACHI) | 538.69 | 264.37 | 49.08 | 100
6 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based Bamangachi PWSS to accommodate FHTC | SM/13468 | Augmentation | Acceptance cum work order for Sinking of 1 (one) no. 250 mm. x 150 mm. big dia. 210 mtr deep Tubewell by D.R. Rig method having 250 mm dia 42.0 mtr. long PVC housing pipe & 150 mm dia 30.0 mtr. long filter for Augmentation Bamangachhi Water Supply Scheme (2nd T/W Site) of Barasat Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001771/2023-2024 | 588/BD | 23/02/2024 | 24/03/2024 | SUBHAJIT SAHA | 11.22 | 5.44 | 48.48 | 100
7 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based Bamangachi PWSS to accommodate FHTC | SM/13468 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000110/2023-2024 | 3092/BD | 10/10/2023 |  | Resource Division | 12.26 | 0 | 0 | 0
8 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based Bamangachi PWSS to accommodate FHTC | SM/13468 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000124/2023-2024 | 4368/BD | 10/11/2023 |  | Resource Division | 21.03 | 0 | 0 | 0
9 | NORTH 24 PARAGANAS |  | Central Drilling | Augmentation of Ground water based Bamangachi PWSS to accommodate FHTC | SM/13468 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well (250mm X150mm X 300 Mtrs. Depth) by utilising Departmental Machineries for Bamanghachhi W/S Scheme (T/W-I&II), Barasat-I Block under North 24 Pgs District, Central Drilling Division, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000184/2023-2024 | 900/CDD | 18/07/2023 | 17/08/2023 | UNIVERSAL ENTERPRISES | 33.24 | 6 | 18.04 | 37
10 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of Ground water based Bamangachi PWSS to accommodate FHTC | SM/13468 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electrio-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Zone-I) (Replacement) under Bajitpur W/S Scheme & Bamangachi W/S Scheme (P/H-I, II, III & IV) District of 24 Pgs. (N). NIET No.- 24 of EE/EMD of 2022-23 (Sl. No. -01) |  |  | ORD/000822/2022-2023 | 29/EMD | 03/01/2023 | 02/02/2023 | SUNRISE ENGINEERING CORPORATION | 67.59 | 13.6 | 20.12 | 100
Total | [13 empty] | 698.05 | 290.76 | 41.65