## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Berachampa Zone-3 Piped Water Supply Scheme | SM/13894 | Augmentation | Formal work order for Construction of 450 cum capacity 20 Mtr. staging height RCC Over Head Reservoir and laying of Rising main & distribution pipe line by DI & UPVC and providing FHTC for augmentation of Berachampa Zone-III Water Supply Scheme under Barasat Sub Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000565/2023-2024 | 2449/BD | 16/08/2023 | 10/08/2024 | H.I.ENTERPRISE. | 621.51 | 118.52 | 19.07 | 35
2 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Berachampa Zone-3 Piped Water Supply Scheme | SM/13894 | Augmentation | Detail route survey, design of distribution network and preparation of estimate, drawing & DPR for providing FHTC in the scheme of Berachampa Water Supply Scheme Zone-III under Barasat Sub Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000609/2022-2023 | 668/BSD | 25/08/2022 | 24/09/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.73 | 3.73 | 100 | 1
3 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Berachampa Zone-3 Piped Water Supply Scheme | SM/13894 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different village of verious PWSS of Deganga Block within Barasat Sub Division under Barasat Division, P.H.E. Dte. Part-E | Assistant Engineer | Junior Engineer | ORD/001847/2023-2024 | 1120/BSD | 09/02/2024 | 13/02/2024 | S.M.TRADERS. | 0.87 | 0.44 | 50 | 100
4 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Berachampa Zone-3 Piped Water Supply Scheme | SM/13894 | Augmentation | Acceptance cum work order for Sinking of 1 (one) no. 300 mm. x 200 mm. big dia. 185 mtr deep Tube well by D.R. Rig method having 300 mm dia 42.0 mtr. long PVC housing pipe & 200 mm dia 30.0 mtr. long filter for Augmentation Berachampa Zone-III Water Supply Scheme (Head Work Site) of Barasat Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001926/2023-2024 | 803/BD | 12/03/2024 | 11/04/2024 | ACME CONSTRUCTION | 13.08 | 6.19 | 47.35 | 100
5 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Berachampa Zone-3 Piped Water Supply Scheme | SM/13894 | Augmentation | Construction of Pump House with latrine at Berachampa Zone-III water Supply Scheme under Deganga Block size of 5.40m x 3.60m within Barasat Sub Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002152/2023-2024 | 1243/BSD | 15/03/2024 | 14/04/2024 | D.K.CONSTRUCTION | 4.91 | 0 | 0 | 0
6 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Berachampa Zone-3 Piped Water Supply Scheme | SM/13894 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000105/2023-2024 | 3088/BD | 10/10/2023 |  | Resource Division | 17.77 | 0 | 0 | 0
7 | NORTH 24 PARAGANAS |  | Central Drilling | Augmentation of Berachampa Zone-3 Piped Water Supply Scheme | SM/13894 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 17/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
8 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of Berachampa Zone-3 Piped Water Supply Scheme | SM/13894 | Augmentation | New service connection at P.H.No- I ,Zone- III of Berachampa water supply scheme under EMSD-I ,PHE Dte .im24Pgs(N). |  |  | BILL/04805/2023-2024 | BP-305-23-24 | 04/03/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.64 | 0 | 0 | null
Total | [13 empty] | 22006.28 | 128.88 | 0.59