## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based Joypul Piped water supply scheme to accommodate FHTC | SM/15324 | Augmentation | Acceptance cum work order for Construction of Pump House with latrine at Joypul water Supply Scheme under Barasat-I Block size of 5.40m x 3.60m within Barasat Sub Division, P.H.E.Dte. | Assistant Engineer |  | ORD/000106/2024-2025 | 1922/BD | 09/07/2024 | 08/08/2024 | CHAKRABORTY SUPPLIERS & CONSTRUCTION. | 5.09 | 0 | 0 | 0
2 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based Joypul Piped water supply scheme to accommodate FHTC | SM/15324 | Augmentation | Continuation work order for Hiring 1(one) no. Diesel Luxary Car on daily basis (for 01.05.2023 to 31.08.2023) for office use of the Assistant Engineer, R.W.S Barasat Sub-Division, P.H.E. Dte | Assistant Engineer |  | ORD/000108/2023-2024 | 382/BST | 27/04/2023 | 28/08/2023 | DEBAPRASAD MONDAL. | 0.58 | 1.03 | 177.1 | 0
3 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based Joypul Piped water supply scheme to accommodate FHTC | SM/15324 | Augmentation | Continuation work order for Hiring 1(One) No. Diesel Luxury Car on Daily basis for 6 (six) months for the office use of the Assistant Engineer, Barasat Sub Division, P.H.E. Dte. @ Rs. 475.00 (Rupees four hundred and seventy five only) per day excluding fuel. (Period from 01/09/2024 to 28/02/2024) |  | Junior Engineer | ORD/000377/2024-2025 | 504/BSD | 29/08/2024 | 25/02/2025 | ANJALI ENTERPRISE. | 0.86 | 0 | 0 | 0
4 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based Joypul Piped water supply scheme to accommodate FHTC | SM/15324 | Augmentation | Different works in connection with Augmentation Joypul PWSS (1st Tubewell - Boundary Wall & Service Road). | Assistant Engineer | Junior Engineer | ORD/000436/2024-2025 | 567/BSD | 09/09/2024 | 29/09/2024 | CHAKRABORTY SUPPLIERS & CONSTRUCTION. | 3.12 | 0 | 0 | 0
5 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based Joypul Piped water supply scheme to accommodate FHTC | SM/15324 | Augmentation | Different works in connection with Augmentation Joypul PWSS (1st Tubewell - Pump House). | Assistant Engineer | Junior Engineer | ORD/000437/2024-2025 | 568/BSD | 09/09/2024 | 29/09/2024 | NEW MA TARA ENTERPRISE. | 2.95 | 0 | 0 | 0
6 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based Joypul Piped water supply scheme to accommodate FHTC | SM/15324 | Augmentation | Preparation of DPR in connection of augumentation of Joypul Water Supply Scheme under Barasat Sub Division, P.H.E. Dte. Sl. No.-01 | Assistant Engineer | Junior Engineer | ORD/000603/2022-2023 | 656/BSD | 18/08/2022 | 17/09/2022 | RADIANT | 3.73 | 0 | 0 | 100
7 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based Joypul Piped water supply scheme to accommodate FHTC | SM/15324 | Augmentation | Formal work order for Construction of 550cum capacity 20mtr staging height R.C.C Over Head Reservoir as per Departmental design, drawing and specification including bored pile & pile cap and laying of Rising main & distribution pipe line by DI & UPVC and Providing FHTC for Augmentation of Joypul water supply Scheme under Barasat Sub-Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000754/2023-2024 | 2549/BD | 23/08/2023 | 17/08/2024 | MONDAL ENTERPRISE. (BARASAT) | 650.34 | 106.85 | 16.43 | 35
8 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based Joypul Piped water supply scheme to accommodate FHTC | SM/15324 | Augmentation | Hiring 1(one) no. Diesel Luxary Car on daily basis (for 01.09.2023 to 29.02.2024) for office use of the Assistant Engineer, R.W.S, Barasat Sub- Division, P.H.E. Dte. | Assistant Engineer |  | ORD/001183/2023-2024 | 783/BST | 29/08/2023 | 27/02/2024 | DEBAPRASAD MONDAL. | 0.86 | 1.44 | 166.08 | 0
9 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based Joypul Piped water supply scheme to accommodate FHTC | SM/15324 | Augmentation | Hiring 1(One) No. Diesel Luxury Car on Daily basis. (for six months w.e.f. 08.09.2023) for the office use of the Assistant Engineer, Barasat Sub Division, P.H.E. Dte. | Assistant Engineer |  | ORD/001405/2023-2024 | 663/BSD | 07/09/2023 | 05/03/2024 | ANJALI ENTERPRISE. | 0.86 | 0.75 | 86.58 | 2
10 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based Joypul Piped water supply scheme to accommodate FHTC | SM/15324 | Augmentation | Laying of partly damaged UPVC pipe line at Nabajibonpally under Joypul Water Supply Scheme within Barasat Sub Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001854/2023-2024 | 1133/BSD | 12/02/2024 | 19/02/2024 | TALUKDER & CO. | 0.87 | 0.37 | 41.78 | 100
11 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based Joypul Piped water supply scheme to accommodate FHTC | SM/15324 | Augmentation | Hiring 1(One) No. Diesel Luxury Car on Daily basis for the office use of the Assistant Engineer, Barasat Sub Division, P.H.E. Dte. (For the Period from 08/03/2024 to 31/08/2024) | Assistant Engineer | Junior Engineer | ORD/002032/2023-2024 | 1215/BSD | 07/03/2024 | 30/08/2024 | ANJALI ENTERPRISE. | 0.84 | 1.22 | 146.26 | 0
12 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based Joypul Piped water supply scheme to accommodate FHTC | SM/15324 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000114/2023-2024 | 4023/BD | 12/10/2023 |  | Resource Division | 25.78 | 0 | 0 | 0
13 | NORTH 24 PARAGANAS |  | Central Drilling | Augmentation of Ground water based Joypul Piped water supply scheme to accommodate FHTC | SM/15324 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 17/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 2.84 | 0.01 | 11
14 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of Ground water based Joypul Piped water supply scheme to accommodate FHTC | SM/15324 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No. III (New) under Joypul W/S Scheme, District of 24 Pgs. (N). |  |  | ORD/001144/2023-2024 | 4747/EMD | 07/08/2023 | 06/09/2023 | T.S.CONSTRUCTION | 10.59 | 0 | 0 | 0
Total | [13 empty] | 22046.24 | 114.49 | 0.52