## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARAGANAS | Sandeshkhali - I | Barasat Division | Matbari Abad Piped Water Supply Scheme | SM/15825 | New | Formal work order for Construction of switch room cum chlorine room with sanitary & water supply arrangement including plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No-2 (Size-3.60x3.00 mtr.), Laying of DI rising main and DI/UPVC distribution pipe line, Providing Functional Household Tap Connection, Protection works for different dia. UPVC/DI distribution pipeline by UC bullah/Bamboo pile, Construction of 250 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap within Mathbari Abad W/S Scheme, Sandeshkhali-I Block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000900/2023-2024 | 2704/BD | 04/09/2023 | 29/08/2024 | M/S DATTA ENTERPRISE. | 442.43 | 152.65 | 34.5 | 85
2 | NORTH 24 PARAGANAS | Sandeshkhali - I | Barasat Division | Matbari Abad Piped Water Supply Scheme | SM/15825 | New | Acceptance cum work order for Temporary approach road for movement of winch machine and other allied machineries at Head Work site within Mathbari Abad W/S scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer |  | ORD/001910/2023-2024 | 282/HSD | 06/03/2024 | 16/03/2024 | M/S DATTA ENTERPRISE. | 0.84 | 0.42 | 49.41 | 22
3 | NORTH 24 PARAGANAS | Sandeshkhali - I | Barasat Division | Matbari Abad Piped Water Supply Scheme | SM/15825 | New | Acceptance cum work order for 1 no. pump connection at PH No.-2 in connection with Augmentation of Gabberia water supply scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/002481/2023-2024 | 35/HSD | 09/01/2024 | 19/01/2024 | ABDUL ALIM MONDAL. | 0.79 | 0 | 0 | 0
4 | NORTH 24 PARAGANAS | Sandeshkhali - I | Barasat Division | Matbari Abad Piped Water Supply Scheme | SM/15825 | New | Acceptance cum work order for 1 no. pump connection at PH No.-1 in connection with Augmentation of Gabberia water supply scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002482/2023-2024 | 36/HSD | 09/01/2024 | 19/01/2024 | ABDUL ALIM MONDAL. | 0.79 | 0 | 0 | 0
5 | NORTH 24 PARAGANAS | Sandeshkhali - I | Barasat Division | Matbari Abad Piped Water Supply Scheme | SM/15825 | New | Acceptance cum work order for Hiring of one no. DIESEL MOTOR CAB (BS-VI) on daily hire basis for use of the Assistant Engineer, HASNABAD SUB-DIVISION, PHE DTE. Period from 01.11.23 to 30.04.24 | Assistant Engineer | Junior Engineer | ORD/002507/2023-2024 | 1315/HSD | 30/10/2023 | 27/04/2024 | RANJIT KUMAR MANDAL | 0.86 | 2.26 | 261.65 | 0
6 | NORTH 24 PARAGANAS | Sandeshkhali - I | Barasat Division | Matbari Abad Piped Water Supply Scheme | SM/15825 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (MATBARI ABAD Water Supply Scheme) in SANDESHKHALI-I BLOCK under Barasat Division, PHE Dte. (PART-A). | Assistant Engineer | Junior Engineer | ORD/002744/2021-2022 | 348/HSD | 21/02/2022 | 08/03/2022 | TIYAS CONSULTANCY AND INFRASTRUCTURE PVT.LTD. | 4.83 | 4.83 | 100 | 1
7 | NORTH 24 PARAGANAS | Sandeshkhali - I | Barasat Division | Matbari Abad Piped Water Supply Scheme | SM/15825 | New | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (MATBARI ABAD Water Supply Scheme) in SANDESHKHALI-I BLOCK under Barasat Division, PHE Dte. (PART-B) | Assistant Engineer | Junior Engineer | ORD/002745/2021-2022 | 349/HSD | 21/02/2022 | 08/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.82 | 4.82 | 100 | 1
8 | NORTH 24 PARAGANAS | Sandeshkhali - I | Barasat Division | Matbari Abad Piped Water Supply Scheme | SM/15825 | New | Material Requisition To Resource Division |  |  | RTOR000232/2022-2023 | 868/BD | 22/03/2023 |  | Resource Division | 23.84 | 0 | 0 | 0
9 | NORTH 24 PARAGANAS | Sandeshkhali - I | Central Drilling | Matbari Abad Piped Water Supply Scheme | SM/15825 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 17/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
10 | NORTH 24 PARAGANAS | Sandeshkhali - I | Eastern Mechanical | Matbari Abad Piped Water Supply Scheme | SM/15825 | New | Service connection charges at PH-II under Mathbari Abad W/S Scheme |  |  | BILL/04756/2023-2024 | BP-295-23-24 | 27/02/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.79 | 0 | 0 | null
11 | NORTH 24 PARAGANAS | Sandeshkhali - I | Eastern Mechanical | Matbari Abad Piped Water Supply Scheme | SM/15825 | New | Quotation for Service Connection Charges for PH- I under Mathbari Abad W/S Scheme in the district of North 24 Pgs. |  |  | BILL/05538/2023-2024 | BP-364-23-24 | 21/03/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.37 | 0 | 0 | null
Total | [13 empty] | 21830.12 | 164.97 | 0.76