## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based Bodai Zone-I PWSS to accommodate FHTC | SM/18416 | Augmentation | Formal work order for Additional pipeline and other allied works as per revised LDS in connection with Augmentation of Bodai-I Water Supply Scheme under JJM programme in Amdanga block within Barasat Sub Division, P.H.E.Dte. | Assistant Engineer |  | ORD/000108/2024-2025 | 2580/BD | 05/09/2024 | 04/12/2024 | A.P POWER & CONCRETE | 325.89 | 0 | 0 | 0
2 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based Bodai Zone-I PWSS to accommodate FHTC | SM/18416 | Augmentation | Preparation of DPR in connection of augumentation of Bodai Water Supply Scheme Zone-I under Barasat Sub Division, P.H.E. Dte. Sl. No.-01 | Assistant Engineer | Junior Engineer | ORD/000287/2022-2023 | 548/BSD | 29/06/2022 | 29/07/2022 | RADIANT | 3.7 | 1.66 | 44.92 | 100
3 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based Bodai Zone-I PWSS to accommodate FHTC | SM/18416 | Augmentation | Formal work order for Construction of 900 cum capacity 20mtr Height R.C.C Over Head Reservoir and laying of Rising main & distribution pipe line by DI & UPVC and providing FHTC for Augmentation of Bodai Zone-I Water Supply Scheme under Barasat Sub-Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001196/2023-2024 | 3080/BD | 10/10/2023 | 04/10/2024 | PUSPA ENTERPRISE. | 1051.63 | 248.17 | 23.6 | 60
4 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based Bodai Zone-I PWSS to accommodate FHTC | SM/18416 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different village of verious PWSS of Amdanga Block within Barasat Sub Division under Barasat Division, P.H.E. Dte. Part-A | Assistant Engineer | Junior Engineer | ORD/001836/2023-2024 | 1116/BSD | 09/02/2024 | 13/02/2024 | BIBHAS PAL. | 0.88 | 0.88 | 99.99 | 89
5 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based Bodai Zone-I PWSS to accommodate FHTC | SM/18416 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different village of verious PWSS of Amdanga Block within Barasat Sub Division under Barasat Division, P.H.E. Dte. Part-B | Assistant Engineer | Junior Engineer | ORD/001838/2023-2024 | 1116./1/BSD | 09/02/2024 | 13/02/2024 | BIBHAS PAL. | 0.88 | 0.88 | 100 | 100
6 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based Bodai Zone-I PWSS to accommodate FHTC | SM/18416 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000111/2023-2024 | 3094/BD | 10/10/2023 |  | Resource Division | 26.86 | 0 | 0 | 0
7 | NORTH 24 PARAGANAS |  | Central Drilling | Augmentation of Ground water based Bodai Zone-I PWSS to accommodate FHTC | SM/18416 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 17/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
8 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of Ground water based Bodai Zone-I PWSS to accommodate FHTC | SM/18416 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No. III (Zone-I) (Rep.) under Bodai W/S Scheme District of 24 Pgs. (N) N.I.E.T No. 27 of EE / EMD of 2022-2023 (2022_PHED_431015_9) |  |  | ORD/001883/2023-2024 | 6727/EMD | 28/11/2023 | 28/12/2023 | S.G. ENTERPRISE | 13.13 | 0 | 0 | 0
9 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of Ground water based Bodai Zone-I PWSS to accommodate FHTC | SM/18416 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No. III (Zone-II) (Rep.) under Bodai W/S Scheme District of 24 Pgs. (N) N.I.E.T No. 27 of EE / EMD of 2022-2023 (2022_PHED_431015_10) |  |  | ORD/001884/2023-2024 | 6728/EMD | 28/11/2023 | 28/12/2023 | DEY ENTERPRISE | 13.15 | 0 | 0 | 0
10 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of Ground water based Bodai Zone-I PWSS to accommodate FHTC | SM/18416 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sinkinng Tube Well in connection to Accommodate FHTC at Pump House No.-IV , V Zone-I under Bodai ground water based water supply scheme under Block_ Amdanga Dist. - North 24PGS under EMD, PHE Dte. | Assistant Engineer |  | ORD/002949/2023-2024 | 804/EMD | 11/03/2024 | 10/04/2024 | ESENCE ENGINEERING CONCERN | 25.37 | 0 | 0 | 0
Total | [13 empty] | 22801.27 | 251.6 | 1.1