## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARAGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation under Jal Swapna for DIghari Water Supply Scheme in Bongaon Block of North 24 Parganas District. | SM/10098 | Augmentation | Laying of Distribution pipe line including all necessary works at distribution system and Providing Functional House Hold Tap Connection (FHTC) including supplying, laying, fitting, fixing of 15 mm NB PVC , Schedule 80/20 mm OD HDPE (PE 100, PN 16) pipe with all necessary works including proposed Rising Main system within command area of Dighari Water Supply Scheme under North 24 Parganas Water Supply Division-I PHE Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL),JUNIOR ENGINEER 1 | ORD/000035/2022-2023 | 669/NWSD-I | 26/05/2022 | 24/08/2022 | M/S. S.S. ENTERPRISE | 581.29 | 461.61 | 79.41 | 82
2 | NORTH 24 PARAGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation under Jal Swapna for DIghari Water Supply Scheme in Bongaon Block of North 24 Parganas District. | SM/10098 | Augmentation | Repair and renovation works of R.C.C. Elevated Reservoir of 550 Cum capacity at Head work site and other allied works at DIGHARI under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000114/2023-2024 | 1239/NWSD-I | 18/08/2023 | 17/10/2023 | MONDAL ENTERPRISE | 52.05 | 0 | 0 | 0
3 | NORTH 24 PARAGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation under Jal Swapna for DIghari Water Supply Scheme in Bongaon Block of North 24 Parganas District. | SM/10098 | Augmentation | Detail route Survey, Design and preparation of Augmentation DPR in connection with " Providing functional household tap connection to every Household with in Dighari Water Supply Scheme in North 24 Pgs. District under North 24 Pgs. W/S. Division-I P.H.E. Dte." | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000138/2021-2022 | 1185/NWSD-I | 31/12/2021 | 15/01/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.52 | 3.52 | 100 | 1
4 | NORTH 24 PARAGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation under Jal Swapna for DIghari Water Supply Scheme in Bongaon Block of North 24 Parganas District. | SM/10098 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000009/2022-2023 | 640/NWSD-I | 20/05/2022 |  | Resource Division | 18.63 | 0 | 0 | 0
5 | NORTH 24 PARAGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation under Jal Swapna for DIghari Water Supply Scheme in Bongaon Block of North 24 Parganas District. | SM/10098 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000017/2022-2023 | 674/NWSD-I | 26/05/2022 |  | Resource Division | 81.68 | 0 | 0 | 0
Total | [13 empty] | 737.17 | 465.13 | 63.1