## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARAGANAS |  | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bandipur Block- Barrackpur-II, Dist-North 24 Parganas. | SM/10109 | Augmentation | Laying of Distribution pipe line including all necessary works at distribution system and Providing Functional House Hold Tap Connection (FHTC) including supplying, laying, fitting, fixing of 15 mm NB PVC , Schedule 80/20 mm OD HDPE (PE 100, PN16) pipe with all necessary works including proposed Rising Main system within command area of Bandipur Water Supply Scheme under district North 24 Parganas Water Supply Division-I PHE Dte. | ASSISTANT ENGINEER (HQ-II) |  | ORD/000034/2022-2023 | 654/NWSD-I | 24/05/2022 | 22/08/2022 | UMWELT ENGINEER PRIVATE LIMITED | 548.41 | 546.29 | 99.61 | 70
2 | NORTH 24 PARAGANAS |  | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bandipur Block- Barrackpur-II, Dist-North 24 Parganas. | SM/10109 | Augmentation | Surging of 5 (five) nos existing big dia Tube well for Bandipur W/S Scheme at Barrackpore -II Block under North 24 Pgs.W/S Division-I, P.H.E. Dte. | ASSISTANT ENGINEER (HQ-II) |  | ORD/000052/2022-2023 | 891/NWSD-I | 26/07/2022 | 10/08/2022 | AQUATECH ENGINEER | 3.34 | 2.28 | 68.29 | 1
3 | NORTH 24 PARAGANAS |  | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bandipur Block- Barrackpur-II, Dist-North 24 Parganas. | SM/10109 | Augmentation | Sinking of 1 no. 300 mm. x 200 mm. dia. 300 mtr deep tubewell by D.R. Rig method at Bandipur Water Supply Scheme ( H/W site ) within the jurisdiction of North 24 Pgs Water Supply Division- I, P.H.E. Dte. | ASSISTANT ENGINEER (HQ-II) | JUNIOR ENGINEER (CIVIL) | ORD/000063/2023-2024 | 876/NWSD-I | 12/07/2023 | 11/08/2023 | AUXILIARY TUBEWELL DRILLER | 21.83 | 12.81 | 58.66 | 100
4 | NORTH 24 PARAGANAS |  | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bandipur Block- Barrackpur-II, Dist-North 24 Parganas. | SM/10109 | Augmentation | Detail route Survey, Design and preparation of Augmentation DPR in connection with " Providing functional household tap connection to every Household with in Bandipur Water Supply Scheme in North 24 Pgs. District under North 24 Pgs. W/S. Division-I P.H.E. Dte." | ASSISTANT ENGINEER (HQ-II) |  | ORD/000130/2021-2022 | 1180/NWSD-I | 31/12/2021 | 15/01/2022 | UMWELT ENGINEER PRIVATE LIMITED | 4.72 | 4.72 | 100 | 1
5 | NORTH 24 PARAGANAS |  | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bandipur Block- Barrackpur-II, Dist-North 24 Parganas. | SM/10109 | Augmentation | Repair and renovation works for 700 cum. capacity 20 mtr. staging height R.C.C. Over Head water Reservoir, Boundary wall, Pump House at H/W site and PH-II, III, IV, V with other allied works at Bandipur W/S Scheme under North 24 Pgs Water Supply Division- I, | ASSISTANT ENGINEER (HQ-II) | JUNIOR ENGINEER (CIVIL) | ORD/000142/2023-2024 | 1683/NWSD-I | 30/10/2023 | 29/12/2023 | B. S. ENTERPRISE | 45.68 | 22.34 | 48.91 | 100
6 | NORTH 24 PARAGANAS |  | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bandipur Block- Barrackpur-II, Dist-North 24 Parganas. | SM/10109 | Augmentation | Supply and installation of Display Board to be placeed at BILKANDA ZONE-I, BANDIPUR, BILKANDA ZONE-II, PATULIA and MOHANPUR, Zone-I-B (Telinipara), Zone-IA-II (Chak Kanthalia) pipe water supply scheme for Barrackpore-II Block under North 24 Pgs. Water Supply Division-I, PHE. Dte. | ASSISTANT ENGINEER (HQ-II) | JUNIOR ENGINEER (CIVIL) | ORD/000275/2023-2024 | 70/NWSD-I | 10/01/2024 | 09/02/2024 | BIBHAS PAL | 4.94 | 0 | 0 | 100
7 | NORTH 24 PARAGANAS |  | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bandipur Block- Barrackpur-II, Dist-North 24 Parganas. | SM/10109 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000004/2022-2023 | 610/NWSD-I | 17/05/2022 |  | Resource Division | 35.68 | 0 | 0 | 0
8 | NORTH 24 PARAGANAS |  | North 24 Pgs W/S Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bandipur Block- Barrackpur-II, Dist-North 24 Parganas. | SM/10109 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000038/2022-2023 | 1406/NWSD-I | 13/12/2022 |  | Resource Division | 15.16 | 0 | 0 | 0
Total | [13 empty] | 679.77 | 588.44 | 86.56