## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARAGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation for Bagangram Zone-I Water Supply Scheme in Bongaon Block of North 24 Pgs. District under North 24 Pgs. Water Supply Division-I, PHE Dte. | SM/10412 | Augmentation | Repair and renovation of Boundary wall for 40 m Length in 2nd Pump House site & Service road (50 Mtr. Length X 3 Mtr. Width at Head Works site at Bagangram Zone-I Water Supply scheme in Bongaon Block under North 24 Parganas water Supply Division-I, PHE Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000003/2023-2024 | 377/NWSD-I | 05/04/2023 | 20/05/2023 | GHOSH CONSTRUCTION | 8.32 | 0 | 0 | 60
2 | NORTH 24 PARAGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation for Bagangram Zone-I Water Supply Scheme in Bongaon Block of North 24 Pgs. District under North 24 Pgs. Water Supply Division-I, PHE Dte. | SM/10412 | Augmentation | Special repair and renovation of Pump House & allied works at Head Works Site & 2nd Tube Well Site at Bagangram Zone-I Water Supply scheme in Bongaon Block under North 24 Parganas water Supply Division-I, PHE Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000004/2023-2024 | 378/NWSD-I | 05/04/2023 | 20/05/2023 | GHOSH CONSTRUCTION | 5.25 | 4.24 | 80.74 | 70
3 | NORTH 24 PARAGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation for Bagangram Zone-I Water Supply Scheme in Bongaon Block of North 24 Pgs. District under North 24 Pgs. Water Supply Division-I, PHE Dte. | SM/10412 | Augmentation | Repair and renovation of Boundary wall for 40 m Length in 2nd Pump House site & Service road (50 Mtr. Length X 3 Mtr. Width at Head Works site at Bagangram Zone-I Water Supply scheme in Bongaon Block under North 24 Parganas water Supply Division-I, PHE Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000022/2023-2024 | 377/NWSD-I. | 05/04/2023 | 20/05/2023 | GHOSH CONSTRUCTION | 8.32 | 4.1 | 49.36 | 100
4 | NORTH 24 PARAGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation for Bagangram Zone-I Water Supply Scheme in Bongaon Block of North 24 Pgs. District under North 24 Pgs. Water Supply Division-I, PHE Dte. | SM/10412 | Augmentation | Special Repair and renovation of Pump House & Allied Works at Head Works site & 2nd Tube Well site at Bagangram Zone-I Water Supply scheme in Bongaon Block under North 24 Parganas water Supply Division-I, PHE Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000024/2023-2024 | 378/NWSD-I. | 05/04/2023 | 20/05/2023 | GHOSH CONSTRUCTION | 5.25 | 0 | 0 | 0
5 | NORTH 24 PARAGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation for Bagangram Zone-I Water Supply Scheme in Bongaon Block of North 24 Pgs. District under North 24 Pgs. Water Supply Division-I, PHE Dte. | SM/10412 | Augmentation | Laying of Distribution pipe line including all necessary works at distribution system & Providing Functional House hold Tap Connection (FHTC) including supplying, laying, fitting, fixing of 15 mm NB PVC, Schedule 80/20 mm OD HDPE (PE 100, PN 16) pipe with all necessary works including proposed Rising Main system within command area of BAGANGRAM ZONE-I Water Supply Scheme under North 24 Parganas Water Supply Division-I, PHE,Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000053/2022-2023 | 1094/NWSD-I | 12/09/2022 | 11/12/2022 | M/S. NANDY ENTERPRISES | 413.37 | 194.49 | 47.05 | 75
6 | NORTH 24 PARAGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation for Bagangram Zone-I Water Supply Scheme in Bongaon Block of North 24 Pgs. District under North 24 Pgs. Water Supply Division-I, PHE Dte. | SM/10412 | Augmentation | Survey, Design and preparation of Retrofitting DPR in connection with " Providing functional household tap connection to every Household under Bagangram Zone-I W/S scheme in North 24 Pgs. District under North 24 Pgs. W/S Sub-Division-I, P.H.E. Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000194/2021-2022 | 316/NWSD - I | 21/03/2022 | 28/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.24 | 4.24 | 100 | 1
7 | NORTH 24 PARAGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation for Bagangram Zone-I Water Supply Scheme in Bongaon Block of North 24 Pgs. District under North 24 Pgs. Water Supply Division-I, PHE Dte. | SM/10412 | Augmentation | Repair and renovation works of R.C.C. Elevaced Reservoir 350 cum & Boundary Wall for 234 m Length in Head Works site at Bagangram Zone-I Water Supply scheme in Bongaon Block under North 24 Parganas water Supply Division-I, PHE Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000199/2022-2023 | 316/NWSD-I | 20/03/2023 | 04/05/2023 | M/S. ASOKE GHOSH AND BROTHERS | 33.8 | 12.77 | 37.77 | 100
8 | NORTH 24 PARAGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation for Bagangram Zone-I Water Supply Scheme in Bongaon Block of North 24 Pgs. District under North 24 Pgs. Water Supply Division-I, PHE Dte. | SM/10412 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000053/2023-2024 | 1135/NWSD-I | 04/08/2023 |  | Resource Division | 122.72 | 0 | 0 | 0
9 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Providing FHTC (Functional Household Tap Connection) by augmentation for Bagangram Zone-I Water Supply Scheme in Bongaon Block of North 24 Pgs. District under North 24 Pgs. Water Supply Division-I, PHE Dte. | SM/10412 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Zone-I) (Rep) under Bagangram W/S Scheme District of 24 Pgs. (N) | Assistant Engineer | Junior Engineer | ORD/001154/2023-2024 | 4757/EMD | 07/08/2023 | 06/09/2023 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 26.48 | 7.68 | 29 | 60
Total | [13 empty] | 627.73 | 227.52 | 36.24