## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARAGANAS |  | North 24 Pgs W/S Division I | Operational charges of Mangal Pandey WTP Water Testing Laboratory related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/12048 | Support-WQMSP | Providing services for deputing resource person for supervision for desktop surveillance audit of NABL Accreditation as per ISO / IEC: 17025 : 2017, calibration of applicable analytical instruments & supply of reagents-consumables for Mangal Pandey Water Testing Laboratory under The Executive Engineer, North 24 Pgs. W/S Division-I, P.H.E Dte, Government of West Bengal. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER 1 | ORD/000040/2022-2023 | 731/NWSD-I | 09/06/2022 | 06/12/2022 | LAB ANALYTICS | 2.85 | 1.63 | 57.15 | 10
2 | NORTH 24 PARAGANAS |  | North 24 Pgs W/S Division I | Operational charges of Mangal Pandey WTP Water Testing Laboratory related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/12048 | Support-WQMSP | Engagement of Laboratory personnel for Day to Day water testing at Laboratory of Mangal Pandey Water Treatment Plant in the status of District Laboratory under North 24 Pgs. W/S Division-I, PHE. Dte for the period of 1 (One) year.(2nd Call) | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER 1 | ORD/000225/2021-2022 | 383/NWSD-I | 29/03/2022 | 30/03/2022 | M/S PHOENIX INFRASTRUCTURE | 11.2 | 10.59 | 94.58 | 100
Total | [13 empty] | 14.05 | 12.22 | 86.98