## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Emergency hiring of generator for Yass |  |  | ORD/000017/2021-2022 | 1231/EMSD I | 21/05/2021 | 21/05/2022 | BISALAXMI ENTERPRISE | 0.81 | 0.81 | 100 | 0
2 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | hiring charges of mobile DG set on emergency basis at PH-H/L Z-II under Hingalganj Aug W/S scheme on YAAS, T.No.641/EMSD-I, W.O-1342/EMSD-I |  |  | ORD/000065/2022-2023 | 1342/ SD I | 31/05/2022 | 31/05/2023 | BISALAXMI ENTERPRISE | 0.82 | 0.82 | 100 | 0
3 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | hiring charges of mobile siletn type DG set on emergency basis under Hingalganj W/S scheme |  |  | ORD/000074/2021-2022 | 1343/ EMSD-I | 31/05/2021 | 30/06/2021 | INDTECH ASSOCIATES | 0.73 | 0 | 0 | 0
4 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Supply and delivery of Caocl2 of kanaikathikanthaberia W/S for disinfecting of drinking water on situation YAAS. |  |  | ORD/000075/2021-2022 | 1327/ EMSD-I | 28/05/2021 | 27/06/2021 | KASHINATH PAL & CO. | 0.94 | 0 | 0 | 0
5 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Hiring charges of mobile silent type DG set open type DG set on emergency basis for the himgalganj W/S on the impending cyclonic storm YAAS under EMD |  |  | ORD/000076/2021-2022 | 1401/ EMSD-I | 04/06/2021 | 09/06/2021 | INDTECH ASSOCIATES | 0.73 | 0 | 0 | 0
6 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Emergency hiring charges of 1 no.45 KVA mobile silent DG set on the situation of cylone YASS 2021 at P.H.-H/L Z-II under Hingal ganj Aug. W/S Scheme |  |  | ORD/000089/2021-2022 | 1235/EMSD-I | 21/05/2021 | 20/06/2021 | BISALAXMI ENTERPRISE | 0.91 | 0 | 0 | 0
7 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Emergency hiring charges of 1 no.30 KVA mobile silent DG set on the situation of cylone Amphan 2020 at P.H.-H/L Z-II under Hingalganj Aug W/S Scheme |  |  | ORD/000091/2021-2022 | 1381/EMSD-I | 03/06/2021 | 08/06/2021 | BISALAXMI ENTERPRISE | 0.82 | 0 | 0 | 0
8 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Emergency Hiring charges of 1 no. 30 KVA mobile silent type DG set in the situation of cyclone YAAS 2021 at P.H.-I under Barunhat W/S Scheme |  |  | ORD/000092/2021-2022 | 1242/EMSD-I | 21/05/2021 | 20/06/2021 | AVINABA ENGINEERING CONCERN | 0.96 | 0 | 0 | 0
9 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Emergency Hiring charges of 1 no. 45 KVA mobile silent type DG set in the situation of cyclone YAAS 2021 at P.H.-H/L Z-II under HingalGanj Aug. W/S Scheme |  |  | ORD/000093/2021-2022 | 1304/EMSD-I | 27/05/2021 | 30/05/2021 | BISALAXMI ENTERPRISE | 0.82 | 0 | 0 | 0
10 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Emergency Hiring charges of 1 no. 45 KVA mobile silent type DG set in the situation of cyclone YAAS 2021 at P.H.-H/L Z-II under HingalGanj Aug. W/S Scheme |  |  | ORD/000094/2021-2022 | 1342/EMSD-I | 31/05/2021 | 03/06/2021 | BISALAXMI ENTERPRISE | 0.82 | 0 | 0 | 0
11 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Emergency Hiring charges of mobile silent type DG set in the situation of cyclone YAAS 2021 at under HingalGanj W/S Scheme |  |  | ORD/000095/2021-2022 | 1308/EMSD-I | 27/05/2021 | 31/05/2021 | INDTECH ASSOCIATES | 0.73 | 0 | 0 | 0
12 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Emergency Hiring charges of mobile silent type DG set in the situation of cyclone YAAS 2021 at under hingalganj W/S Scheme |  |  | ORD/000096/2021-2022 | 1263/EMSD-I | 24/05/2021 | 28/05/2021 | INDTECH ASSOCIATES | 0.82 | 0 | 0 | 0
13 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Emergency Hiring charges of mobile silent type DG set in the situation of cyclone YAAS 2021 at under Atapur W/S Scheme |  |  | ORD/000097/2021-2022 | 1264/EMSD-I | 24/05/2021 | 25/05/2021 | DIPALI CONSTRUCTION | 0.2 | 0 | 0 | 0
14 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Hiring charges of mobile Silent type DG set on emergency basis at Hingalganj W/S Scheme on YAAS, T.No.1061/EMD, W.O-1343/EMSD-I |  |  | ORD/000180/2021-2022 | 1343/ SD I | 31/05/2021 | 31/05/2022 | INDTECH ASSOCIATES | 0.73 | 0.73 | 100 | 0
15 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Supply delivery of Cacocl tablet at Kanaikathikantaberia W/S scheme, T.No.828/EMSD-I, W.O-1327/EMSD-I |  |  | ORD/000181/2021-2022 | 1327/Sd I | 28/05/2021 | 28/05/2022 | KASHINATH PAL & CO. | 0.94 | 0.94 | 100 | 0
16 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | hiring charges of mobile DG set on emergency basis Hingalganj W/S scheme on YASS, T.No.10/EMSD-I, W.O1401/EMSD-I |  |  | ORD/000182/2021-2022 | 1401/ SD I | 04/06/2021 | 04/06/2022 | INDTECH ASSOCIATES | 0.73 | 0.73 | 100 | 0
17 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | hiring charges of mobile DG set on emergency basis at PH-H/L under Hingalganj W/S scheme on YASS, T.No.211/EMSD-I, W.O1235/EMSD-I |  |  | ORD/000183/2021-2022 | 1235/ SD I | 21/05/2021 | 21/05/2022 | BISALAXMI ENTERPRISE | 0.91 | 0.91 | 100 | 0
18 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | hiring charges of mobile DG set on emergency basis at PH-H/L under Hingalganj Aug. W/S scheme on YAAS, T.No.869/EMSD-I, W.O-1381/EMSD-I |  |  | ORD/000184/2021-2022 | 1381/ SD I | 03/06/2021 | 03/06/2022 | BISALAXMI ENTERPRISE | 0.82 | 0.82 | 100 | 0
19 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | hiring charges of mobile DG set on emergency basis at PH-I under Barunhat W/S scheme on YAAS, T.No.377/EMSD-I, W.O-1242/EMSD-I |  |  | ORD/000185/2021-2022 | 1242/ SD I | 21/05/2021 | 21/05/2022 | AVINABA ENGINEERING CONCERN | 0.96 | 0.96 | 100 | 0
20 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | hiring charges of mobile DG set on emergency basis at PH-H/L Z-II under Hingalganj W/S scheme on YAAS, T.No.617/EMSD-I, W.O-1304/EMSD-I |  |  | ORD/000186/2021-2022 | 1304/ SD I | 27/05/2021 | 27/05/2022 | BISALAXMI ENTERPRISE | 0.82 | 0.82 | 100 | 0
21 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | hiring charges of mobile DG set on emergency basis at PH- under Hingalganj Aug W/S scheme on YAAS, T.No.952/EMSD-I, W.O-1308/EMSD-I |  |  | ORD/000187/2021-2022 | 1308/ SD I | 27/05/2021 | 27/05/2022 | INDTECH ASSOCIATES | 0.73 | 0.73 | 100 | 0
22 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | hiring charges of mobile DG set on emergency basis at PH- under HINGALGANJ W/S scheme on yaas, T.No.679/EMSD-I, W.O-1263/EMSD-I |  |  | ORD/000188/2021-2022 | 1263/ SD I | 24/05/2021 | 24/05/2022 | INDTECH ASSOCIATES | 0.82 | 0.82 | 100 | 0
23 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | hiring charges of mobile DG set on emergency basis at PH- under Atapur W/S scheme on yaas, T.No.833/EMSD-I, W.O-1264/EMSD-I |  |  | ORD/000189/2021-2022 | 1264/ SD I | 24/05/2021 | 24/05/2022 | DIPALI CONSTRUCTION | 0.2 | 0.2 | 100 | 0
24 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Supply & delivery of calcium hypochlorite Caocl2 tablets at diffrnt. P.H. for disinfection of drinking water at cyclone storm Amphan effected under EMSD-I under Gobindapur (Block-Bagdah, Dhanyakuria W/S Scheme. |  |  | ORD/001079/2020-2021 | 1007A/ EMSD-I | 28/05/2020 | 27/06/2020 | BIJAN ENTERPRISE | 0.85 | 0 | 0 | 0
25 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Restoration of external Illumination arrabgement after Amphan cyclone in diffrnt. PWSS under EMSD-II |  |  | ORD/001080/2020-2021 | 572/ EMSD-II | 14/09/2020 | 25/09/2020 | ABHISEK ENGINEERING CONCERN | 2.25 | 0 | 0 | 0
26 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Emergency hiring charges of 1 no. 30 KVA mobile siletn type DG set on the situation of Amphan 2020 at P.H.-I under Kola W/S scheme |  |  | ORD/001081/2020-2021 | 1018B/ EMSD-I | 29/05/2020 | 28/06/2020 | M/S DAS ENTERPRISE | 0.96 | 0 | 0 | 0
27 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Emergency hiring charges of 1 no.30 KVA mobile silent DG set on the situation of cylone Amphan 2020 at P.H.-I Z-III under Bongaon Municipal W/S Scheme |  |  | ORD/001088/2020-2021 | 995C/EMSD-I | 28/05/2020 | 27/06/2020 | ESENCE ENGINEERING CONCERN | 0.96 | 0 | 0 | 0
28 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Emergency hiring charges of 1 no.30 KVA mobile silent DG set on the situation of cylone Amphan 2020 at P.H.-I under Kaniara W/S Scheme |  |  | ORD/001089/2020-2021 | 998C/EMSD-I | 28/05/2020 | 27/06/2020 | ESENCE ENGINEERING CONCERN | 0.96 | 0 | 0 | 0
29 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Emergency hiring charges of 1 no.30 KVA mobile silent DG set on the situation of cylone Amphan 2020 at P.H.-I under Kaniara W/S Scheme |  |  | ORD/001090/2020-2021 | 991E/EMSD-I | 28/05/2020 | 27/06/2020 | ESENCE ENGINEERING CONCERN | 0.96 | 0 | 0 | 0
30 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Emergency hiring charges of 1 no.30 KVA mobile silent DG set on the situation of cylone Amphan 2020 at P.H.-I under Mollahati W/S Scheme |  |  | ORD/001091/2020-2021 | 993E/EMSD-I | 28/05/2020 | 27/06/2020 | ESENCE ENGINEERING CONCERN | 0.96 | 0 | 0 | 0
31 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Emergency hiring charges of 1 no.30 KVA mobile silent DG set on the situation of cylone Amphan 2020 at P.H.-I under Dhalani W/S Scheme |  |  | ORD/001092/2020-2021 | 997C/EMSD-I | 28/05/2020 | 27/06/2020 | ESENCE ENGINEERING CONCERN | 0.96 | 0 | 0 | 0
32 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Emergency hiring charges of 1 no.30 KVA mobile silent DG set on the situation of cylone Amphan 2020 at P.H.-I under Dighari W/S Scheme |  |  | ORD/001093/2020-2021 | 994E/EMSD-I | 28/05/2020 | 27/06/2020 | ESENCE ENGINEERING CONCERN | 0.96 | 0 | 0 | 0
33 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Emergency Hiring charges of 1 no. 30 KVA mobile silent type DG set in the situation of cyclone Amphan 2020 at under Matigacha W/S Scheme |  |  | ORD/001094/2020-2021 | 981A/EMSD-I | 22/05/2020 | 30/05/2020 | DAS ENTERPRISE (BARANAGAR) | 0.96 | 0 | 0 | 0
34 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Emergency Hiring charges of 1 no. 30 KVA mobile silent type DG set in the situation of cyclone Amphan 2020 at under Diara W/S Scheme |  |  | ORD/001095/2020-2021 | 983B/EMSD-I | 22/05/2020 | 30/05/2020 | BISALAXMI ENTERPRISE | 0.96 | 0 | 0 | 0
35 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Emergency Hiring charges of 1 no. 30 KVA mobile silent type DG set in the situation of cyclone Amphan 2020 at P.H.-I under Ashudi W/S Scheme |  |  | ORD/001096/2020-2021 | 980B/EMSD-I | 22/05/2020 | 30/05/2020 | DAS ENTERPRISE (BARANAGAR) | 0.96 | 0 | 0 | 0
36 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Supply delivery of Calcium Hypochlorite tablet at Gobindapur W/S Scheme, T.No.397/EMD, W.O-1007A/EMD |  |  | ORD/001124/2020-2021 | 1007A/ SD I | 28/05/2020 | 28/05/2021 | BIJAN ENTERPRISE | 0.85 | 0.85 | 100 | 0
37 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Restoration of external Illumination on Amphan in different W/S Scheme, T.No49/EMSD-I, W.O-572/EMSD-II |  |  | ORD/001125/2020-2021 | 572/ SD II | 14/09/2020 | 14/09/2021 | ABHISEK ENGINEERING CONCERN | 2.25 | 2.25 | 100 | 0
38 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Emergency hiring of 30 KVA Mobile silent DG Set on Amphan at PH-I under Kola W/S scheme, T.No.556/EMSD-I, W.O-1018B/EMSD-I |  |  | ORD/001126/2020-2021 | 1018B/ SD I | 29/05/2020 | 29/05/2021 | M/S DAS ENTERPRISE | 0.96 | 0.96 | 100 | 0
39 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | hiring charges of mobile DG set on emergency basis at PH-i Z-III under Bongaon Municipal W/S scheme on Amphan, T.No.579/EMSD-I, W.O-995C/EMSD-I |  |  | ORD/001127/2020-2021 | 995C/ SD I | 28/05/2020 | 28/05/2021 | ESENCE ENGINEERING CONCERN | 0.96 | 0.96 | 100 | 0
40 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | hiring charges of mobile DG set on emergency basis at PH-I under Kaniara W/S scheme on Amphan, T.No.598/EMSD-I, W.O-998C/EMSD-I |  |  | ORD/001128/2020-2021 | 998C/ SD I | 28/05/2020 | 28/05/2021 | ESENCE ENGINEERING CONCERN | 0.96 | 0.96 | 100 | 0
41 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | hiring charges of mobile DG set on emergency basis at PH-I Z-II under Ihhlampur W/S scheme on Amphan, T.No.577/EMSD-I, W.O-991E/EMSD-I |  |  | ORD/001129/2020-2021 | 991E/ SD I | 28/05/2020 | 28/05/2021 | ESENCE ENGINEERING CONCERN | 0.96 | 0.96 | 100 | 0
42 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | hiring charges of mobile DG set on emergency basis at PH-I under Mollahati W/S scheme on Amphan, T.No.578/EMSD-I, W.O-993E/EMSD-I |  |  | ORD/001130/2020-2021 | 993E/ SD I | 28/05/2020 | 28/05/2021 | ESENCE ENGINEERING CONCERN | 0.96 | 0.96 | 100 | 0
43 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | hiring charges of mobile DG set on emergency basis at PH-I under Dhalani W/S scheme on Amphan, T.No.580/EMSD-I, W.O-997C/EMSD-I |  |  | ORD/001131/2020-2021 | 997C/ SD I | 28/05/2020 | 28/05/2021 | ESENCE ENGINEERING CONCERN | 0.96 | 0.96 | 100 | 0
44 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | hiring charges of mobile DG set on emergency basis at PH-I under Dighari W/S scheme on Amphan, T.No.596/EMSD-I, W.O-994E/EMSD-I |  |  | ORD/001132/2020-2021 | 994E/ SD I | 28/05/2020 | 28/05/2021 | ESENCE ENGINEERING CONCERN | 0.96 | 0.96 | 100 | 0
45 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | hiring charges of mobile DG set on emergency basis at PH- under Hingalganj Aug W/S scheme on Amphan, T.No.436/EMSD-I, W.O-981A/EMSD-I |  |  | ORD/001133/2020-2021 | 981A/ SD I | 22/05/2020 | 22/05/2021 | DAS ENTERPRISE (BARANAGAR) | 0.96 | 0.96 | 100 | 0
46 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | hiring charges of mobile DG set on emergency basis at PH-i under Deara W/S scheme on Amphan, T.No.542/EMSD-I, W.O-983B/EMSD-I |  |  | ORD/001134/2020-2021 | 983B/ SD I | 22/05/2020 | 22/05/2021 | BISALAXMI ENTERPRISE | 0.96 | 0.96 | 100 | 0
47 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | hiring charges of mobile DG set on emergency basis at PH-I under Ashudi W/S scheme on Amphan, T.No.440/EMSD-I, W.O-980B/EMSD-I |  |  | ORD/001135/2020-2021 | 980B/ SD I | 22/05/2020 | 22/05/2021 | DAS ENTERPRISE (BARANAGAR) | 0.96 | 0.96 | 100 | 0
48 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Emergency Hiring of Mobile Silent DG Set on emergency basis On the Situation of Amphan at Different W/S Scheme under EMD |  |  | ORD/001136/2020-2021 | 102/EMSD-I | 19/05/2020 | 19/05/2021 | BISALAXMI ENTERPRISE | 9.67 | 0 | 0 | 0
49 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Emergency Hiring of Mobile Silent DG Set on emergency basis On the Situation of YAAS at Different W/S Scheme under EMD |  |  | ORD/001137/2020-2021 | 103/EMSD-I | 26/05/2020 | 26/05/2021 | ESENCE ENGINEERING CONCERN | 11.57 | 0 | 0 | 0
50 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Emergency Hiring of Mobile Silent DG Set on emergency basis On the Situation of Amphan at Different W/S Scheme under EMD |  |  | ORD/001138/2020-2021 | 110/EMSD-I | 21/05/2020 | 21/05/2021 | ESENCE ENGINEERING CONCERN | 11.57 | 0 | 0 | 0
51 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Supply & delivery at Cyclonic Storm Amphan affected areas |  |  | VCH/002684/2021-2022 | null | 11/02/2022 |  | BISALAXMI ENTERPRISE | 6.48 | 0 | 0 | 0
52 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Supply & delivery at Cyclonic Storm Amphan affected areas |  |  | VCH/002685/2021-2022 | null | 11/02/2022 |  | D.K. ELECTRIC | 6.14 | 0 | 0 | 0
53 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Supply & delivery at Cyclonic Storm Amphan affected areas |  |  | VCH/002686/2021-2022 | null | 11/02/2022 |  | DAS ENTERPRISE (BARANAGAR) | 5.77 | 0 | 0 | 0
54 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Supply & delivery at Cyclonic Storm Amphan affected areas |  |  | VCH/002687/2021-2022 | null | 11/02/2022 |  | GHOSH AND GHOSH | 1.07 | 0 | 0 | 0
55 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Supply & delivery at Cyclonic Storm Amphan affected areas |  |  | VCH/002688/2021-2022 | null | 11/02/2022 |  | H.K. DAS & CO. | 2.85 | 0 | 0 | 0
56 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Supply & delivery at Cyclonic Storm Amphan affected areas |  |  | VCH/002689/2021-2022 | null | 11/02/2022 |  | INDTECH ASSOCIATES | 7.46 | 0 | 0 | 0
57 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Supply & delivery at Cyclonic Storm Amphan affected areas |  |  | VCH/002690/2021-2022 | null | 11/02/2022 |  | M/S DAS ENTERPRISE | 4.81 | 0 | 0 | 0
58 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Supply & delivery at Cyclonic Storm Amphan affected areas |  |  | VCH/002691/2021-2022 | null | 11/02/2022 |  | MAA KALI ENTERPRISE | 0.84 | 0 | 0 | 0
59 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Supply & delivery at Cyclonic Storm Amphan affected areas |  |  | VCH/002692/2021-2022 | null | 11/02/2022 |  | STANDARD ENGINEERING | 0.94 | 0 | 0 | 0
60 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Operation & guarding DG set for Yaas |  |  | VCH/003076/2021-2022 | PFMS-Feb-22 | 09/02/2022 |  | H.K. DAS & CO. | 0.65 | 0 | 0 | 0
61 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Operation & guarding DG set for Amphan |  |  | VCH/003077/2021-2022 | PFMS-Feb-22 | 09/02/2022 |  | INDTECH ASSOCIATES | 0.84 | 0 | 0 | 0
62 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Operation & guarding DG set for Yaas |  |  | VCH/003078/2021-2022 | PFMS-Feb-22 | 09/02/2022 |  | BISALAXMI ENTERPRISE | 0.73 | 0 | 0 | 0
63 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Operation & guarding DG set for Yaas |  |  | VCH/003079/2021-2022 | PFMS-Feb-22 | 09/02/2022 |  | BISALAXMI ENTERPRISE | 0.89 | 0 | 0 | 0
64 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Operation & guarding DG set for Yaas |  |  | VCH/003080/2021-2022 | PFMS-Feb-22 | 09/02/2022 |  | BISALAXMI ENTERPRISE | 0.8 | 0 | 0 | 0
65 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Operation & guarding DG set for Yaas |  |  | VCH/003081/2021-2022 | PFMS-Feb-22 | 09/02/2022 |  | BISALAXMI ENTERPRISE | 0.7 | 0 | 0 | 0
66 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Operation & guarding DG set for Yaas |  |  | VCH/003082/2021-2022 | PFMS-Feb-22 | 09/02/2022 |  | BISALAXMI ENTERPRISE | 0.02 | 0 | 0 | 0
67 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Operation & guarding DG set for Yaas |  |  | VCH/003083/2021-2022 | PFMS-Feb-22 | 09/02/2022 |  | BISALAXMI ENTERPRISE | 0.83 | 0 | 0 | 0
68 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Operation & guarding DG set for Yaas |  |  | VCH/003084/2021-2022 | PFMS-Feb-22 | 09/02/2022 |  | BISALAXMI ENTERPRISE | 0.79 | 0 | 0 | 0
69 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Operation & guarding DG set for Yaas |  |  | VCH/003085/2021-2022 | PFMS-Feb-22 | 09/02/2022 |  | BISALAXMI ENTERPRISE | 0.86 | 0 | 0 | 0
70 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Carrying at Haringhata |  |  | VCH/003087/2021-2022 | PFMS-Feb-22 | 09/02/2022 |  | ABHISEK ENGINEERING CONCERN | 0.74 | 0 | 0 | 0
71 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Generator hiring for Amphan |  |  | VCH/003090/2021-2022 | PFMS-Feb-22 | 09/02/2022 |  | AVINABA ENGINEERING CONCERN | 0.73 | 0 | 0 | 0
72 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Operation & guarding DG set for Yaas |  |  | VCH/003093/2021-2022 | PFMS-Feb-22 | 09/02/2022 |  | DAS ENTERPRISE (BARANAGAR) | 0.81 | 0 | 0 | 0
73 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Operation & guarding DG set for Yaas |  |  | VCH/003094/2021-2022 | PFMS-Feb-22 | 09/02/2022 |  | DAS ENTERPRISE (BARANAGAR) | 0.49 | 0 | 0 | 0
74 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Operation & guarding DG set for Yaas |  |  | VCH/003095/2021-2022 | PFMS-Feb-22 | 09/02/2022 |  | H.K. DAS & CO. | 0.98 | 0 | 0 | 0
75 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Operation & guarding DG set for Yaas |  |  | VCH/003096/2021-2022 | PFMS-Feb-22 | 09/02/2022 |  | M/S G.P. ENTERPRISE | 0.43 | 0 | 0 | 0
76 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Carrying at Haringhata Bottling plant |  |  | VCH/003097/2021-2022 | PFMS-Feb-22 | 09/02/2022 |  | ABHISEK ENGINEERING CONCERN | 0.74 | 0 | 0 | 0
77 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Carrying at Haringhata |  |  | VCH/003100/2021-2022 | PFMS-Feb-22 | 09/02/2022 |  | ABHISEK ENGINEERING CONCERN | 0.83 | 0 | 0 | 0
78 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Operation & guarding DG set for Yaas |  |  | VCH/003101/2021-2022 | PFMS-Feb-22 | 09/02/2022 |  | DAS ENTERPRISE (BARANAGAR) | 0.8 | 0 | 0 | 0
79 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Operation & guarding DG set for Yaas |  |  | VCH/003102/2021-2022 | PFMS-Feb-22 | 09/02/2022 |  | DAS ENTERPRISE (BARANAGAR) | 0.93 | 0 | 0 | 0
80 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Operation & guarding DG set for Yaas |  |  | VCH/003103/2021-2022 | PFMS-Feb-22 | 09/02/2022 |  | DAS ENTERPRISE (BARANAGAR) | 0.73 | 0 | 0 | 0
81 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Hiring DG set at Kurulia |  |  | VCH/003105/2021-2022 | PFMS-Feb-22 | 23/02/2022 |  | BISALAXMI ENTERPRISE | 0.96 | 0 | 0 | 0
82 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Hiring DG set at Auldanga |  |  | VCH/003106/2021-2022 | PFMS-Feb-22 | 23/02/2022 |  | BISALAXMI ENTERPRISE | 0.96 | 0 | 0 | 0
83 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Hiring DG set at Chandpur |  |  | VCH/003107/2021-2022 | PFMS-Feb-22 | 23/02/2022 |  | BISALAXMI ENTERPRISE | 0.96 | 0 | 0 | 0
84 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Hiring DG set at Kuruli |  |  | VCH/003108/2021-2022 | PFMS-Feb-22 | 23/02/2022 |  | BISALAXMI ENTERPRISE | 0.96 | 0 | 0 | 0
85 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Hiring DG set at Boyra |  |  | VCH/003109/2021-2022 | PFMS-Feb-22 | 23/02/2022 |  | BISALAXMI ENTERPRISE | 0.96 | 0 | 0 | 0
86 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Hiring DG set at Paikpara |  |  | VCH/003110/2021-2022 | PFMS-Feb-22 | 23/02/2022 |  | BISALAXMI ENTERPRISE | 0.96 | 0 | 0 | 0
87 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Hiring DG set at Rupmari |  |  | VCH/003111/2021-2022 | PFMS-Feb-22 | 23/02/2022 |  | BISALAXMI ENTERPRISE | 0.7 | 0 | 0 | 0
88 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Hiring DG set at Panchita |  |  | VCH/003112/2021-2022 | PFMS-Feb-22 | 23/02/2022 |  | D.K. ELECTRIC | 0.96 | 0 | 0 | 0
89 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Hiring DG set at Bharatpur |  |  | VCH/003113/2021-2022 | PFMS-Feb-22 | 23/02/2022 |  | D.K. ELECTRIC | 0.61 | 0 | 0 | 0
90 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Hiring DG set at Krisnachandrapur |  |  | VCH/003114/2021-2022 | PFMS-Feb-22 | 23/02/2022 |  | D.K. ELECTRIC | 0.96 | 0 | 0 | 0
91 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Hiring DG set at ganrapota |  |  | VCH/003115/2021-2022 | PFMS-Feb-22 | 23/02/2022 |  | D.K. ELECTRIC | 0.96 | 0 | 0 | 0
92 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Hiring DG set at Sindrani |  |  | VCH/003117/2021-2022 | PFMS-Feb-22 | 23/02/2022 |  | D.K. ELECTRIC | 0.96 | 0 | 0 | 0
93 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Hiring DG set at Sindrani |  |  | VCH/003118/2021-2022 | PFMS-Feb-22 | 23/02/2022 |  | D.K. ELECTRIC | 0.96 | 0 | 0 | 0
94 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Hiring DG set at Gainpur |  |  | VCH/003119/2021-2022 | PFMS-Feb-22 | 23/02/2022 |  | DAS ENTERPRISE (BARANAGAR) | 0.96 | 0 | 0 | 0
95 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Hiring DG set at parmadan |  |  | VCH/003120/2021-2022 | PFMS-Feb-22 | 23/02/2022 |  | DAS ENTERPRISE (BARANAGAR) | 0.96 | 0 | 0 | 0
96 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Hiring DG set at Bagangram |  |  | VCH/003121/2021-2022 | PFMS-Feb-22 | 23/02/2022 |  | DAS ENTERPRISE (BARANAGAR) | 0.96 | 0 | 0 | 0
97 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Hiring DG set at Paschim panchberia |  |  | VCH/003122/2021-2022 | PFMS-Feb-22 | 23/02/2022 |  | DAS ENTERPRISE (BARANAGAR) | 0.96 | 0 | 0 | 0
98 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Hiring DG set at Paschim panchberia |  |  | VCH/003123/2021-2022 | PFMS-Feb-22 | 23/02/2022 |  | DAS ENTERPRISE (BARANAGAR) | 0.96 | 0 | 0 | 0
99 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Hiring DG set at Bagangram |  |  | VCH/003124/2021-2022 | PFMS-Feb-22 | 23/02/2022 |  | DAS ENTERPRISE (BARANAGAR) | 0.96 | 0 | 0 | 0
100 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Hiring DG set for Amphan at Barrackpore |  |  | VCH/003126/2021-2022 | PFMS-Feb-22 | 23/02/2022 |  | H.K. DAS & CO. | 0.96 | 0 | 0 | 0
101 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Hiring DG set for Amphan at Chowberia |  |  | VCH/003127/2021-2022 | PFMS-Feb-22 | 23/02/2022 |  | H.K. DAS & CO. | 0.96 | 0 | 0 | 0
102 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Hiring DG set for Amphan at Hingalganj |  |  | VCH/003129/2021-2022 | PFMS-Feb-22 | 23/02/2022 |  | INDTECH ASSOCIATES | 0.8 | 0 | 0 | 0
103 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Hiring DG set for Amphan at Palla |  |  | VCH/003130/2021-2022 | PFMS-Feb-22 | 23/02/2022 |  | INDTECH ASSOCIATES | 0.96 | 0 | 0 | 0
104 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Hiring DG set for Amphan at Icchlampur |  |  | VCH/003131/2021-2022 | PFMS-Feb-22 | 23/02/2022 |  | INDTECH ASSOCIATES | 0.96 | 0 | 0 | 0
105 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Hiring DG set for Amphan at kamarkella |  |  | VCH/003132/2021-2022 | PFMS-Feb-22 | 23/02/2022 |  | INDTECH ASSOCIATES | 0.96 | 0 | 0 | 0
106 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Hiring DG set for Amphan at Barrackpore |  |  | VCH/003133/2021-2022 | PFMS-Feb-22 | 23/02/2022 |  | INDTECH ASSOCIATES | 0.96 | 0 | 0 | 0
107 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Hiring DG set for Amphan at Santoshpur |  |  | VCH/003134/2021-2022 | PFMS-Feb-22 | 23/02/2022 |  | INDTECH ASSOCIATES | 0.96 | 0 | 0 | 0
108 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Hiring DG set for Amphan at santoshpur |  |  | VCH/003135/2021-2022 | PFMS-Feb-22 | 23/02/2022 |  | INDTECH ASSOCIATES | 0.96 | 0 | 0 | 0
109 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Hiring DG set for Amphan at kaniara |  |  | VCH/003137/2021-2022 | PFMS-Feb-22 | 23/02/2022 |  | M/S DAS ENTERPRISE | 0.96 | 0 | 0 | 0
110 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Hiring DG set for Amphan at Ghatpatila |  |  | VCH/003138/2021-2022 | PFMS-Feb-22 | 23/02/2022 |  | M/S DAS ENTERPRISE | 0.96 | 0 | 0 | 0
111 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Hiring DG set for Amphan at Bagda |  |  | VCH/003139/2021-2022 | PFMS-Feb-22 | 23/02/2022 |  | M/S DAS ENTERPRISE | 0.96 | 0 | 0 | 0
112 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Hiring DG set for Amphan at Hariharpur |  |  | VCH/003140/2021-2022 | PFMS-Feb-22 | 23/02/2022 |  | M/S DAS ENTERPRISE | 0.96 | 0 | 0 | 0
113 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Hiring DG set for Amphan at Helenchi |  |  | VCH/003141/2021-2022 | PFMS-Feb-22 | 23/02/2022 |  | M/S DAS ENTERPRISE | 0.96 | 0 | 0 | 0
114 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Arrangement of Drinking Water at Cyclonic Storm Amphan affected areas under Eastern Mechanical Division. | SM/08994 | Disaster | Hiring DG set for Amphan |  |  | VCH/003145/2021-2022 | PFMS-Feb-22 | 09/02/2022 |  | AVINABA ENGINEERING CONCERN | 0.73 | 0 | 0 | 0
Total | [13 empty] | 159.47 | 22.05 | 13.83