## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARAGANAS |  | Barasat Arsenic Division | Emergent restoration by repairing and renovation of existing pipeline, providing DG set and arrangement of temporary water supply through mechanised van for uninterrupted supply of drinking water to the extensively damaged ground W/S scheme of Baduria, Ha | SM/09030 | Disaster | Bullah Pilling for protection of Pipeline (Approx 60 m) near pond of Bulbul Fakir at Fakir Para under Konanagar W/S Scheme at Hasnabad Block due to Super Cyclone "AMPHAN" under Barasat Arsenic Division, P.H.E. Dte. | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000283/2021-2022 | 557/B.Ar.D | 23/03/2022 | 30/03/2022 | SAFE STEP ENTERPRISE | 3.87 | 0 | 0 | 0
2 | NORTH 24 PARAGANAS |  | Barasat Arsenic Division | Emergent restoration by repairing and renovation of existing pipeline, providing DG set and arrangement of temporary water supply through mechanised van for uninterrupted supply of drinking water to the extensively damaged ground W/S scheme of Baduria, Ha | SM/09030 | Disaster | Eucalyptus bullah pilling, drum sheet walling including earth filling for protection of different dia UPVC/HDPE Pipeline near pond of Pankoj Bhwomik , Jame Masjid at Maheshpur Majher para under Tildanga W/S Scheme at Baduria block due to Super Cyclone " AMPHAN" under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000284/2021-2022 | 558/B.Ar.D | 23/03/2022 | 30/03/2022 | R. K. MANDAL & CO. | 4.8 | 0 | 0 | 0
3 | NORTH 24 PARAGANAS |  | Barasat Arsenic Division | Emergent restoration by repairing and renovation of existing pipeline, providing DG set and arrangement of temporary water supply through mechanised van for uninterrupted supply of drinking water to the extensively damaged ground W/S scheme of Baduria, Ha | SM/09030 | Disaster | Eucalyptus bullah pilling, drum sheet walling including earth filling for protection of different dia UPVC/HDPE Pipeline near 2nd Pump House under Dwarir Jungle W/S Scheme at Sandeshkhali - II block due to Super Cyclone "Amphan" under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000285/2021-2022 | 559/B.Ar.D | 23/03/2022 | 30/03/2022 | R. K. MANDAL & CO. | 4.61 | 0 | 0 | 0
Total | [13 empty] | 13.28 | 0 | 0