## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARAGANAS |  | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for KRISHNAPARA to accommodate FHTC under Jal Swapna Mission under Hasnabad Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11706 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 17/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for KRISHNAPARA to accommodate FHTC under Jal Swapna Mission under Hasnabad Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11706 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I & II (Rep.) under Krishnapara W/S Scheme District of 24 Pgs. (N). N.I.E.T No. 27 of EE / EMD of 2022-2023 (2022_PHED_431015_27) |  |  | ORD/001886/2023-2024 | 6730/EMD | 28/11/2023 | 28/12/2023 | ASHUTOSH DAS & CO. | 0 | 0 | NAN | 0
3 | NORTH 24 PARAGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KRISHNAPARA to accommodate FHTC under Jal Swapna Mission under Hasnabad Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11706 | Augmentation | Laying of distribution System Including specials all Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area for Augmentation of Ground Based Water Supply Scheme at Krishnapara at Hasnabad Block in North 24 Pgs District under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000089/2022-2023 | 1558/B.Ar.D. | 24/08/2022 | 22/11/2022 | PALCON | 103.23 | 68.52 | 66.37 | 100
4 | NORTH 24 PARAGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KRISHNAPARA to accommodate FHTC under Jal Swapna Mission under Hasnabad Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11706 | Augmentation | Preparation of Augmentation DPR for Krishnapara Water Supply Scheme under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000108/2022-2023 | 1836/B.Ar.D | 19/09/2022 | 09/10/2022 | SIRCON ENGINEERING SERVICES | 0.98 | 0.98 | 99.43 | 1
5 | NORTH 24 PARAGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KRISHNAPARA to accommodate FHTC under Jal Swapna Mission under Hasnabad Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11706 | Augmentation | Construction of Remaining portion of boundary wall & allied works at Krishnapara Head Work site at Krishnapara Water Supply scheme of Hasnabad Block under Barasat Arsenic Division, P.H.E. Dte. | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000172/2023-2024 | 2657/B.Ar.D. | 09/11/2023 | 24/12/2023 | M/S DAS & CO | 8.62 | 4.28 | 49.66 | 100
6 | NORTH 24 PARAGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KRISHNAPARA to accommodate FHTC under Jal Swapna Mission under Hasnabad Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11706 | Augmentation | Repair and Renovation works of Existing R.C.C. Elevated Reservoir of Capacity 250 Cu.m. at Krishnapara W/S Scheme of Hasnababad Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000194/2022-2023 | 275/B.Ar.D. | 06/02/2023 | 07/04/2023 | M/S SANJAY ADHIKARI | 13.9 | 13.58 | 97.66 | 0
7 | NORTH 24 PARAGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KRISHNAPARA to accommodate FHTC under Jal Swapna Mission under Hasnabad Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11706 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000006/2022-2023 | 2108/B.Ar.D. | 02/11/2022 |  | Resource Division | 1.07 | 0 | 0 | 0
8 | NORTH 24 PARAGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KRISHNAPARA to accommodate FHTC under Jal Swapna Mission under Hasnabad Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11706 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000021/2022-2023 | 2295/B.Ar.D | 02/12/2022 |  | Resource Division | 7.71 | 0 | 0 | 0
Total | [13 empty] | 21475.28 | 87.35 | 0.41