## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for JASHAIKATI ZONE-II to accommodate FHTC under Jal Swapna Mission under Baduria Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11708 | Augmentation | New Service Connection at PH-III Z-II under Jashaikati W/ Scheme. |  |  | BILL/02683/2023-2024 | BP-167-23-24 | 19/09/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.86 | 0 | 0 | 0
2 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for JASHAIKATI ZONE-II to accommodate FHTC under Jal Swapna Mission under Baduria Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11708 | Augmentation | Supply Delivery Installation of Submersible Pumping Machinery alongwith allied Electro Mechanical works Voltage Stabilizer and Automatic Chlorinator in connection with Aug. work related to FHTC at Pump House No.I and II Zone II Rep. under Jashaikathi WS Scheme District of 24 Pgs. N. | Assistant Engineer | Junior Engineer | ORD/001214/2023-2024 | 4870/EMD | 14/08/2023 | 13/09/2023 | M/S S.R. ENTERPRISE | 26.07 | 6.08 | 23.33 | 47
3 | NORTH 24 PARAGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JASHAIKATI ZONE-II to accommodate FHTC under Jal Swapna Mission under Baduria Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11708 | Augmentation | Hiring of one (1) no. Diesel / Petrol operated AC motor cab / maxi cab (Car No. - WB25F - 6815) with engine capacity less than or equal to 2000 C.C. with driver for official use of the Chief Engineer (Head Quarters), Office, PHE Dte. with all costs towards the owner except fuel cost i.e. Diesel / Petrol, Mobil oil w.e.f. 01.07.2024 to 31.12.2024. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000033/2024-2025 | 1047/F/B.Ar.D | 27/06/2024 | 28/12/2024 | TOJO ENTERPRISE | 0.96 | 0.8 | 83.56 | 0
4 | NORTH 24 PARAGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JASHAIKATI ZONE-II to accommodate FHTC under Jal Swapna Mission under Baduria Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11708 | Augmentation | Construction of 3.6 mtr. x 3.0 mtr. size new Pump House ( Pump House-III ) with sanitary arrangement, construction of boundary wall and Allied Works for Jasaikathi ( Z-II ) W/S Scheme Under Baduria Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000071/2023-2024 | 1796/B.Ar.D. | 28/07/2023 | 26/09/2023 | AFRINA ENTERPRISE | 11.68 | 5.71 | 48.89 | 100
5 | NORTH 24 PARAGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JASHAIKATI ZONE-II to accommodate FHTC under Jal Swapna Mission under Baduria Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11708 | Augmentation | Preparation of Augmentation DPR for Jasaikathi (Zone-II) Water Supply Scheme under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000107/2022-2023 | 1835/B.Ar.D | 19/09/2022 | 09/10/2022 | RISHAN ENGINEERING CONSULTANCY | 0.98 | 0.97 | 98.58 | 1
6 | NORTH 24 PARAGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JASHAIKATI ZONE-II to accommodate FHTC under Jal Swapna Mission under Baduria Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11708 | Augmentation | Laying of distribution System Including specials all Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area for Augmentation of Ground Based Water Supply Scheme at Jasaikathi Zone -II at Baduria Block in North 24 Pgs District under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000113/2022-2023 | 1635/B.Ar.D. | 30/08/2022 | 28/11/2022 | CHANCHAL ENTERPRISE & CO. | 284.52 | 219.24 | 77.06 | 86
7 | NORTH 24 PARAGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JASHAIKATI ZONE-II to accommodate FHTC under Jal Swapna Mission under Baduria Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11708 | Augmentation | Sinking for 1 no 250 mm. x 150 mm. dia. 330 mtr deep Tubewell by D.R. Rig method near Pump House no.-2 with PVC pipe & strainer having 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long filter at Jasaikathi (Z-II) w/s scheme of Baduria block under Barasat Arsenic Division, P.H.E. Dte. (Sl No. 3) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000133/2022-2023 | 2057/B.Ar.D. | 19/10/2022 | 03/12/2022 | M/S RAJPATH CONSTRUCTION | 15.35 | 12.2 | 79.45 | 1
8 | NORTH 24 PARAGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JASHAIKATI ZONE-II to accommodate FHTC under Jal Swapna Mission under Baduria Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11708 | Augmentation | Repair and Renovation works of Existing R.C.C. Elevated Reservoir of Capacity 550 Cu.m. at Jasaikathi (Z-II) W/S Scheme of Baduria Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000188/2022-2023 | 238/B.Ar.D. | 02/02/2023 | 03/04/2023 | M/S DATTA ENTERPRISE | 13.66 | 13.47 | 98.65 | 1
9 | NORTH 24 PARAGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JASHAIKATI ZONE-II to accommodate FHTC under Jal Swapna Mission under Baduria Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11708 | Augmentation | Laying of DI pipe and Repairing, Rennovation and protection of boundary wall, Fencing work etc and other allied works at Head work site of Jasaikathi-(Z-II) W/S Scheme under Baduria Block under Barasat Arsenic Division PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000232/2023-2024 | 393/B.Ar.D | 21/02/2024 | 06/04/2024 | MAHALAXMI CONSTRUCTION | 14.79 | 3.51 | 23.71 | 100
10 | NORTH 24 PARAGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JASHAIKATI ZONE-II to accommodate FHTC under Jal Swapna Mission under Baduria Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11708 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000004/2022-2023 | 2106/B.Ar.D. | 02/11/2022 |  | Resource Division | 9.61 | 0 | 0 | 0
11 | NORTH 24 PARAGANAS |  | Barasat Arsenic Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JASHAIKATI ZONE-II to accommodate FHTC under Jal Swapna Mission under Baduria Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. | SM/11708 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000020/2022-2023 | 2293/B.Ar. | 02/12/2022 |  | Resource Division | 10.97 | 0 | 0 | 0
Total | [13 empty] | 392.45 | 261.98 | 66.75