## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARAGANAS | Barasat - II | Central Drilling | TEGHARIA Piped Water Supply Scheme | SM/16457 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 17/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2 | NORTH 24 PARAGANAS | Barasat - II | Barasat Arsenic Division | TEGHARIA Piped Water Supply Scheme | SM/16457 | New | Survey, Design Drawing & DPR Preparation for TEGHARIA Water Supply Scheme (NEW PWSS) in BARASAT-II BLOCK under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000005/2023-2024 | 982/B.Ar.D. | 20/04/2023 | 20/05/2023 | TIYAS CONSULTANCY AND INFRASTRUCTURE PRIVATE LIMITED | 6.01 | 6.01 | 100 | 100
3 | NORTH 24 PARAGANAS | Barasat - II | Barasat Arsenic Division | TEGHARIA Piped Water Supply Scheme | SM/16457 | New | Laying of Distribution System including specials all complete and Providing Functional House Hold Tap Connection (FHTC) from distribution system within command area & construction of 2 nos. pump house & Construction of 300 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir including soil test as per Departmental design, drawing and specification including bored pile & pile cap at TEGHARIA water supply scheme, Barasat-II block under Barasat Arsenic Division, P.H.E. Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000092/2023-2024 | 1883/B.Ar.D. | 04/08/2023 | 29/07/2024 | R. K. MANDAL & CO. | 343.74 | 0 | 0 | 0
4 | NORTH 24 PARAGANAS | Barasat - II | Barasat Arsenic Division | TEGHARIA Piped Water Supply Scheme | SM/16457 | New | Material Requisition To Resource Division |  |  | RTOR000005/2023-2024 | 74/B.Ar.D | 11/01/2024 |  | Resource Division | 8.9 | 0 | 0 | 0
Total | [13 empty] | 21698.41 | 6.01 | 0.03