## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Procurement of Chemicals, Glassware for routine testing chemical requirement for OMAS Testing, maintenance contract of computer and others .........and collection of special drive samples for 1 Yr. | SM/06617 | Support-WQMSP | Procurement of CRMs for NABL Recognized 3 Sub District Water Testing Laboratories in Hooghly District under Hooghly Division, P.H.E. Dte. | Assistant Engineer(HQ) |  | ORD/000057/2023-2024 | 137/HQ/HUG | 18/04/2023 | 25/04/2023 | A.R. CONSTRUCTION | 0.9 | 0 | 0 | 100
2 | HOOGHLY |  | Hooghly Division | Procurement of Chemicals, Glassware for routine testing chemical requirement for OMAS Testing, maintenance contract of computer and others .........and collection of special drive samples for 1 Yr. | SM/06617 | Support-WQMSP | Procurement of CRMs for NABL Recognized 3 Sub District Water Testing Laboratories in Hooghly District under Hooghly Division, P.H.E. Dte. | Assistant Engineer(HQ) |  | ORD/000058/2023-2024 | 138/HQ/HUG | 18/04/2023 | 25/04/2023 | A.R. CONSTRUCTION | 0.9 | 0 | 0 | 100
3 | HOOGHLY |  | Hooghly Division | Procurement of Chemicals, Glassware for routine testing chemical requirement for OMAS Testing, maintenance contract of computer and others .........and collection of special drive samples for 1 Yr. | SM/06617 | Support-WQMSP | Procurement of CRMs for NABL Recognized 3 Sub District Water Testing Laboratories in Hooghly District under Hooghly Division, P.H.E. Dte. | Assistant Engineer(HQ) |  | ORD/000060/2023-2024 | 148/HQ/HUG | 18/04/2023 | 25/04/2023 | LAB SOLUTION | 0.83 | 0 | 0 | 100
4 | HOOGHLY |  | Hooghly Division | Procurement of Chemicals, Glassware for routine testing chemical requirement for OMAS Testing, maintenance contract of computer and others .........and collection of special drive samples for 1 Yr. | SM/06617 | Support-WQMSP | Procurement of CRMs for NABL Recognized 3 Sub District Water Testing Laboratories in Hooghly District under Hooghly Division, P.H.E. Dte. | Assistant Engineer(HQ) |  | ORD/000061/2023-2024 | 149/HQ/HUG | 18/04/2023 | 25/04/2023 | A.R. CONSTRUCTION | 0.88 | 0 | 0 | 100
5 | HOOGHLY |  | Hooghly Division | Procurement of Chemicals, Glassware for routine testing chemical requirement for OMAS Testing, maintenance contract of computer and others .........and collection of special drive samples for 1 Yr. | SM/06617 | Support-WQMSP | Testing total arsenic for status review of habitations that remained quality affected by Arsenic at Hooghly District under Executive Engineer Hooghly Division, Public Health Engineering Directorate, Government of West Bengal. | Assistant Engineer(HQ) |  | ORD/000188/2023-2024 | 200/HQ/HUG | 22/05/2023 | 01/06/2023 | ARUN SEAL AND CO. | 0.82 | 0 | 0 | 0
6 | HOOGHLY |  | Hooghly Division | Procurement of Chemicals, Glassware for routine testing chemical requirement for OMAS Testing, maintenance contract of computer and others .........and collection of special drive samples for 1 Yr. | SM/06617 | Support-WQMSP | Testing total arsenic for status review of habitations that remained quality affected by Arsenic at Hooghly District under Executive Engineer Hooghly Division, Public Health Engineering Directorate, Government of West Bengal. | Assistant Engineer(HQ) |  | ORD/000189/2023-2024 | 201/HQ/HUG | 22/05/2023 | 01/06/2023 | SOUMYADIP DE | 0.77 | 0 | 0 | 0
7 | HOOGHLY |  | Hooghly Division | Procurement of Chemicals, Glassware for routine testing chemical requirement for OMAS Testing, maintenance contract of computer and others .........and collection of special drive samples for 1 Yr. | SM/06617 | Support-WQMSP | Testing total arsenic for status review of habitations that remained quality affected by Arsenic at Hooghly District under Executive Engineer Hooghly Division, Public Health Engineering Directorate, Government of West Bengal. | Assistant Engineer(HQ) |  | ORD/000190/2023-2024 | 202/HQ/HUG | 22/05/2023 | 01/06/2023 | SOUMYADIP DE | 0.77 | 0 | 0 | 0
8 | HOOGHLY |  | Hooghly Division | Procurement of Chemicals, Glassware for routine testing chemical requirement for OMAS Testing, maintenance contract of computer and others .........and collection of special drive samples for 1 Yr. | SM/06617 | Support-WQMSP | Testing total arsenic for status review of habitations that remained quality affected by Arsenic at Hooghly District under Executive Engineer Hooghly Division, Public Health Engineering Directorate, Government of West Bengal | Assistant Engineer(HQ) |  | ORD/000191/2023-2024 | 203/HQ/HUG | 22/05/2023 | 01/06/2023 | SOUMYADIP DE | 0.5 | 0 | 0 | 0
9 | HOOGHLY |  | Hooghly Division | Procurement of Chemicals, Glassware for routine testing chemical requirement for OMAS Testing, maintenance contract of computer and others .........and collection of special drive samples for 1 Yr. | SM/06617 | Support-WQMSP | Supply & Delivery of Water Testing Chemicals, Media, Reagent, etc. for (9) Nine Water Testing Laboratories in Hooghly District under Hooghly Division, P.H.E. Dte. | Assistant Engineer(HQ) |  | ORD/000213/2021-2022 | 1693/Hug | 15/09/2021 | 05/10/2021 | M/S LAXMI ENTERPRISE | 20.34 | 0 | 0 | 0
10 | HOOGHLY |  | Hooghly Division | Procurement of Chemicals, Glassware for routine testing chemical requirement for OMAS Testing, maintenance contract of computer and others .........and collection of special drive samples for 1 Yr. | SM/06617 | Support-WQMSP | Supply and Delivery of Consumables for On-site Mobile Analysis System, including cost of facilitating and coordinating for onsite testing of drinking water sources through OMAS App ensuring 50 tests per month by data updation on State Water Quality Dashboard on a monthly basis. | Assistant Engineer(HQ) |  | ORD/000372/2021-2022 | 282/Hug | 17/02/2022 | 18/02/2022 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 3.86 | 0 | 0 | 0
11 | HOOGHLY |  | Hooghly Division | Procurement of Chemicals, Glassware for routine testing chemical requirement for OMAS Testing, maintenance contract of computer and others .........and collection of special drive samples for 1 Yr. | SM/06617 | Support-WQMSP | SUPPLY AND DELIVERY OF CONSUMABLE BY OMAS APP |  |  | VCH/000477/2022-2023 |  | 24/06/2022 | 24/06/2022 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 3.86 | 0 | 0 | 0
12 | HOOGHLY |  | Hooghly Division | Procurement of Chemicals, Glassware for routine testing chemical requirement for OMAS Testing, maintenance contract of computer and others .........and collection of special drive samples for 1 Yr. | SM/06617 | Support-WQMSP | LAB |  |  | VCH/000521/2022-2023 |  | 07/07/2022 | 07/07/2022 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 1 | 0 | 0 | 0
Total | [13 empty] | 35.46 | 0 | 0