## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Retrofitting Works for providing 1089 nos Functional Household Tap Connection(FHTC) within the Dakshinkul, Baganbati & Gazipur Mouza of Malia Water Supply Schem | SM/06765 | Retrofitting | Laying pipe line For damaged portion of MALIA Water Supply Scheme under Chandannagar Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000389/2022-2023 | 2142/HUG | 26/09/2022 | 16/10/2022 | WELFARE ENGINEER'S CO - OPERATIVE SOCIETY LTD | 4.95 | 4.95 | 99.98 | 100
2 | HOOGHLY |  | Hooghly Division | Retrofitting Works for providing 1089 nos Functional Household Tap Connection(FHTC) within the Dakshinkul, Baganbati & Gazipur Mouza of Malia Water Supply Schem | SM/06765 | Retrofitting | Construction of 3.6 X 3.0 m Swicth Room with Additional Plinth Height along with laying DI rising main at 3rd boosting tubewell site for Malia Water Supply Scheme under Chandannagar Sub - Division, PHE DTE. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000888/2020-2021 | 121/Chan | 24/02/2021 | 10/04/2021 | M/S S.G. CONSTRUCTION | 4.97 | 4.9 | 98.64 | 100
3 | HOOGHLY |  | Hooghly Division | Retrofitting Works for providing 1089 nos Functional Household Tap Connection(FHTC) within the Dakshinkul, Baganbati & Gazipur Mouza of Malia Water Supply Schem | SM/06765 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000033/2022-2023 | 1125/6/HUG | 06/06/2022 |  | Resource Division | 12.32 | 0 | 0 | 0
4 | HOOGHLY |  | Hooghly Division | Retrofitting Works for providing 1089 nos Functional Household Tap Connection(FHTC) within the Dakshinkul, Baganbati & Gazipur Mouza of Malia Water Supply Schem | SM/06765 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000125/2021-2022 | 2197/HUG | 14/12/2021 |  | Resource Division | 1.59 | 0 | 0 | 0
5 | HOOGHLY |  | Hooghly Division | Retrofitting Works for providing 1089 nos Functional Household Tap Connection(FHTC) within the Dakshinkul, Baganbati & Gazipur Mouza of Malia Water Supply Schem | SM/06765 | Retrofitting | FHTC |  |  | VCH/001919/2020-2021 | null | 15/02/2021 |  | PAUL CONSTRUCTION (RANJIT KUMAR PAUL) | 36 | 0 | 0 | 0
6 | HOOGHLY |  | Hooghly Division | Retrofitting Works for providing 1089 nos Functional Household Tap Connection(FHTC) within the Dakshinkul, Baganbati & Gazipur Mouza of Malia Water Supply Schem | SM/06765 | Retrofitting | SURVEY |  |  | VCH/002112/2021-2022 | null | 28/01/2022 |  | SIKHA ENTERPRISE | 5.1 | 0 | 0 | 0
7 | HOOGHLY |  | Hooghly Division | Retrofitting Works for providing 1089 nos Functional Household Tap Connection(FHTC) within the Dakshinkul, Baganbati & Gazipur Mouza of Malia Water Supply Schem | SM/06765 | Retrofitting | Direct purchase of land for Lakshmipur PWSS |  |  | VCH/002242/2021-2022 | 844321 | 09/11/2021 |  | HOOGHLY ZILLA PARISHAD | 11.85 | 0 | 0 | 0
Total | [13 empty] | 76.78 | 9.85 | 12.83