## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Retrofitting Works for providing Functional Household Tap Connection(FHTC) within the Hamirgachhi, Malia & Krishnabati Mouza of Malia Water Supply Scheme | SM/06767 | Retrofitting | Providing 512 nos F.H.T.C. in Krishnabati & Gazipur village of Malia and its Adjoining Mouzas Water Supply Scheme Under Chandannagar Sub-Division of Hooghly Division P.H.E Dte. [Block-Haripal] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000083/2020-2021 | 1549/Hug | 24/11/2020 | 24/11/2021 | PAUL CONSTRUCTION (RANJIT KUMAR PAUL) | 18.11 | 3 | 16.56 | 100
2 | HOOGHLY |  | Hooghly Division | Retrofitting Works for providing Functional Household Tap Connection(FHTC) within the Hamirgachhi, Malia & Krishnabati Mouza of Malia Water Supply Scheme | SM/06767 | Retrofitting | Providing 62 nos FHTC in Krishnabati village at Nawapara Habitation of Malia and its Adj. Mouzas Water Supply Scheme under Chandannagar Sub Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000423/2020-2021 | 59/Chan | 02/02/2021 | 18/02/2021 | PAUL CONSTRUCTION (RANJIT KUMAR PAUL) | 2.17 | 0.31 | 14.15 | 100
3 | HOOGHLY |  | Hooghly Division | Retrofitting Works for providing Functional Household Tap Connection(FHTC) within the Hamirgachhi, Malia & Krishnabati Mouza of Malia Water Supply Scheme | SM/06767 | Retrofitting | PROVIDING 72 NOS FHTC FOR MALIA PWSS | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000457/2020-2021 | 88/CHAN | 15/02/2021 | 17/03/2021 | PAUL CONSTRUCTION (RANJIT KUMAR PAUL) | 3.16 | 0.41 | 12.89 | 100
4 | HOOGHLY |  | Hooghly Division | Retrofitting Works for providing Functional Household Tap Connection(FHTC) within the Hamirgachhi, Malia & Krishnabati Mouza of Malia Water Supply Scheme | SM/06767 | Retrofitting | Providing 112 nos F.H.T.C. & extension of pipe line in left out portion of Dakshinkul, Baganbati& Hamir gachhi village of Malia and its Adjoining Mouzas Water Supply Scheme Under Chandannagar Sub-Division of Hooghly Division P.H.E Dte. [Block-Haripal] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000880/2020-2021 | 327/HUG | 11/02/2021 | 13/03/2021 | M/S S.G. CONSTRUCTION | 10.08 | 10.08 | 100 | 100
5 | HOOGHLY |  | Hooghly Division | Retrofitting Works for providing Functional Household Tap Connection(FHTC) within the Hamirgachhi, Malia & Krishnabati Mouza of Malia Water Supply Scheme | SM/06767 | Retrofitting | FHTC |  |  | VCH/001038/2021-2022 | null | 30/09/2021 |  | M/S S.G. CONSTRUCTION | 13.22 | 0 | 0 | 0
6 | HOOGHLY |  | Hooghly Division | Retrofitting Works for providing Functional Household Tap Connection(FHTC) within the Hamirgachhi, Malia & Krishnabati Mouza of Malia Water Supply Scheme | SM/06767 | Retrofitting | Placement of Fund |  |  | VCH/002590/2021-2022 | 844368 | 19/01/2022 |  | JAL JEEVAN MISSION WEST BENGAL ESCROW AC | 11.53 | 0 | 0 | 0
Total | [13 empty] | 58.27 | 13.79 | 23.67