## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KISHORPUR WATER SUPPLY SCHEME. | SM/07439 | Retrofitting | Providing 500 nos Functional Household Tap Connection (FHTC) within the command area of KISHORPUR Water Supply Scheme Under Arambag Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer | Junior Engineer (Civill) | ORD/000443/2021-2022 | 461/Hug | 10/03/2022 | 09/04/2022 | MS CHANDIMATA CONSTRUCTION | 26.43 | 25.98 | 98.3 | 0
2 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KISHORPUR WATER SUPPLY SCHEME. | SM/07439 | Retrofitting | FHTC |  |  | VCH/000011/2021-2022 | null | 12/04/2021 |  | DULAL CHANDRA ROY | 2.67 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KISHORPUR WATER SUPPLY SCHEME. | SM/07439 | Retrofitting | FHTC |  |  | VCH/000515/2021-2022 | null | 23/07/2021 |  | DULAL CHANDRA ROY | 21.01 | 0 | 0 | 0
4 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KISHORPUR WATER SUPPLY SCHEME. | SM/07439 | Retrofitting | FHTC |  |  | VCH/000838/2021-2022 | null | 21/09/2021 |  | NIRMAN ENGINEERS CO - OPERATIVE SOCIETY LTD. | 59.08 | 0 | 0 | 0
5 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KISHORPUR WATER SUPPLY SCHEME. | SM/07439 | Retrofitting | FHTC |  |  | VCH/001100/2021-2022 | null | 08/11/2021 |  | SAMRAT REALPROJECTS PRIVATE LIMITED, | 37.7 | 0 | 0 | 0
6 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KISHORPUR WATER SUPPLY SCHEME. | SM/07439 | Retrofitting | FHTC |  |  | VCH/001104/2021-2022 | null | 08/11/2021 |  | SAMRAT REALPROJECTS PRIVATE LIMITED, | 37.7 | 0 | 0 | 0
Total | [13 empty] | 184.59 | 25.98 | 14.07