## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MANDARA WATER SUPPLY SCHEME. | SM/07441 | Retrofitting | Providing 1693nos F.H.T.C. in Mandara Village of Mandara and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Dhaniakhali] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000321/2020-2021 | 393/Hug | 15/02/2021 | 06/04/2021 | PAUL CONSTRUCTION (RANJIT KUMAR PAUL) | 88.47 | 60.72 | 68.64 | 0
2 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MANDARA WATER SUPPLY SCHEME. | SM/07441 | Retrofitting | Providing 253 nos F.H.T.C. in Gangarampur Village of Mandara and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Dhaniakhali] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000322/2020-2021 | 394/Hug | 15/02/2021 | 07/03/2021 | K. JAGADHATRY & CO. | 13.2 | 7.39 | 55.98 | 0
3 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MANDARA WATER SUPPLY SCHEME. | SM/07441 | Retrofitting | Providing 1693nos F.H.T.C. in Mandara Village of Mandara and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Dhaniakhali] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000910/2020-2021 | 393/HUG | 15/02/2021 | 06/04/2021 | PAUL CONSTRUCTION (RANJIT KUMAR PAUL) | 88.47 | 21.9 | 24.75 | 100
4 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MANDARA WATER SUPPLY SCHEME. | SM/07441 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000169/2021-2022 | 428/3-5/Hug | 07/03/2022 |  | Resource Division | 10.98 | 0 | 0 | 0
5 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MANDARA WATER SUPPLY SCHEME. | SM/07441 | Retrofitting | FHTC |  |  | VCH/000931/2021-2022 | null | 24/09/2021 |  | PAUL CONSTRUCTION (RANJIT KUMAR PAUL) | 41.41 | 0 | 0 | 0
6 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MANDARA WATER SUPPLY SCHEME. | SM/07441 | Retrofitting | FHTC |  |  | VCH/000944/2021-2022 | null | 24/09/2021 |  | K. JAGADHATRY & CO. | 7.39 | 0 | 0 | 0
Total | [13 empty] | 249.92 | 90.01 | 36.02