## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of PRATAPNAGAR Water Supply Scheme | SM/07461 | Retrofitting | Providing 304 nos Functional Household Tap Connection (FHTC) within the command area of Pratapnagar Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. Work Allotted : 152 Nos FHTC out of 304 Nos FHTC within the command area of Pratapnagar Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. Estimate Value : Rs. 707651.50(50% of Rs. 1415303.00) | Assistant Engineer | Junior Engineer (Civill) | ORD/000243/2021-2022 | 1965/Hug | 02/11/2021 | 02/12/2021 | GHOSH ENTERPRISE | 11.32 | 5.43 | 47.92 | 0
2 | HOOGHLY |  | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of PRATAPNAGAR Water Supply Scheme | SM/07461 | Retrofitting | Providing 304 nos Functional Household Tap Connection (FHTC) within the command area of PROTAPNAGAR Water Supply Scheme Under ARAMBAG Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000341/2021-2022 | 18/Hug | 04/01/2022 | 03/02/2022 | SURAJIT SINGHA RAY | 12.56 | 3.06 | 24.36 | 0
3 | HOOGHLY |  | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of PRATAPNAGAR Water Supply Scheme | SM/07461 | Retrofitting | Providing FHTC for Pratapnagar PWSS | Assistant Engineer | Junior Engineer (Civill) | ORD/000503/2021-2022 | 525/Arg. | 30/11/2021 | 14/01/2022 | BENGAL TRADERS | 4.84 | 4.84 | 100 | 0
4 | HOOGHLY |  | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of PRATAPNAGAR Water Supply Scheme | SM/07461 | Retrofitting | Providing 304 nos FHTC for Pratapnagar PWSS | Assistant Engineer | Junior Engineer (Civill) | ORD/000509/2021-2022 | 1998/Hug. | 12/11/2021 | 17/12/2021 | MESSRS FREEDOM CONSTRUCTION | 5.58 | 5.58 | 100 | 0
5 | HOOGHLY |  | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of PRATAPNAGAR Water Supply Scheme | SM/07461 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000123/2021-2022 | 2196/1/HUG | 14/12/2021 |  | Resource Division | 1.59 | 0 | 0 | 0
6 | HOOGHLY |  | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of PRATAPNAGAR Water Supply Scheme | SM/07461 | Retrofitting | FHTC |  |  | VCH/000006/2021-2022 | null | 12/04/2021 |  | MONDAL PRECESSION PVT LTD. | 22.48 | 0 | 0 | 0
7 | HOOGHLY |  | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of PRATAPNAGAR Water Supply Scheme | SM/07461 | Retrofitting | FHTC |  |  | VCH/001091/2021-2022 | null | 05/10/2021 |  | MONDAL PRECESSION PVT LTD. | 40.25 | 0 | 0 | 0
8 | HOOGHLY |  | Hooghly Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) within the command area of PRATAPNAGAR Water Supply Scheme | SM/07461 | Retrofitting | FHTC |  |  | VCH/002100/2021-2022 | null | 28/01/2022 |  | MESSRS. FREEDOM CONSTRUCTION | 5.58 | 0 | 0 | 0
Total | [13 empty] | 104.21 | 18.91 | 18.14