## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF ANANDAPUR WATER SUPPLY SCHEME. | SM/07534 | Retrofitting | Providing 304 nos Functional Household Tap Connection (FHTC) within the command area of Anandapur Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer | Junior Engineer (Civill) | ORD/000270/2021-2022 | 2124/Hug | 01/12/2021 | 31/12/2021 | GHOSH CONSTRUCTION | 12.06 | 10.04 | 83.24 | 0
2 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF ANANDAPUR WATER SUPPLY SCHEME. | SM/07534 | Retrofitting | Providing 285 nos Functional Household Tap Connection (FHTC) within the command area of ANANDAPUR Water Supply Scheme Under ARAMBAG Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000344/2021-2022 | 21/Hug | 04/01/2022 | 03/02/2022 | ARATI ENGINEERING | 11.81 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF ANANDAPUR WATER SUPPLY SCHEME. | SM/07534 | Retrofitting | Providing 114 nos. Functional Household Tap Connection (F.H.T.C) within Command area of Mohanpur Village under Anandapur Water Supply Scheme under Arambagh Sub-Division, P.H.E. Dte. [Block-Goghat-I]. | Assistant Engineer | Junior Engineer (Civill) | ORD/000349/2021-2022 | 526/Arg | 30/11/2021 | 30/12/2021 | M/S TANISHA ENTERPRISE | 4.7 | 4.81 | 102.38 | 0
4 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF ANANDAPUR WATER SUPPLY SCHEME. | SM/07534 | Retrofitting | Providing 50 nos Functional Household Tap Connection (FHTC) within the command area of ANANDAPUR Water Supply Scheme Under Arambag Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer | Junior Engineer (Civill) | ORD/000362/2021-2022 | 123/Hug | 19/01/2022 | 13/02/2022 | M/S ROY CONSTRUCTION AND CO. | 14.88 | 0 | 0 | 100
5 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF ANANDAPUR WATER SUPPLY SCHEME. | SM/07534 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000014/2021-2022 | 2096/11/Hug | 26/11/2021 |  | Resource Division | 0.82 | 0 | 0 | 0
6 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF ANANDAPUR WATER SUPPLY SCHEME. | SM/07534 | Retrofitting | FHTC |  |  | VCH/000024/2021-2022 | null | 12/04/2021 |  | R AND D TRADERS | 1.5 | 0 | 0 | 0
7 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF ANANDAPUR WATER SUPPLY SCHEME. | SM/07534 | Retrofitting | FHTC |  |  | VCH/000025/2021-2022 | null | 12/04/2021 |  | M/S R.M. CONSTRUCTION | 2.96 | 0 | 0 | 0
8 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF ANANDAPUR WATER SUPPLY SCHEME. | SM/07534 | Retrofitting | FHTC |  |  | VCH/000589/2021-2022 | null | 17/08/2021 |  | M/S R.M. CONSTRUCTION | 14.97 | 0 | 0 | 0
9 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF ANANDAPUR WATER SUPPLY SCHEME. | SM/07534 | Retrofitting | FHTC |  |  | VCH/000590/2021-2022 | null | 17/08/2021 |  | ARATI ENGINEERING | 10.31 | 0 | 0 | 0
10 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF ANANDAPUR WATER SUPPLY SCHEME. | SM/07534 | Retrofitting | FHTC |  |  | VCH/002258/2020-2021 | null | 15/03/2021 |  | R AND D TRADERS | 5 | 0 | 0 | 0
11 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF ANANDAPUR WATER SUPPLY SCHEME. | SM/07534 | Retrofitting | FHTC |  |  | VCH/002621/2020-2021 | null | 19/03/2021 |  | M/S R.M. CONSTRUCTION | 18 | 0 | 0 | 0
Total | [13 empty] | 97.02 | 14.85 | 15.31