## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF NATAGARI WATER SUPPLY SCHEME. | SM/07538 | Retrofitting | Providing 477 nos F.H.T.C. in Natagari and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Balagarh] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000330/2020-2021 | 402/Hug | 15/02/2021 | 17/03/2021 | ARUN SEAL AND CO. | 24.94 | 15.13 | 60.69 | 100
2 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF NATAGARI WATER SUPPLY SCHEME. | SM/07538 | Retrofitting | Providing 477 nos F.H.T.C. in Natagari and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Balagarh] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000876/2020-2021 | 402/HUG | 15/02/2021 | 17/03/2021 | ARUN SEAL AND CO. | 6.69 | 6.69 | 100 | 100
3 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF NATAGARI WATER SUPPLY SCHEME. | SM/07538 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000064/2021-2022 | 2097/4/Hug | 26/11/2021 |  | Resource Division | 0.83 | 0 | 0 | 0
4 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF NATAGARI WATER SUPPLY SCHEME. | SM/07538 | Retrofitting | FHTC |  |  | VCH/000858/2021-2022 | null | 21/09/2021 |  | ARUN SEAL AND CO. | 15.14 | 0 | 0 | 0
Total | [13 empty] | 47.59 | 21.83 | 45.86