## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULTEGHARI WATER SUPPLY SCHEME. | SM/07956 | Retrofitting | Providing Functional Household Tap Connection (FHTC) under JJM within left out portion of Tullyan, Keshabchak, Kulteghari, Mohanbati Mouza in KULTEGHORI PWSS, Block Tarakeswar under Chandannagar Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000593/2022-2023 | 2852/HUG | 16/12/2022 | 15/01/2023 | S K ENTERPRISE | 14.97 | 14.45 | 96.52 | 100
2 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULTEGHARI WATER SUPPLY SCHEME. | SM/07956 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000037/2021-2022 | 2098/1/Hug | 26/11/2021 |  | Resource Division | 0.83 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULTEGHARI WATER SUPPLY SCHEME. | SM/07956 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000134/2022-2023 | 2686/1/Hug | 01/12/2022 |  | Resource Division | 0.34 | 0 | 0 | 0
4 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULTEGHARI WATER SUPPLY SCHEME. | SM/07956 | Retrofitting | FHTC |  |  | VCH/000519/2021-2022 | null | 23/07/2021 |  | M/S RAJKUMAR KHAN | 32.53 | 0 | 0 | 0
5 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULTEGHARI WATER SUPPLY SCHEME. | SM/07956 | Retrofitting | FHTC |  |  | VCH/000534/2021-2022 | null | 23/07/2021 |  | M/S RAJKUMAR KHAN | 32.53 | 0 | 0 | 0
6 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULTEGHARI WATER SUPPLY SCHEME. | SM/07956 | Retrofitting | FHTC |  |  | VCH/000593/2021-2022 | null | 17/08/2021 |  | M/S S.G. CONSTRUCTION | 34.67 | 0 | 0 | 0
7 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULTEGHARI WATER SUPPLY SCHEME. | SM/07956 | Retrofitting | FHTC |  |  | VCH/000848/2021-2022 | null | 21/09/2021 |  | M/S RAJKUMAR KHAN | 23.52 | 0 | 0 | 0
8 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULTEGHARI WATER SUPPLY SCHEME. | SM/07956 | Retrofitting | FHTC |  |  | VCH/001042/2021-2022 | null | 30/09/2021 |  | M/S S.G. CONSTRUCTION | 18.9 | 0 | 0 | 0
9 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULTEGHARI WATER SUPPLY SCHEME. | SM/07956 | Retrofitting | FHTC |  |  | VCH/002111/2021-2022 | null | 28/01/2022 |  | M/S S.G. CONSTRUCTION | 20 | 0 | 0 | 0
Total | [13 empty] | 178.29 | 14.45 | 8.1