## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GOSWAMI MALIPARA WATER SUPPLY SCHEME. | SM/08741 | Retrofitting | Providing 1350 nos F.H.T.C. in Talchinan- Sanihati, Popai & Dhanijpur Village of Goswami Malipara and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Polba-Dadpur] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000019/2021-2022 | 957/Hug | 10/05/2021 | 19/06/2021 | MINTU CHAKRABORTY | 61.16 | 52.83 | 86.38 | 100
2 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GOSWAMI MALIPARA WATER SUPPLY SCHEME. | SM/08741 | Retrofitting | Providing 12 Nos. House Connection Within Goswami Malipara & It¿s Adjoining mouzas W/S Scheme under Chinsurah Sub-Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000118/2022-2023 | 400/CH | 06/05/2022 | 21/05/2022 | MINTU CHAKRABORTY | 4.74 | 4.73 | 99.92 | 100
3 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GOSWAMI MALIPARA WATER SUPPLY SCHEME. | SM/08741 | Retrofitting | Construction of Boundary Wall, Pathway & Repairing of Switch room at Head Works site & 2nd T/W Site of PAUNAN W/S Scheme under Chinsurah Sub-Division under Hooghly Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000237/2021-2022 | 1922/Hug | 27/10/2021 | 06/12/2021 | M/S S.G. CONSTRUCTION | 26.25 | 12.44 | 47.37 | 100
4 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GOSWAMI MALIPARA WATER SUPPLY SCHEME. | SM/08741 | Retrofitting | Providing 1963 nos F.H.T.C. in Hadilpur, Bali Kukhari, Mirkhila, Chaupala & Goswami Malipara Village of Goswami Malipara and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Polba-Dadpur] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000289/2020-2021 | 364/Hug | 15/02/2021 | 17/03/2021 | MINTU CHAKRABORTY | 92.96 | 5.85 | 6.29 | 100
5 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GOSWAMI MALIPARA WATER SUPPLY SCHEME. | SM/08741 | Retrofitting | Providing 200 nos Functional Household Tap Connection (FHTC) within the command area of Goswami Malipara Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000297/2021-2022 | 2208/Hug | 14/12/2021 | 03/01/2022 | M/S KAMALA ENTERPRISE | 13.84 | 13.37 | 96.63 | 100
6 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GOSWAMI MALIPARA WATER SUPPLY SCHEME. | SM/08741 | Retrofitting | Repairing of concrete road due to laying of pipe line at Choska Para of Goswami Malipara PWSS under Chinsurah Sub Division of Hooghly Division, P.H.E.Dte. | Assistant Engineer (Civil) |  | ORD/000420/2023-2024 | 756/CH | 14/08/2023 | 29/08/2023 | M/S BIMAL DAS AND CO. | 0.91 | 0.91 | 99.9 | 97
7 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GOSWAMI MALIPARA WATER SUPPLY SCHEME. | SM/08741 | Retrofitting | Repairing of concrete road due to laying of pipe line at Dengor para of Goswami Malipara PWSS under Chinsurah Sub Division of Hooghly Division, P.H.E.Dte. | Assistant Engineer (Civil) |  | ORD/000422/2023-2024 | 757/CH | 14/08/2023 | 29/08/2023 | M/S BIMAL DAS AND CO. | 0.87 | 0.85 | 97.7 | 97
8 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GOSWAMI MALIPARA WATER SUPPLY SCHEME. | SM/08741 | Retrofitting | Repairing of concrete road due laying of pipe line at Gosai para of Goswami Malipara PWSS under Chinsurah Sub Division of Hooghly Division, P.H.E.Dte. | Assistant Engineer (Civil) |  | ORD/000423/2023-2024 | 759/CH | 14/08/2023 | 29/08/2023 | M/S BIMAL DAS AND CO. | 0.87 | 0.86 | 98.58 | 97
9 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GOSWAMI MALIPARA WATER SUPPLY SCHEME. | SM/08741 | Retrofitting | Repairing of concrete road due laying of pipe line at Doltala of Goswami Malipara PWSS under Chinsurah Sub Division of Hooghly Division, P.H.E.Dte. | Assistant Engineer (Civil) |  | ORD/000425/2023-2024 | 760/CH | 14/08/2023 | 29/08/2023 | M/S BIMAL DAS AND CO. | 0.9 | 0.9 | 99.11 | 97
10 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GOSWAMI MALIPARA WATER SUPPLY SCHEME. | SM/08741 | Retrofitting | Repairing of concrete road due laying of pipe line at Doltala of Goswami Malipara PWSS under Chinsurah Sub Division of Hooghly Division, P.H.E.Dte. | Assistant Engineer (Civil) |  | ORD/000427/2023-2024 | 762/CH | 16/08/2023 | 31/08/2023 | M/S BIMAL DAS AND CO. | 0.8 | 0.76 | 94.56 | 97
11 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GOSWAMI MALIPARA WATER SUPPLY SCHEME. | SM/08741 | Retrofitting | Repairing of concrete road due to laying of pipe line at Kallyandanga of Goswami Malipara PWSS under Chinsurah Sub Division of Hooghly Division, P.H.E.Dte. | Assistant Engineer (Civil) |  | ORD/000428/2023-2024 | 763/CH | 16/08/2023 | 31/08/2023 | M/S BIMAL DAS AND CO. | 0.91 | 0.9 | 99.5 | 97
12 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GOSWAMI MALIPARA WATER SUPPLY SCHEME. | SM/08741 | Retrofitting | Repairing of concrete road due laying of pipe line at Bhagarpar of Goswami Malipara PWSS under Chinsurah Sub Division of Hooghly Division, P.H.E.Dte. | Assistant Engineer (Civil) |  | ORD/000431/2023-2024 | 764/CH | 16/08/2023 | 31/08/2023 | M/S BIMAL DAS AND CO. | 0.89 | 0.89 | 99.59 | 97
13 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GOSWAMI MALIPARA WATER SUPPLY SCHEME. | SM/08741 | Retrofitting | Repairing of concrete road due laying of pipe line at Purba Para of Goswami Malipara PWSS under Chinsurah Sub Division of Hooghly Division, P.H.E.Dte. | Assistant Engineer (Civil) |  | ORD/000432/2023-2024 | 770/CH | 18/08/2023 | 02/09/2023 | M/S BIMAL DAS AND CO. | 0.89 | 0.85 | 95.9 | 97
14 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GOSWAMI MALIPARA WATER SUPPLY SCHEME. | SM/08741 | Retrofitting | Repairing of concrete road due to laying of pipe line at Kolor Par of Goswami Malipara PWSS under Chinsurah Sub Division of Hooghly Division, P.H.E.Dte. | Assistant Engineer (Civil) |  | ORD/000433/2023-2024 | 771/CH | 18/08/2023 | 02/09/2023 | M/S BIMAL DAS AND CO. | 0.91 | 0.81 | 89.76 | 97
15 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GOSWAMI MALIPARA WATER SUPPLY SCHEME. | SM/08741 | Retrofitting | Repairing of concrete road due laying of pipe line at Kalyan danga Goswami Malipara PWSS under Chinsurah Sub Division of Hooghly Division, P.H.E.Dte. | Assistant Engineer (Civil) |  | ORD/000434/2023-2024 | 772/CH | 18/08/2023 | 02/09/2023 | M/S BIMAL DAS AND CO. | 0.87 | 0.86 | 99.14 | 97
16 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GOSWAMI MALIPARA WATER SUPPLY SCHEME. | SM/08741 | Retrofitting | Repairing of concrete road due laying of pipe line at Doltala of Goswami Malipara PWSS under Chinsurah Sub Division of Hooghly Division, P.H.E.Dte. | Assistant Engineer (Civil) |  | ORD/000435/2023-2024 | 773/CH | 18/08/2023 | 02/09/2023 | M/S BIMAL DAS AND CO. | 0.84 | 0.83 | 99.64 | 97
17 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GOSWAMI MALIPARA WATER SUPPLY SCHEME. | SM/08741 | Retrofitting | Repairing of concrete road due laying of pipe line at Purba Para of Goswami Malipara PWSS under Chinsurah Sub Division of Hooghly Division, P.H.E.Dte. | Assistant Engineer (Civil) |  | ORD/000436/2023-2024 | 777/CH | 21/08/2023 | 05/09/2023 | M/S BIMAL DAS AND CO. | 0.52 | 0.49 | 93.81 | 97
18 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GOSWAMI MALIPARA WATER SUPPLY SCHEME. | SM/08741 | Retrofitting | Providing Functional Household Tap Connection (FHTC) under JJM within left out portion of Goswami Malipara PWSS, Block POLBA DADPUR under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000582/2022-2023 | 2841/HUG | 16/12/2022 | 15/01/2023 | BOSE ENTERPRISE (RATUL BOSE) | 29.55 | 29.52 | 99.9 | 40
19 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GOSWAMI MALIPARA WATER SUPPLY SCHEME. | SM/08741 | Retrofitting | FHTC |  |  | VCH/001127/2021-2022 | null | 16/11/2021 |  | MINTU CHAKRABORTY | 28.28 | 0 | 0 | 0
Total | [13 empty] | 266.95 | 128.66 | 48.2