## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Augmentation of RAJHAT ZONE 1 Piped Water Supply Scheme by installing ( 01 ) no. Tube well including Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. | SM/09516 | Augmentation | HIRE CHARGES BILL FOR THE ASSISTANT ENGINEER, RWS HOOGHLY SUB-DIVISION, PHE DTE. |  |  | BILL/00230/2022-2023 | BP-2022-23-566 | 02/03/2023 | 02/03/2023 | AATISH KUMAR SHAW | 0.77 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | Augmentation of RAJHAT ZONE 1 Piped Water Supply Scheme by installing ( 01 ) no. Tube well including Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. | SM/09516 | Augmentation | Laying of C.I/D.I pipes & specials for connection of T.W No. -III with distribution system & Protection work at 3rd TW Site of Rajhat (Z-I) W/S Scheme under Chinsurah Sub - Division P.H.E. Dte. | Assistant Engineer (Civil) |  | ORD/000465/2021-2022 | 619/CH | 20/12/2021 | 14/01/2022 | BOSE ENTERPRISE (RATUL BOSE) | 4.16 | 0.86 | 20.7 | 100
3 | HOOGHLY |  | Hooghly Division | Augmentation of RAJHAT ZONE 1 Piped Water Supply Scheme by installing ( 01 ) no. Tube well including Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. | SM/09516 | Augmentation | Construction of 3.6 m X 3.00 m Switch Room without Sanitary and Water Supply arrangement at 3rd T/W Site for Rajhat (Z-I) W/S Scheme under Chinsurah Sub-Division P.H.E. Dte. | Assistant Engineer (Civil) |  | ORD/000466/2021-2022 | 620/CH | 20/12/2021 | 29/01/2022 | BOSE ENTERPRISE (RATUL BOSE) | 2.44 | 2.4 | 98.58 | 100
4 | HOOGHLY |  | Hooghly Division | Augmentation of RAJHAT ZONE 1 Piped Water Supply Scheme by installing ( 01 ) no. Tube well including Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. | SM/09516 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000352/2023-2024 | 3004/9/Hug | 05/10/2023 | 05/10/2023 | Resource Division | 2.86 | 0 | 0 | 0
5 | HOOGHLY |  | Electrical | Augmentation of RAJHAT ZONE 1 Piped Water Supply Scheme by installing ( 01 ) no. Tube well including Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. | SM/09516 | Augmentation | Fuel Charges Bil |  |  | BILL/00736/2022-2023 | 147 | 31/01/2023 | 31/01/2023 | JAMECO AGENCIES PRIVATE LIMITED. | 0.14 | 0 | 0 | 0
6 | HOOGHLY |  | Electrical | Augmentation of RAJHAT ZONE 1 Piped Water Supply Scheme by installing ( 01 ) no. Tube well including Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. | SM/09516 | Augmentation | Hiring Charges Bill |  |  | BILL/00737/2022-2023 | 146 | 31/01/2023 | 31/01/2023 | SUNIL RAJAK | 0.26 | 0 | 0 | 0
7 | HOOGHLY |  | Electrical | Augmentation of RAJHAT ZONE 1 Piped Water Supply Scheme by installing ( 01 ) no. Tube well including Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. | SM/09516 | Augmentation | Hire Charges Bill |  |  | BILL/00738/2022-2023 | 138 | 20/01/2023 | 20/01/2023 | DILIP KUMAR GHOSH | 0.15 | 0 | 0 | 0
8 | HOOGHLY |  | Electrical | Augmentation of RAJHAT ZONE 1 Piped Water Supply Scheme by installing ( 01 ) no. Tube well including Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. | SM/09516 | Augmentation | Fuel Charges Bill |  |  | BILL/00739/2022-2023 | 137 | 20/01/2023 | 20/01/2023 | JAMECO AGENCIES PRIVATE LIMITED. | 0.25 | 0 | 0 | 0
9 | HOOGHLY |  | Electrical | Augmentation of RAJHAT ZONE 1 Piped Water Supply Scheme by installing ( 01 ) no. Tube well including Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. | SM/09516 | Augmentation | Supply, Delivery & Installation of S/P/M & other allied works for Rajhat W/S. Sch. Z-I, TW-III Dist-Hooghly |  |  | ORD/000063/2022-2023 | 1035/ED | 28/06/2022 | 26/09/2022 | C.M. ENTERPRISE | 9.45 | 9.4 | 99.51 | 100
10 | HOOGHLY |  | Electrical | Augmentation of RAJHAT ZONE 1 Piped Water Supply Scheme by installing ( 01 ) no. Tube well including Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. | SM/09516 | Augmentation | Supply & installation of Automatic Chlorinator at Rajhat water supply scheme, Zone-I, P.H. No.- II, District - Hooghly under Electrical Division, PHE Dte. |  |  | ORD/000597/2022-2023 | 1770/HMSD | 28/09/2022 | 05/10/2022 | GANGULY ENGINEERING CO. | 0.8 | 0.8 | 100 | 100
11 | HOOGHLY |  | Electrical | Augmentation of RAJHAT ZONE 1 Piped Water Supply Scheme by installing ( 01 ) no. Tube well including Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. | SM/09516 | Augmentation | Supply & installation of LED board and outside display board for depicting details of Pump/Valve operators at Zone-I & II, P.H. No.-III of Rajhat w/s scheme, Dist.- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/000598/2022-2023 | 2349/HMSD | 20/12/2022 | 30/12/2022 | INDTECH ASSOCIATES. | 0.84 | 0.84 | 100 | 0
12 | HOOGHLY |  | Electrical | Augmentation of RAJHAT ZONE 1 Piped Water Supply Scheme by installing ( 01 ) no. Tube well including Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. | SM/09516 | Augmentation | Supply & installation of LED board at Zone-I, P.H. No.-I & II of Rajhat water supply scheme, Dist.- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/000599/2022-2023 | 2347/HMSD | 20/12/2022 | 30/12/2022 | DAS ENTERPRISE | 0.79 | 0.79 | 100 | 0
13 | HOOGHLY |  | Electrical | Augmentation of RAJHAT ZONE 1 Piped Water Supply Scheme by installing ( 01 ) no. Tube well including Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. | SM/09516 | Augmentation | Electric Supply |  |  | VCH/001970/2022-2023 | 12 | 08/06/2022 | 08/06/2022 | WBSEDCL | 7.29 | 0 | 0 | 0
Total | [13 empty] | 30.19 | 15.1 | 50.01