## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KHARSARAI. | SM/09689 | Augmentation | Laying Distribution of left out portion of pipeline to restore the water supply at Kharsarai Functional Hosuehold Tap Connection at Kharsarai Water Supply Scheme within Chanditala-II Block under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000025/2024-2025 | 2224/HUG | 10/06/2024 | 10/07/2024 | ARATI ENGINEERING | 14.18 | 13.75 | 97 | 100
2 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KHARSARAI. | SM/09689 | Augmentation | Sinking of I(One) No Big dia tube well (300 mmx200mm) with supply of PVC Pipe and strainer and having depth upto 150M of Kharsarai W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000145/2022-2023 | 1416/HUG | 12/07/2022 | 11/08/2022 | B.R SUPPLIERS | 9.8 | 9.47 | 96.56 | 100
3 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KHARSARAI. | SM/09689 | Augmentation | Repairing work of O.H.R. and allied works of Boundary Wall, Gate, Pump room etc. at KHARSARAI water supply scheme due to damages caused by Super Cyclone "AMPHAN" Under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000228/2021-2022 | 1867/Hug | 07/10/2021 | 06/11/2021 | R.K. TRADERS | 6.22 | 0 | 0 | 100
4 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KHARSARAI. | SM/09689 | Augmentation | Repairing work of O.H.R. and allied works of Boundary Wall, Gate, Pump room etc. at KHARSARAI water supply scheme due to damages caused by Super Cyclone "AMPHAN" Under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000233/2021-2022 | 1918/HUg | 27/10/2021 | 26/11/2021 | R.K. TRADERS | 6.22 | 6.2 | 99.66 | 100
5 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KHARSARAI. | SM/09689 | Augmentation | Augmentation of Kharsari Piped WS scheme with LDS Rising main Construction of switch room without w/s & toilet construction repairing of boundary wall switch room with FHTC work at Chanditala II Block of Hooghly Dist under Hooghly Divn PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000356/2022-2023 | 638/HUG | 01/04/2022 | 28/09/2022 | M/S S.G. CONSTRUCTION | 166.73 | 163.66 | 98.16 | 80
6 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KHARSARAI. | SM/09689 | Augmentation | Preparation of DPR for Augmentation of Kharsarai Water Supply Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. [Block-Chanditala-II] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000394/2021-2022 | 287/SER | 18/02/2022 | 10/03/2022 | SRIJAN ECHOLOGICAL UPLIFTMENT PVT. LTD. | 2.8 | 2.8 | 99.99 | 100
7 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KHARSARAI. | SM/09689 | Augmentation | Painting of OHR, Construction of Guard Wall with Boundary Wall, Pathwaty, Drain at Kharsarai Water Supply Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000848/2023-2024 | 732/HUG | 05/03/2024 | 04/05/2024 | M/S ATANU DAS | 20.89 | 7.84 | 37.51 | 80
8 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KHARSARAI. | SM/09689 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000008/2022-2023 | 1122/5/HUG | 06/06/2022 |  | Resource Division | 12.32 | 0 | 0 | 0
9 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KHARSARAI. | SM/09689 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000156/2021-2022 | 422/1/Hug | 07/03/2022 |  | Resource Division | 39.63 | 0 | 0 | 0
10 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KHARSARAI. | SM/09689 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000308/2023-2024 | 1384/5/Hug | 15/05/2023 |  | Resource Division | 10.71 | 0 | 0 | 0
Total | [13 empty] | 289.5 | 203.72 | 70.37