## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR GOGHAT. | SM/09691 | Augmentation | Construction of 1 no.400 CUM capacity R.C.C. Elevated Reservoir with 20 m staging height Over R.C.C Bored Pile Foundation / Raft Foundation as per Departmental Type Drawing Design and Specification including pipeline connection and cost of pipes, specials alongwith Laying Distribution System,Laying CI/D.I pipes & specials for Rising Main pipe line in between T.W NO.-I &II to OHR and for Direct Pumping from Proposed T.W NO.-III to nearest feasible distribution system , Construction of 1 No. 3.6 M X3.00 M Switch Room with Additional Plinth Height without Sanitary and Water Supply Arrangements at 3rd T.W, Construction of Boundary wall at 3 rd T.W Site,Soil Investigation works for constrution of OHR including & Providing 2202 nos, FHTC in Goghat for Augmentation of Goghat Water Supply Scheme under Arambagh Sub-DivisionP.H.E. Dte. of Hooghly Division, P.H.E. Dte., Dist. Hooghly. | Assistant Engineer | Junior Engineer (Civill) | ORD/000048/2022-2023 | 832/Hug | 20/04/2022 | 14/02/2023 | M/S S.S. ENTERPRISE | 420.51 | 292.52 | 69.56 | 45
2 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR GOGHAT. | SM/09691 | Augmentation | Preparation of DPR for Augmentation of GOGHAT Piped Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Goghat-I]. | Assistant Engineer | Junior Engineer (Civill) | ORD/000380/2021-2022 | 611/Arg | 31/12/2021 | 30/01/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.85 | 3.83 | 99.37 | 100
3 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR GOGHAT. | SM/09691 | Augmentation | Sinking of 3rd tube-well by D.R. Rig method, Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of GOGHAT Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.HE Dte. |  |  | ORD/000808/2023-2024 | 594/HUG | 22/02/2024 | 22/04/2024 | SPG ENTERPRISES | 31.67 | 0 | 0 | 0
4 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR GOGHAT. | SM/09691 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000020/2022-2023 | 1124/1/HUG | 06/06/2022 |  | Resource Division | 12.32 | 0 | 0 | 0
5 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR GOGHAT. | SM/09691 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000022/2023-2024 | 1234/3/Hug | 28/04/2023 |  | Resource Division | 1.38 | 0 | 0 | 0
6 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR GOGHAT. | SM/09691 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000056/2022-2023 | 1688/6/HUG | 22/08/2022 |  | Resource Division | 22.44 | 0 | 0 | 0
7 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR GOGHAT. | SM/09691 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000099/2022-2023 | 1773/33/Hug | 29/08/2022 |  | Resource Division | 0.69 | 0 | 0 | 0
8 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR GOGHAT. | SM/09691 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000162/2021-2022 | 424/3/Hug | 07/03/2022 |  | Resource Division | 36.05 | 0 | 0 | 0
9 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR GOGHAT. | SM/09691 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000192/2023-2024 | 1385/63/Hug | 15/05/2023 |  | Resource Division | 5.34 | 0 | 0 | 0
10 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR GOGHAT. | SM/09691 | Augmentation | Adhoc Payment to WBSEDCL against Service Connection |  |  | BILL/01124/2023-2024 | null | 28/06/2023 |  | WBSEDCL | 89.37 | 0 | 0 | 0
Total | [13 empty] | 623.63 | 296.34 | 47.52