## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING 4123 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MASAT WATER SUPPLY SCHEME UNDER HOOGHLY DIVISION | SM/11004 | Retrofitting | Laying of Pipeline for left out portion of Masat and its Adjoining Mouzas Water Supply Scheme Under Serampore Sub-Division of Hooghly Division P.H.E Dte .[Block-Chanditala I] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000363/2023-2024 | 2450/HUG | 12/08/2023 | 11/09/2023 | SADHUKHAN ENTERPRISE | 9.87 | 3.72 | 37.71 | 10
2 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING 4123 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MASAT WATER SUPPLY SCHEME UNDER HOOGHLY DIVISION | SM/11004 | Retrofitting | Laying of Pipeline for left out portion of Masat , Banamalipur, AusbaliMouza of MASAT Water Supply Scheme Under Serampore Sub-Division of Hooghly Division P.H.E Dte .[Block-Chanditala I]. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000366/2023-2024 | 2451/HUG | 12/08/2023 | 11/09/2023 | S.D ENTERPRISE (SAMIR KR. DAS) | 8.03 | 4.41 | 54.92 | 35
3 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING 4123 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MASAT WATER SUPPLY SCHEME UNDER HOOGHLY DIVISION | SM/11004 | Retrofitting | Providing Functional Household Tap Connection (FHTC) under JJM within Chhunche & Ausbati Mouza in MASAT PWSS, Block CHANDITALA-I under Serampore Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000583/2022-2023 | 2842/HUG | 16/12/2022 | 30/01/2023 | K. JAGADHATRY & CO. | 39.46 | 26.64 | 67.5 | 30
4 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING 4123 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MASAT WATER SUPPLY SCHEME UNDER HOOGHLY DIVISION | SM/11004 | Retrofitting | Providing Functional Household Tap Connection (FHTC) under JJM within Ajabnagar, Banamalipur & Mukundapur Mouza in MASAT PWSS, Block CHANDITALA-I under Serampore Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000584/2022-2023 | 2843/HUG | 16/12/2022 | 30/01/2023 | BAKSHI ENTERPRISE | 46.45 | 35.35 | 76.1 | 20
5 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING 4123 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MASAT WATER SUPPLY SCHEME UNDER HOOGHLY DIVISION | SM/11004 | Retrofitting | Providing Functional Household Tap Connection (FHTC) under JJM within Masat Mouza in MASAT PWSS, Block CHANDITALA-I under Serampore Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000585/2022-2023 | 2844/HUG | 16/12/2022 | 14/02/2023 | NIRMAN ENGINEERS CO - OPERATIVE SOCIETY LTD. | 66.74 | 58.42 | 87.53 | 30
6 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING 4123 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MASAT WATER SUPPLY SCHEME UNDER HOOGHLY DIVISION | SM/11004 | Retrofitting | Laying Distribution System of Balanced portion with Additional laying including Repairing of Roads (Concrete) within Masat, Banamalipur, Ajabnagar and Ausbali mouzas in Masat W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000898/2023-2024 | 821/HUG | 11/03/2024 | 10/04/2024 | DILIP KUMAR GHOSH | 31.69 | 31.07 | 98.03 | 96
7 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING 4123 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MASAT WATER SUPPLY SCHEME UNDER HOOGHLY DIVISION | SM/11004 | Retrofitting | Sinking of tube-well by D.R. Rig method Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of MASAT Piped Water Supply Scheme under SERAMPORE Sub-Division of Hooghly Division P.HE Dte. |  |  | ORD/000902/2023-2024 | 823/HUG | 11/03/2024 | 10/05/2024 | G. T. AGRO CENTRE | 31.46 | 0 | 0 | 0
8 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING 4123 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MASAT WATER SUPPLY SCHEME UNDER HOOGHLY DIVISION | SM/11004 | Retrofitting | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to be placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Serampore Sub Division under Hooghly Division PHE Dte. 1. Mollarber PWSS 2. Uttar Rajyadharpur PWSS 3. Piarapur PWSS 4. Krishnarampur PWSS 5. Jangalpara PWSS 6. Masat PWSS | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000938/2023-2024 | 108/SER | 23/02/2024 | 01/03/2024 | AMBIAN INFRASTRUCTURE | 0.95 | 0.48 | 50 | 80
Total | [13 empty] | 234.66 | 160.08 | 68.22