## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF SOMRA WATER SUPPLY SCHEME | SM/11005 | Retrofitting | RESTORATION COST FOR PIPE LAYING WORK BALAGARH INCHURA ROAD |  |  | BILL/00182/2024-2025 | BP-2024-25-96 | 02/05/2024 |  | EXECUTIVE ENGINEER HOOGHLY HIGHWAY DIVISION-II PW (ROADS) DTE. | 33.75 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF SOMRA WATER SUPPLY SCHEME | SM/11005 | Retrofitting | Restoration Balagarh Inchura Road |  |  | BILL/01809/2023-2024 | BP-2024-25-1 | 08/04/2024 |  | EXECUTIVE ENGINEER HOOGHLY HIGHWAY DIVISION-II PW (ROADS) DTE. | 33 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF SOMRA WATER SUPPLY SCHEME | SM/11005 | Retrofitting | Providing 1000 nos Functional Household Tap Connection (FHTC) within Bankipur, Jasra, Somra &Baligari Mouza of Somra Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Balagarh] | Assistant Engineer (Civil) |  | ORD/000026/2022-2023 | 1272/Hug | 23/06/2022 | 02/08/2022 | S AND P CONSTRUCTION | 50.86 | 50.04 | 98.39 | 0
4 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF SOMRA WATER SUPPLY SCHEME | SM/11005 | Retrofitting | Providing 1000 nos Functional Household Tap Connection (FHTC) within Masara,Debipur, Belgachhi, Muragari,Rajaipur,Kanpara, Bhelurgari,Kolara & Sukharia Mouza of Somra Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Balagarh] | Assistant Engineer (Civil) |  | ORD/000027/2022-2023 | 728/Hug | 07/04/2022 | 17/05/2022 | JAI BHARAT COMMERCIAL CORPORATION | 50.33 | 49.09 | 97.54 | 0
5 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF SOMRA WATER SUPPLY SCHEME | SM/11005 | Retrofitting | Functional Household Tap Connection (FHTC) under JJM in SOMRA PWSS, Block-BALAGARH under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. SL NO - 01 | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000369/2022-2023 | 2082/HUG | 21/09/2022 | 05/11/2022 | M/S T.K.B. CONSTRUCTION | 53.89 | 53.8 | 99.83 | 0
6 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF SOMRA WATER SUPPLY SCHEME | SM/11005 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000012/2022-2023 | 1123/1/HUG | 06/06/2022 |  | Resource Division | 11 | 0 | 0 | 0
Total | [13 empty] | 232.83 | 152.92 | 65.68