## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR BHADUR UNDER ARAMBAGH SUB DIV PHE DTE | SM/11463 | Augmentation | HIRE CHARGES BILL FOR THE ASSISTANT ENGINEER, ARAMBAGH SUB-DIVISION, PHE DTE. |  |  | BILL/00228/2022-2023 | BP-2022-23-547 | 21/02/2023 |  | M/S PRADYUT KUMAR HAZRA | 1.15 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR BHADUR UNDER ARAMBAGH SUB DIV PHE DTE | SM/11463 | Augmentation | Construction of 200 cum capacity OHR with 20 mtr. staging height including Soil Investigation work & LDS within Sekati(Part) Mouza for Augmentation of Bhadur (Zone-II) Water Supply Scheme at Goghat-I Block under Armabag Sub-Division of Hooghly Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000160/2022-2023 | 1422/Hug | 12/07/2022 | 08/05/2023 | PAUL CONSTRUCTION (RANJIT KUMAR PAUL) | 98.87 | 46.61 | 47.15 | 25
3 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR BHADUR UNDER ARAMBAGH SUB DIV PHE DTE | SM/11463 | Augmentation | Providing Functional Household Tap Connection in BHADUR (Zone-II) Piped Water Supply Scheme including Construction of 2 Nos. 3.6M X 3.0M Switch Room & 2 Nos. Boundary wall at Goghat-I Block under Arambagh Sub-Division of Hooghly Division PHE Dte. SL NO - 4 | Assistant Engineer | Junior Engineer (Civill) | ORD/000233/2022-2023 | 1782/HUG | 30/08/2022 | 14/10/2022 | THREE MAA ENTERPRISE | 78.11 | 45.12 | 57.76 | 75
4 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR BHADUR UNDER ARAMBAGH SUB DIV PHE DTE | SM/11463 | Augmentation | Preparation of DPR for Augmentation of Bhadur Piped Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Goghat-I].(Bhadur Part-A) | Assistant Engineer | Junior Engineer (Civill) | ORD/000239/2022-2023 | 334/Arg | 02/05/2022 | 01/06/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.68 | 3.6 | 76.84 | 0
5 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR BHADUR UNDER ARAMBAGH SUB DIV PHE DTE | SM/11463 | Augmentation | Additional survey work for preparation of DPR for Augmentation of Bhadur Piped Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Goghat-I]. (Bhadur Part-B) | Assistant Engineer | Junior Engineer (Civill) | ORD/000240/2022-2023 | 335/Arg | 02/05/2022 | 01/06/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 0.46 | 0.46 | 100 | 0
6 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR BHADUR UNDER ARAMBAGH SUB DIV PHE DTE | SM/11463 | Augmentation | Laying CI/D.I pipes & specials for Rising Main pipe line in between T.W NO.-I & II to OHR and interconnection with distribution system including allied work for Augmentation of BHADUR (ZONE-II) Water Supply Scheme at Goghat-I Block under Armabag Sub- Division of Hooghly Division, PHE Dte. | Assistant Engineer |  | ORD/000386/2023-2024 | 2568/HUG | 24/08/2023 | 08/10/2023 | PAUL CONSTRUCTION (RANJIT KUMAR PAUL) | 4.91 | 0 | 0 | 0
7 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR BHADUR UNDER ARAMBAGH SUB DIV PHE DTE | SM/11463 | Augmentation | Laying Distribution System of BHADUR (Zone-II) Piped Water Supply Scheme within Bhadur, Mandalganti & Adra Mouza including Repairing of existing Switch rooms, Boundary walls of BHADUR (Zone-I & Zone-II) Water Supply Scheme at Goghat-I Block under Arambagh Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000464/2022-2023 | 2525/HUG | 23/11/2022 | 07/01/2023 | M/S S & P CONSTRUCTION | 85 | 62.71 | 73.78 | 95
8 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR BHADUR UNDER ARAMBAGH SUB DIV PHE DTE | SM/11463 | Augmentation | Augmentation of BHADUR (ZONE-I) Water Supply Scheme with LDS, FHTC, Rising Main & Construction of 350 cum capacity OHR with 20 mtr. staging height including Soil Investigation work at GOGHAT-I Block under Arambagh Sub-Division under Hooghly Division PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000619/2022-2023 | 43/HUG | 04/01/2023 | 31/10/2023 | TITAS CONSTRUCTION | 411.57 | 169.79 | 41.25 | 55
9 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR BHADUR UNDER ARAMBAGH SUB DIV PHE DTE | SM/11463 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000018/2023-2024 | 1106/5/HUG | 17/04/2023 |  | Resource Division | 23.22 | 0 | 0 | 0
10 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR BHADUR UNDER ARAMBAGH SUB DIV PHE DTE | SM/11463 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000051/2022-2023 | 1590/3/Hug | 03/08/2022 |  | Resource Division | 15.4 | 0 | 0 | 0
11 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR BHADUR UNDER ARAMBAGH SUB DIV PHE DTE | SM/11463 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000057/2022-2023 | 1688/4/HUG | 22/08/2022 |  | Resource Division | 120.14 | 0 | 0 | 0
12 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR BHADUR UNDER ARAMBAGH SUB DIV PHE DTE | SM/11463 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000079/2022-2023 | 1773/13/Hug | 29/08/2022 |  | Resource Division | 1.03 | 0 | 0 | 0
13 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR BHADUR UNDER ARAMBAGH SUB DIV PHE DTE | SM/11463 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000118/2022-2023 | 2211/3/Hug | 30/09/2022 |  | Resource Division | 30.8 | 0 | 0 | 0
14 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR BHADUR UNDER ARAMBAGH SUB DIV PHE DTE | SM/11463 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000145/2023-2024 | 1385/15/Hug | 15/05/2023 |  | Resource Division | 14.32 | 0 | 0 | 0
15 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR BHADUR UNDER ARAMBAGH SUB DIV PHE DTE | SM/11463 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000330/2023-2024 | 2607/3/Hug | 29/08/2023 |  | Resource Division | 18.58 | 0 | 0 | 0
16 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR BHADUR UNDER ARAMBAGH SUB DIV PHE DTE | SM/11463 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000372/2023-2024 | 3002/3/Hug | 05/10/2023 |  | Resource Division | 20.89 | 0 | 0 | 0
17 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR BHADUR UNDER ARAMBAGH SUB DIV PHE DTE | SM/11463 | Augmentation | Additional Quotation of Bhadur w/s Scheme,Zone-I,PH No-3 Block-Goghat-I Dist-Hooghly under Electrical division,PHE Dte.(SM/11463) Reference Id-860301435 |  |  | BILL/00622/2024-2025 | 183 | 03/06/2024 |  | WBSEDCL | 1.61 | 0 | 0 | null
18 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR BHADUR UNDER ARAMBAGH SUB DIV PHE DTE | SM/11463 | Augmentation | Adhoc payment to WBSEDCL against service connnection. |  |  | BILL/01122/2023-2024 | null | 28/06/2023 |  | WBSEDCL | 105.92 | 0 | 0 | 0
19 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR BHADUR UNDER ARAMBAGH SUB DIV PHE DTE | SM/11463 | Augmentation | Quotation of New Service Connection for Bhadur w/s scheme,zone-II,TW No-II Dist-Hooghly under ED,PHE Dte |  |  | BILL/02129/2023-2024 | 119 | 20/07/2023 |  | WBSEDCL | 2.8 | 0 | 0 | 0
20 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR BHADUR UNDER ARAMBAGH SUB DIV PHE DTE | SM/11463 | Augmentation | Quotation of New Service Connection for Bhadur w/s Scheme,Zone-I,TW No-III Dist-Hooghly Under ED,PHE Dte |  |  | BILL/02130/2023-2024 | 116 | 20/07/2023 |  | WBSEDCL | 6.86 | 0 | 0 | 0
21 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR BHADUR UNDER ARAMBAGH SUB DIV PHE DTE | SM/11463 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Bhadur water supply scheme, T.W. No.- I & II, Block: Goghat-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/000200/2022-2023 | 827/ED | 14/02/2023 | 15/05/2023 | C.M.S. ENGINEERING CONCERN | 21.95 | 20.53 | 93.51 | 20
22 | HOOGHLY |  | Central Drilling | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR BHADUR UNDER ARAMBAGH SUB DIV PHE DTE | SM/11463 | Augmentation | Providing Drilling crew and other allied works for construction of Tube well (300mm x 200mm x 235 mtrs. Depth) by utilising Departmental machineries for Bhadur W/S Scheme (Z-II, TW-I & II), Goghat-I block under hooghly District, CDD PHE Dte. |  |  | ORD/000466/2022-2023 | 2298/CDD | 30/03/2023 | 29/04/2023 | CHANDA ENTERPRISE | 30.35 | 18.99 | 62.58 | 31
Total | [13 empty] | 1098.63 | 367.81 | 33.48