## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR SOALUK UNDER ARAMBAGH SUB DIVISION PHE DTE | SM/11467 | Augmentation | Construction of Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between T.W & Distribution For Augmentation of SOALUK Piped Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.HE Dte. within Pursurah Block. | Assistant Engineer | Junior Engineer (Civill) | ORD/000125/2023-2024 | 1459/HUG | 18/05/2023 | 17/06/2023 | RAYCON COOPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD | 6.21 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR SOALUK UNDER ARAMBAGH SUB DIVISION PHE DTE | SM/11467 | Augmentation | Laying Distribution System with providing Functional Household Tap Connection of SOALUK Piped Water Supply Scheme within Soaluk (North) Mouza including Repairing of existing Switch Rooms at PURSURAH Block under Arambagh Sub-Division of Hooghly Division PHE Dte. SL NO - 05 | Assistant Engineer | Junior Engineer (Civill) | ORD/000234/2022-2023 | 1783/HUG | 30/08/2022 | 29/09/2022 | R.K. TRADERS | 52.81 | 52.81 | 100 | 0
3 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR SOALUK UNDER ARAMBAGH SUB DIVISION PHE DTE | SM/11467 | Augmentation | Preparation of DPR for Augmentation of Soaluk Piped Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Pursura]. | Assistant Engineer | Junior Engineer (Civill) | ORD/000242/2022-2023 | 339/Arg | 02/05/2022 | 01/06/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.74 | 3.68 | 98.55 | 0
4 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR SOALUK UNDER ARAMBAGH SUB DIVISION PHE DTE | SM/11467 | Augmentation | Repair and Renovation Works of R.C.C. Elevated Reservoir ,Construction of Boundary Wall Of Head Work site at SOALUK Piped Water Supply Scheme under ARAMBAGH Sub¿Division of Hooghly Division P.HE Dte | Assistant Engineer | Junior Engineer (Civill) | ORD/000361/2023-2024 | 2453/HUG | 12/08/2023 | 11/10/2023 | P.K. GHOSH & CO. | 31.41 | 10.64 | 33.86 | 70
5 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR SOALUK UNDER ARAMBAGH SUB DIVISION PHE DTE | SM/11467 | Augmentation | Laying Distribution System, of proposed pipe line of SOALUK (EAST,WEST,& SOUTH PORTION) Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer |  | ORD/000602/2022-2023 | 2888/HUG | 22/12/2022 | 22/03/2023 | M/S CARE | 191.47 | 0 | 0 | 0
6 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR SOALUK UNDER ARAMBAGH SUB DIVISION PHE DTE | SM/11467 | Augmentation | Functional Household Tap Connection (FHTC) under JJM in SOALUK PWSS, Block. PURSURAH under Arambagh Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000603/2022-2023 | 2889/HUG | 22/12/2022 | 20/02/2023 | M/S CARE | 86.64 | 82.65 | 95.39 | 70
7 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR SOALUK UNDER ARAMBAGH SUB DIVISION PHE DTE | SM/11467 | Augmentation | Sinking of 1 no 300 X200 mm dia Tube Well 180 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at proposed Tube Well Site of SOALUK W/S Scheme under ARAMBAG Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000672/2022-2023 | 170/HUG | 16/01/2023 | 15/02/2023 | GITA ENTERPRISE | 13.54 | 6.77 | 50 | 100
8 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR SOALUK UNDER ARAMBAGH SUB DIVISION PHE DTE | SM/11467 | Augmentation | Laying Distribution System, of proposed pipe line of SOALUK (EAST,WEST,& SOUTH PORTION) Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000686/2022-2023 | 281/HUG | 01/02/2023 | 02/05/2023 | M/S CARE | 191.47 | 145.99 | 76.25 | 70
9 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR SOALUK UNDER ARAMBAGH SUB DIVISION PHE DTE | SM/11467 | Augmentation | Construction of 1 No. switch room (5.40 m x 3.60 m) with sanitary arrangement At Proposed T.W Site OF SOALUK Water Supply Scheme Under Arambagh Sub-Division Under Hooghly Division P.H.E Dte. | Assistant Engineer |  | ORD/000713/2022-2023 | 450/HUG | 16/02/2023 | 02/04/2023 | TANISA ENTERPRISE | 7.5 | 7.5 | 100 | 0
10 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR SOALUK UNDER ARAMBAGH SUB DIVISION PHE DTE | SM/11467 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000008/2023-2024 | 1106/2/HUG | 17/04/2023 |  | Resource Division | 14.48 | 0 | 0 | 0
11 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR SOALUK UNDER ARAMBAGH SUB DIVISION PHE DTE | SM/11467 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000108/2022-2023 | 1773/42/Hug | 29/08/2022 |  | Resource Division | 1.38 | 0 | 0 | 0
12 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR SOALUK UNDER ARAMBAGH SUB DIVISION PHE DTE | SM/11467 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000193/2023-2024 | 1385/64/Hug | 15/05/2023 |  | Resource Division | 12.26 | 0 | 0 | 0
13 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR SOALUK UNDER ARAMBAGH SUB DIVISION PHE DTE | SM/11467 | Augmentation | Electric quot. of WBSEDCL for New service Connection of Soaluk T/W-IV W/S scheme under Electrical Division PHE Dte. (SM/11467) |  |  | BILL/01614/2024-2025 | 376 | 12/08/2024 |  | WBSEDCL | 3.31 | 0 | 0 | null
14 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR SOALUK UNDER ARAMBAGH SUB DIVISION PHE DTE | SM/11467 | Augmentation | Quotation Bill for New Service Connection at Aug. of Soaluk W/S. Sch. PH-I |  |  | BILL/01873/2022-2023 | 208 | 22/03/2023 |  | WBSEDCL | 3 | 0 | 0 | 0
15 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR SOALUK UNDER ARAMBAGH SUB DIVISION PHE DTE | SM/11467 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Soaluk water supply scheme, T.W. No.- I, Block: Pursurah, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000114/2022-2023 | 668/ED | 02/02/2023 | 03/05/2023 | M/S BIPUL BANERJEE | 10.96 | 10.17 | 92.74 | 100
16 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR SOALUK UNDER ARAMBAGH SUB DIVISION PHE DTE | SM/11467 | Augmentation | Replacement of some electrical devices, equipments and items, outdoor lighting, voltage corrector etc. including allied works for Soaluk water supply scheme, P.H. No. I, District- Hooghly under Electrical Division, PHE Dte. |  | Junior Engineer4 | ORD/000316/2022-2023 | 492/HMSD | 02/03/2023 | 01/04/2023 | RADHARANI ENTERPRISE | 2.99 | 1.49 | 50 | 100
17 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR SOALUK UNDER ARAMBAGH SUB DIVISION PHE DTE | SM/11467 | Augmentation | Replacement of some electrical devices and equipments like mcc cum pdb etc. including allied works for Soaluk water supply scheme, P.H. No. I, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/000318/2022-2023 | 494/HMSD | 02/03/2023 | 01/04/2023 | N.S. TRADING | 4.21 | 4.21 | 100 | 0
18 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR SOALUK UNDER ARAMBAGH SUB DIVISION PHE DTE | SM/11467 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Soaluk water supply scheme, T.W. No. IV, Block: Pursurah, District: Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer1 | ORD/002473/2023-2024 | 334/ED | 21/02/2024 | 21/05/2024 | DEY ENTERPRISE | 10.43 | 0 | 0 | 0
19 | HOOGHLY |  | Central Drilling | AUGMENTATION OF GROUND BASED PIPED WATER SPPLY SCHEME FOR SOALUK UNDER ARAMBAGH SUB DIVISION PHE DTE | SM/11467 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 210 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR SOALUK W/S SCH, UNDER HOOGHLY DISTRICT CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000353/2022-2023 | 1559/CDD | 08/12/2022 | 07/01/2023 | ASHUTOSH DAS & CO | 12.66 | 9.62 | 75.97 | 0
Total | [13 empty] | 660.46 | 335.52 | 50.8