## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SIBAICHANDI | SM/11866 | Augmentation | Regarding damage of PMGSY Road |  |  | BILL/00361/2024-2025 | BP-2024-25-294 | 10/07/2024 |  | WEST BENGAL STATE RURAL DEVELOPMENT AGENCY | 9.93 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SIBAICHANDI | SM/11866 | Augmentation | DAMAGED PIPELINE OF PMGSY ROAD FROM RUHIA TO MAJINAN VIA SHIBAICHANDI RAILWAY STATION UNDER DHANIAKHALI BLOCK |  |  | BILL/00932/2023-2024 | BP-2023-24-677 | 22/12/2023 |  | WEST BENGAL STATE RURAL DEVELOPMENT AGENCY | 16.58 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SIBAICHANDI | SM/11866 | Augmentation | AUGMENTATION Of SIBAICHANDI ZONE-II Piped Water Supply Scheme with LDS, Rising Main& construction of boundary wall at HW site under DHANIAKHALI Block, District:- Hooghly [AUGMENTATION SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000054/2023-2024 | 1219/HUG | 27/04/2023 | 26/06/2023 | SK MAIDUL ISLAM | 54.16 | 38.57 | 71.22 | 80
4 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SIBAICHANDI | SM/11866 | Augmentation | Providing FHTC (At ZONE-I & ZONE-II), construction of boundary wall at Proposed TW site OF ZONE-I For AUGMENTATION of SIBAICHANDI ZONE-I & ZONE-II Piped Water Supply Scheme under DHANIAKHALI Block, District:- Hooghly [AUGMENTATION SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000055/2023-2024 | 1220/HUG | 27/04/2023 | 26/07/2023 | R CONSTRUCTION | 82.07 | 36.04 | 43.91 | 80
5 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SIBAICHANDI | SM/11866 | Augmentation | Laying Pipeline in uncovered areas and providing FHTC at the left out portions of Sibachandi (Zone-I & Zone-II) Piped Water Supply Scheme under Dhaniakhali-II Block of Chinsurah Sub-Division under Hooghly Division, PHE Dte. |  |  | ORD/000055/2024-2025 | 2365/HUG | 21/06/2024 | 21/07/2024 | MAA JAGADHATRI CONSTRUCTION | 9.77 | 0 | 0 | 0
6 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SIBAICHANDI | SM/11866 | Augmentation | Construction of 2 Nos. switch-room at different TW site of SIBAICHANDI Water Supply Scheme under DHANIAKHALI Block, District:- Hooghly [AUGMENTATION SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000083/2023-2024 | 1343/HUG | 11/05/2023 | 25/06/2023 | SUDIPTA DAS | 12.29 | 6.14 | 50 | 95
7 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SIBAICHANDI | SM/11866 | Augmentation | AUGMENTATION Of SIBAICHANDI ZONE-I Piped Water Supply Scheme with LDS, Rising Main & construction of boundary wall at HW site under DHANIAKHALI Block, District:- Hooghly [AUGMENTATION SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000196/2023-2024 | 1787/HUG | 16/06/2023 | 14/09/2023 | M/S BISWAS CONSTRUCTION | 138.84 | 85.19 | 61.36 | 30
8 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SIBAICHANDI | SM/11866 | Augmentation | Construction of 300 cum capacity 20 Mtr. staging height RCC Over Head Reservoir (Superstructure part as per Departmental Drawing), pipe connection and cost of pipes & specials with necessary soil investigation with foundation design as per soil test report for AUGMENTATION of SIBAICHANDI ZONE-I Water Supply Scheme under DHANIAKHALI BLOCK, District:- Hooghly | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000331/2023-2024 | 2421/HUG | 11/08/2023 | 07/05/2024 | M/S T.K.B. CONSTRUCTION | 92.66 | 45.43 | 49.03 | 30
9 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SIBAICHANDI | SM/11866 | Augmentation | Preparation of DPR for Augmentation of Sibaichandi Piped Water Supply Scheme under Chinsurah Sub-Division of Hooghly Division P.H.E.Dte. (Block: Dhaniakhali) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000421/2021-2022 | 92/CH | 03/02/2022 | 13/02/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.07 | 4.02 | 98.8 | 0
10 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SIBAICHANDI | SM/11866 | Augmentation | 2ND CONTINUATION ORDER FOR Deployment of 5 (five) Nos. Security Guard without Arm for guarding arrangement of Office cum store at Hooghly Division & Chinsurah Sub-Division Office under Chinsurah Sub-Division, under Hooghly Division, PHE Dte. Period 4 months from 01.04.2022 to 31.07.2022. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000493/2021-2022 | 621/Hug | 31/03/2022 | 31/07/2022 | PRASUN ENTERPRISE (PRASUN BISWAS) | 4.26 | 0 | 0 | 0
11 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SIBAICHANDI | SM/11866 | Augmentation | Sinking of 1 (One) No Big dia tube well (300 mm x200mm) with supply of PVC Pipe and strainer and having depth upto 180 Mtr at SHIBAICHANDI W/S Scheme under Chinsurah Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000602/2023-2024 | 3317/HUG | 10/11/2023 | 10/12/2023 | B.K ENTERPRISE | 14.48 | 7.21 | 49.81 | 95
12 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SIBAICHANDI | SM/11866 | Augmentation | Sinking of Six Nos. Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto180 Mtr at BAGNAN ZONE-II(2NOS.), SIBAICHANDI ZONE-I(2NOS.), SRIKRISHNAPUR ZONE-II(2NOS.) PWSS of CHINSURAH Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000788/2022-2023 | 883/HUG | 27/03/2023 | 11/05/2023 | B.K ENTERPRISE | 75.32 | 0 | 0 | 80
13 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SIBAICHANDI | SM/11866 | Augmentation | Laying Pipeline in left out portions including Repairing of RCC OHR, Switch Room, Boundary Wall, Pathway etc. of Sibaichandi Zone-I Piped Water Supply Scheme under Dhaniakhali Block of Chinsurah Sub-Division under Hooghly Division, PHE Dte. |  |  | ORD/000789/2023-2024 | 534/HUG | 20/02/2024 | 21/03/2024 | M/S BISWAS CONSTRUCTION | 32.28 | 0 | 0 | 0
14 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SIBAICHANDI | SM/11866 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chinsurah Sub Division under Hooghly Division PHE Dte 1. Sibaichandi PWSS 2. Srikrishnapur PWSS 3. Aymanbabpur PWSS 4. Baichi PWSS 5. Balun PWSS 6. Dwarbasini PWSS | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000827/2023-2024 | 205/CH | 29/02/2024 | 07/03/2024 | LIMRA SOCIAL WELFARE SOCIETY | 0.95 | 0.95 | 100 | 50
15 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SIBAICHANDI | SM/11866 | Augmentation | Laying Balance pipeline within left out Mouzas / Habitations of different PWSS under DHANIAKHALI Block of CHINSURAH Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000846/2023-2024 | 3563/HUG | 05/12/2023 | 04/01/2024 | MUKHERJEE AND CO | 43.92 | 20.73 | 47.2 | 95
16 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SIBAICHANDI | SM/11866 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000082/2023-2024 | 1264/24/HUG | 03/05/2023 |  | Resource Division | 33.5 | 0 | 0 | 0
17 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SIBAICHANDI | SM/11866 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000126/2022-2023 | 2209/1/Hug | 30/09/2022 |  | Resource Division | 0.05 | 0 | 0 | 0
18 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SIBAICHANDI | SM/11866 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000302/2023-2024 | 1386/58/Hug | 15/05/2023 |  | Resource Division | 12.71 | 0 | 0 | 0
19 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SIBAICHANDI | SM/11866 | Augmentation | Adhoc Payment to WBSEDCL against Service Connection |  |  | BILL/01124/2023-2024 | null | 28/06/2023 |  | WBSEDCL | 89.37 | 0 | 0 | 0
20 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SIBAICHANDI | SM/11866 | Augmentation | "Quotation Bill for New Service Connection at Sibaichandi W/S. Sch. TW-I & II |  |  | BILL/03758/2023-2024 | 250, 251 | 05/09/2023 |  | WBSEDCL | 27.99 | 0 | 0 | 0
21 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SIBAICHANDI | SM/11866 | Augmentation | "Quotation Bill for New Service Connection at Sibaichandi TW-I & II |  |  | BILL/03788/2023-2024 | 309 & 310 | 27/09/2023 |  | WBSEDCL | 4.03 | 0 | 0 | 0
22 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SIBAICHANDI | SM/11866 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Augmentation of Sibaichandi water supply scheme TW No I and II Block DhaniakhalI District Hooghly under ED PHED. | Assistant Engineer 2 ,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer1 | ORD/000227/2022-2023 | 858/ED | 14/02/2023 | 15/05/2023 | ANJAN ENTERPRISE | 21.45 | 0 | 0 | 45
Total | [13 empty] | 780.67 | 244.29 | 31.29