## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF AMDOBA WATER SUPPLY SCHEME | SM/12001 | Retrofitting | Construction of Boundary Wall, Internal Pathway at 2nd TW Site of AMDOBA Water Supply Scheme under Arambagh Sub-Division, of Hooghly Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000534/2022-2023 | 2735/HUG | 07/12/2022 | 31/03/2024 | DREAM INFRASTRUCTURE | 4.83 | 3.24 | 67.16 | 60
2 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FHTC WITHIN THE COMMAND AREA OF AMDOBA WATER SUPPLY SCHEME | SM/12001 | Retrofitting | Providing Functional Household Tap Connection (FHTC) within the command area of AMDOBA Water Supply Scheme Under Arambag Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000658/2022-2023 | 155/HUG | 16/01/2023 | 07/03/2023 | AICH CONSTRUCTION | 59.77 | 53.22 | 89.04 | 100
Total | [13 empty] | 64.59 | 56.46 | 87.4