## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Augmentation of Goradaha Piped Water Supply Scheme, Block- Goradaha, District-Hooghly | SM/12228 | Augmentation | Construction of supporting arrangement for LDS and allied works of GHORADAHA Piped Water Supply Scheme under Arambag Sub-Division of Hooghly Division, PHE Dte. |  |  | ORD/000060/2024-2025 | 2407/HUG | 26/06/2024 | 10/08/2024 | DILIP KUMAR GHOSH | 17.92 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | Augmentation of Goradaha Piped Water Supply Scheme, Block- Goradaha, District-Hooghly | SM/12228 | Augmentation | Preparation of DPR for Augmentation of Ghoradaha Piped Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Khanakul-II]. | Assistant Engineer,Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/000100/2022-2023 | 390/Arg | 31/05/2022 | 30/06/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.22 | 3.34 | 79.17 | 0
3 | HOOGHLY |  | Hooghly Division | Augmentation of Goradaha Piped Water Supply Scheme, Block- Goradaha, District-Hooghly | SM/12228 | Augmentation | Augmentation of GHORADAHA Piped Water Supply Scheme by Sinking of 2 Nos. Tube well, Laying Distribution System, Construction of 2 Nos. Switch Room at 3rd & 4th Tubewell site and Boundary wall at 2nd, 3rd & 4th Tubewell site under Arambag Sub-Division of Hooghly Division PHE Dte. within Khanakul - II Block. | Assistant Engineer | Junior Engineer (Civill) | ORD/000702/2022-2023 | 396/HUG | 10/02/2023 | 11/05/2023 | NIRMAN ENGINEERS CO - OPERATIVE SOCIETY LTD. | 202.79 | 43.12 | 21.26 | 20
4 | HOOGHLY |  | Hooghly Division | Augmentation of Goradaha Piped Water Supply Scheme, Block- Goradaha, District-Hooghly | SM/12228 | Augmentation | Augmentation of GHORADAHA Piped Water Supply Scheme with Construction of Boundary wall at 1st T.W Site, Repairing of Switch room, Laying of Rising main with necessary interconnection with T.W. & Distribution System & Functional Household tap Connection under Arambag SUb-Division of Hooghly Division, PHE Dte. within Khanakul -II Block. | Assistant Engineer | Junior Engineer (Civill) | ORD/000716/2022-2023 | 493/HUG | 20/02/2023 | 21/05/2023 | DILIP KUMAR GHOSH | 149.07 | 74.52 | 49.99 | 25
5 | HOOGHLY |  | Hooghly Division | Augmentation of Goradaha Piped Water Supply Scheme, Block- Goradaha, District-Hooghly | SM/12228 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000150/2023-2024 | 1385/21/Hug | 15/05/2023 |  | Resource Division | 19.81 | 0 | 0 | 0
6 | HOOGHLY |  | Electrical | Augmentation of Goradaha Piped Water Supply Scheme, Block- Goradaha, District-Hooghly | SM/12228 | Augmentation | Adhoc Payment to WBSEDCL against Service Connection |  |  | BILL/01124/2023-2024 | null | 28/06/2023 |  | WBSEDCL | 89.37 | 0 | 0 | 0
7 | HOOGHLY |  | Electrical | Augmentation of Goradaha Piped Water Supply Scheme, Block- Goradaha, District-Hooghly | SM/12228 | Augmentation | Quotation for New Service Connection of Goradaha w/s Scheme,TW No-3 Block-Khanakul-I,Dist-Hooghly under ED,PHE Dte |  |  | BILL/03627/2023-2024 | 220 | 25/08/2023 |  | WBSEDCL | 6.53 | 0 | 0 | 0
8 | HOOGHLY |  | Electrical | Augmentation of Goradaha Piped Water Supply Scheme, Block- Goradaha, District-Hooghly | SM/12228 | Augmentation | Quotation Bill for New Service Connection at |  |  | BILL/04140/2023-2024 | 390 | 02/11/2023 |  | WBSEDCL | 8.75 | 0 | 0 | 0
9 | HOOGHLY |  | Electrical | Augmentation of Goradaha Piped Water Supply Scheme, Block- Goradaha, District-Hooghly | SM/12228 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Goradaha water supply scheme, T.W. No.- I & II, Block: Khanakul-II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 ,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000212/2022-2023 | 839/ED | 14/02/2023 | 15/05/2023 | M/S S R ENTERPRISE | 21.49 | 5.19 | 24.17 | 15
Total | [13 empty] | 519.94 | 126.18 | 24.27