## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Dhaniakhali | Hooghly Division | BARUL PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12246 | New | Protection Work at H/W & 2ND T.W Site for HASAMPUR W/S under Chinsurah Sub - Division of Hooghly Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000370/2023-2024 | 2460/HUG | 12/08/2023 | 11/10/2023 | CHAKRABORTY ENTERPRISE | 35.44 | 30.86 | 87.1 | 100
2 | HOOGHLY | Dhaniakhali | Hooghly Division | BARUL PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12246 | New | RUDRANI, BARUL, CHALUA, LOKABATI ,KHAJURDAHA, SIMLA, CHAUTARA, KUMRUL, KANAJOLI, KAMALPUR & DURGAPUR Piped Water Supply Schemes with T.W, SWITCH ROOM , BOLTNDARY WALL, RISING MAIN, LDS, FHTC & Construction of OHR with 20 mtr. staging height including Soil Investigation work at DHANIAKHALI Block under CHINSURAH Sub-Division Under Hooghly Division PHE Dte. in connection wih JJM.. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000372/2023-2024 | 2494/HUG | 17/08/2023 | 01/09/2025 | S. P. CONSTRUCTION | 5872.33 | 229.04 | 3.9 | 30
3 | HOOGHLY | Dhaniakhali | Hooghly Division | BARUL PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12246 | New | Material Requisition To Resource Division |  |  | RTOR000117/2023-2024 | 1264/12/HUG | 03/05/2023 | 03/05/2023 | Resource Division | 7.36 | 0 | 0 | 0
4 | HOOGHLY | Dhaniakhali | Hooghly Division | BARUL PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12246 | New | Material Requisition To Resource Division |  |  | RTOR000231/2023-2024 | 1386/10/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 20.6 | 0 | 0 | 0
5 | HOOGHLY | Dhaniakhali | Electrical | BARUL PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12246 | New | Add. Electric quot. of WBSEDCL for New service Connection of Barul T/W-I W/S scheme under Electrical Division PHE Dte. (SM/12246) App. No- 5003997215 Ref. Id- 503556940 |  |  | BILL/02093/2024-2025 | 539 | 29/10/2024 | 29/10/2024 | WBSEDCL | 1.34 | 0 | 0 | 0
6 | HOOGHLY | Dhaniakhali | Electrical | BARUL PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12246 | New | Barul PH__II Water supply Scheme |  |  | BILL/05989/2023-2024 | 726 | 05/02/2024 | 05/02/2024 | WBSEDCL | 4.11 | 0 | 0 | 0
7 | HOOGHLY | Dhaniakhali | Electrical | BARUL PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12246 | New | Barul PH__I Water supply Scheme |  |  | BILL/05990/2023-2024 | 727 | 05/02/2024 | 05/02/2024 | WBSEDCL | 3.04 | 0 | 0 | 0
8 | HOOGHLY | Dhaniakhali | Electrical | BARUL PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/12246 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Barul water supply scheme, T.W. No. I & II, Block: Dhaniakhali, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer1 | ORD/000076/2022-2023 | 3458/ED | 30/12/2022 | 29/12/2025 | T S CONSTRUCTION | 20.35 | 0 | 0 | 65
Total | [13 empty] | 5964.55 | 259.9 | 4.36