## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Khanakul - II | Hooghly Division | GROUND WATER BASED MARAKHANA (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/13324 | New | NATIBPUR, ROUTHKHANA, HIRAPUR(ZONE-I), HIRAPUR(ZONE-II) , HAYATPUR, MOSTAFAPUR, CHINRA(ZONE-I), CHTNRA( ZONE-I), MARAKHANA(ZONE-I), MARAKHANA(ZONE-II) Piped Water Supply Scheme with T.W, SWITCH ROOM, BOUNDARY WALL, RISING MAIN, LDS, FHTC & Construction of different capacity OHR with 20 mtr. staging height including Soil Investigation work at KHANAKUL-II Block under ARAMBAGH Sub-Division of Hooghly Division PHE Dte. | Assistant Engineer | Junior Engineer (Civill),Khanakul 2 Block Junior Engineer | ORD/000551/2023-2024 | 3168/HUG | 19/10/2023 | 13/10/2024 | MACKINTOSH BURN LIMITED | 5743.06 | 0 | 0 | 23
2 | HOOGHLY | Khanakul - II | Hooghly Division | GROUND WATER BASED MARAKHANA (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/13324 | New | Material Requisition To Resource Division |  |  | RTOR000485/2023-2024 | 3057/62/Hug | 11/10/2023 |  | Resource Division | 14.29 | 0 | 0 | 0
3 | HOOGHLY | Khanakul - II | Electrical | GROUND WATER BASED MARAKHANA (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/13324 | New | Quotation of New Service Connection for Marakhana w/s Scheme,Zone-I,PH No-I Block-Khanakul-II Dist-Hooghly under Electrical Division,PHE Dte.(SM/13324) Application no-5004026546 Reference Id-503570690 |  |  | BILL/00429/2024-2025 | 110 | 09/05/2024 |  | WBSEDCL | 5.15 | 0 | 0 | null
4 | HOOGHLY | Khanakul - II | Electrical | GROUND WATER BASED MARAKHANA (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/13324 | New | Quotation of New Service Connection for Marakhana w/s Scheme,Zone-I,PH No-II Block-Khanakul-II Dist-Hooghly under Electrical Division,PHE Dte.(SM/13324) Application no-5004073228 Reference Id-503597246 |  |  | BILL/00441/2024-2025 | 125 | 17/05/2024 |  | WBSEDCL | 8.29 | 0 | 0 | null
5 | HOOGHLY | Khanakul - II | Electrical | GROUND WATER BASED MARAKHANA (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/13324 | New | Adhoc payment to WBSEDCL against service connnection. |  |  | BILL/01122/2023-2024 | null | 28/06/2023 |  | WBSEDCL | 105.92 | 0 | 0 | 0
6 | HOOGHLY | Khanakul - II | Electrical | GROUND WATER BASED MARAKHANA (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/13324 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Marakhana water supply scheme, Zone-I, T.W. No.- I & II, Block: Khanakul-II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer3 | ORD/000188/2022-2023 | 781 /ED | 09/02/2023 | 10/05/2023 | S.G.-ENTERPRISE | 20.5 | 0 | 0 | 0
Total | [13 empty] | 5897.2 | 0 | 0