## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS OF DHARAMPUR PWSS FOR PROVIDING 1600 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION PHE DTE. | SM/13356 | Retrofitting | Providing Functional Household Tap Connection (FHTC) under JJM within left out portion of DHARAMPUR PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) |  | ORD/000029/2023-2024 | 1129/HUG | 19/04/2023 | 03/06/2023 | M/S SHIVAM UDYOG | 54.23 | 0 | 0 | 97
2 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS OF DHARAMPUR PWSS FOR PROVIDING 1600 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION PHE DTE. | SM/13356 | Retrofitting | Providing FHTC in left out portion at Maynadanga under Dharampur W/S scheme under Chinsurah Sub Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000031/2024-2025 | 533/CH | 14/06/2024 | 21/06/2024 | NOBLE ENGINEERS CO-OPERATIVE SOCIETY LTD. | 5 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS OF DHARAMPUR PWSS FOR PROVIDING 1600 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION PHE DTE. | SM/13356 | Retrofitting | Providing FHTC in left out portion at Sukanta Nagar under Dharampur W/S scheme under Chinsurah Sub Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000032/2024-2025 | 534/CH | 14/06/2024 | 21/06/2024 | NOBLE ENGINEERS CO-OPERATIVE SOCIETY LTD. | 4.99 | 0 | 0 | 0
4 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS OF DHARAMPUR PWSS FOR PROVIDING 1600 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION PHE DTE. | SM/13356 | Retrofitting | Construction of 1 No. 3.6 m X 3.0 m Switch Room with Additional Plinth Height, with Sanitary and Water Supply arrangement, Construction of 2 nos. Boundary wall &Laying of C.I/D.I pipes & specials for connection of Proposed 2 nos.T.W with distribution system, FHTC of DHARAMPUR W/S Scheme under Chinsurah Sub - Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000087/2023-2024 | 1341/HUG | 11/05/2023 | 25/06/2023 | NOBLE ENGINEERS CO-OPERATIVE SOCIETY LTD. | 44.76 | 0 | 0 | 75
5 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS OF DHARAMPUR PWSS FOR PROVIDING 1600 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION PHE DTE. | SM/13356 | Retrofitting | Rising Main in between 4th T.W to OHR Bypass arrangement and interconnection with Distribution System for DHARAMPUR Water Supply Scheme Under Chinsurah Sub-Division. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000253/2022-2023 | 720/CH | 23/08/2022 | 07/09/2022 | SOUMYADIP DE | 3.71 | 3.27 | 88.19 | 0
6 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS OF DHARAMPUR PWSS FOR PROVIDING 1600 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION PHE DTE. | SM/13356 | Retrofitting | Functional Household Tap Connection (FHTC) under JJM in DHARAMPUR PWSS, Block-CHINSURAH MOGRA under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. SL NO -02 | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000370/2022-2023 | 2083/HUG | 21/09/2022 | 21/10/2022 | M/S RAJKUMAR KHAN | 16.76 | 16.44 | 98.09 | 0
7 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS OF DHARAMPUR PWSS FOR PROVIDING 1600 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION PHE DTE. | SM/13356 | Retrofitting | Laying of Pipe line within left out portion for providing Functional Household Tap Connection (FHTC) under JJM in DHARAMPUR PWSS, Block-CHINSURAH MOGRA under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. SL NO - 03 | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000371/2022-2023 | 2084/HUG | 21/09/2022 | 21/10/2022 | MECCANO UNEMPLOYED ENGINEERS CO - OPERATIVE SOCIETY LTD. | 17.05 | 16.52 | 96.88 | 0
8 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS OF DHARAMPUR PWSS FOR PROVIDING 1600 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION PHE DTE. | SM/13356 | Retrofitting | Connection of replacement T.W. with existing rising main pipe line at head works site for Dharampur W/S under Chinsurah Sub - Division P.H.E. Dte. | Assistant Engineer (Civil) |  | ORD/000718/2022-2023 | 12B/CH | 06/01/2023 | 21/01/2023 | M/S BIMAL DAS AND CO. | 0.97 | 0.96 | 99.77 | 0
9 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS OF DHARAMPUR PWSS FOR PROVIDING 1600 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION PHE DTE. | SM/13356 | Retrofitting | Sinking of Six Nos. Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto180 Mtr at DHARAMPUR, BADINAN, BHASTARA, KOLA, PATNABHAIRABPUR, GURAP PWSS of CHINSURAH Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) |  | ORD/000787/2022-2023 | 882/HUG | 27/03/2023 | 11/05/2023 | AUXILIARY TUBEWELL DRILLERS | 75.1 | 13.09 | 17.43 | 65
10 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS OF DHARAMPUR PWSS FOR PROVIDING 1600 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION PHE DTE. | SM/13356 | Retrofitting | Providing FHTC in rest out portion of at Chatterjee Bagan of Dharampur PWSS under Chinsurah Sub Division under Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001045/2023-2024 | 289/CH | 15/03/2024 | 22/03/2024 | NOBLE ENGINEERS CO-OPERATIVE SOCIETY LTD. | 0.96 | 0.95 | 99.71 | 80
11 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS OF DHARAMPUR PWSS FOR PROVIDING 1600 NOS. FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN COMMAND AREA OF THE SCHEME UNDER HOOGHLY DIVISION PHE DTE. | SM/13356 | Retrofitting | Providing FHTC in rest out portion of at Maynadanga of Dharampur PWSS under Chinsurah Sub Division under Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001046/2023-2024 | 290/CH | 15/03/2024 | 22/03/2024 | NOBLE ENGINEERS CO-OPERATIVE SOCIETY LTD. | 0.96 | 0.95 | 99.71 | 80
Total | [13 empty] | 224.48 | 52.19 | 23.25