## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Goghat - I | Hooghly Division | GROUND WATER BASED NAKUNDA PIPED WATER SUPPLY SCHEME IN GOGHAT-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/13414 | New | NAKUNDA Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 250 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under GOGHAT-I Block of Arambag SUb-Division under Hooghly Division, PHE Dte. [NEW SCHEME] | Assistant Engineer | Junior Engineer (Civill) | ORD/000147/2023-2024 | 1502/HUG | 22/05/2023 | 16/02/2024 | UNIQUE AGENCY | 554.69 | 166.45 | 30.01 | 50
2 | HOOGHLY | Goghat - I | Hooghly Division | GROUND WATER BASED NAKUNDA PIPED WATER SUPPLY SCHEME IN GOGHAT-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/13414 | New | Material Requisition To Resource Division |  |  | RTOR000160/2023-2024 | 1385/31/Hug | 15/05/2023 |  | Resource Division | 10.84 | 0 | 0 | 0
3 | HOOGHLY | Goghat - I | Hooghly Division | GROUND WATER BASED NAKUNDA PIPED WATER SUPPLY SCHEME IN GOGHAT-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/13414 | New | Material Requisition To Resource Division |  |  | RTOR000329/2023-2024 | 2607/Hug | 29/08/2023 |  | Resource Division | 35.3 | 0 | 0 | 0
4 | HOOGHLY | Goghat - I | Hooghly Division | GROUND WATER BASED NAKUNDA PIPED WATER SUPPLY SCHEME IN GOGHAT-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/13414 | New | Material Requisition To Resource Division |  |  | RTOR000471/2023-2024 | 3057/13/Hug | 11/10/2023 |  | Resource Division | 10.84 | 0 | 0 | 0
5 | HOOGHLY | Goghat - I | Electrical | GROUND WATER BASED NAKUNDA PIPED WATER SUPPLY SCHEME IN GOGHAT-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/13414 | New | Adhoc payment to WBSEDCL against service connnection. |  |  | BILL/01121/2023-2024 | null | 28/06/2023 |  | WBSEDCL | 97.65 | 0 | 0 | 0
6 | HOOGHLY | Goghat - I | Electrical | GROUND WATER BASED NAKUNDA PIPED WATER SUPPLY SCHEME IN GOGHAT-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/13414 | New | quotation of New Service Connection for Nakunda W/S Scheme, TW No-I Block-Goghat-I, Dist-Hooghly under ED,PHE Dte |  |  | BILL/02478/2023-2024 | 151 | 01/08/2023 |  | WBSEDCL | 5.07 | 0 | 0 | 0
7 | HOOGHLY | Goghat - I | Electrical | GROUND WATER BASED NAKUNDA PIPED WATER SUPPLY SCHEME IN GOGHAT-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/13414 | New | Quotation of New Service Connection for Nakunda W/s Scheme,TW No-2, Block-Goghat-II, Dist-Hooghly under ED,PHE Dte |  |  | BILL/02479/2023-2024 | 152 | 01/08/2023 |  | WBSEDCL | 5.56 | 0 | 0 | 0
8 | HOOGHLY | Goghat - I | Electrical | GROUND WATER BASED NAKUNDA PIPED WATER SUPPLY SCHEME IN GOGHAT-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/13414 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Nakunda water supply scheme, T.W. No.- I & II, Block: Goghat-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/000177/2022-2023 | 770/ED | 09/02/2023 | 10/05/2023 | R.M.D TRADING. | 20.61 | 10.3 | 49.95 | 40
Total | [13 empty] | 740.54 | 176.75 | 23.87