## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF RAJHAT (Z-I & II) PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/13677 | Augmentation | Repairing of concrete road due laying of pipe line at Antpukur of Rajhat PWSS under Chinsurah Sub Division of Hooghly Division, P.H.E.Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000049/2024-2025 | 552/CH | 14/06/2024 | 21/06/2024 | M/S BIMAL DAS AND CO. | 1.81 | 1.79 | 99.09 | 80
2 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF RAJHAT (Z-I & II) PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/13677 | Augmentation | Preparation of DPR for Augmentation RAJHAT Piped Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-POLBA DADPUR]. | Assistant Engineer (Civil) |  | ORD/000079/2024-2025 | 694/CH | 09/08/2024 | 16/08/2024 | APEX ENGINEERING | 2.71 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF RAJHAT (Z-I & II) PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/13677 | Augmentation | Construction of 2 Nos. 3.6 m X 3.0 m Switch Room with Additional Plinth Height, with Sanitary and Water Supply arrangement, Laying of C.I/D.I pipes & specials for connection of Proposed 2 nos.T.W with distribution system, FHTC of RAJHAT W/S Scheme under Chinsurah Sub - Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000100/2023-2024 | 1419/Hug | 17/05/2023 | 01/07/2023 | BOSE ENTERPRISE (RATUL BOSE) | 40.33 | 26.34 | 65.3 | 80
4 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF RAJHAT (Z-I & II) PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/13677 | Augmentation | Laying of Pipe Line for necessary interconnection with T.W.& Distribution System For RAJHAT Water Supply Scheme under CHINSURAH Sub-Division of HOOGHLY DIVISION P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000134/2023-2024 | 1476/HUG | 19/05/2023 | 03/07/2023 | R.K. TRADERS | 29.66 | 29.65 | 99.97 | 100
5 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF RAJHAT (Z-I & II) PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/13677 | Augmentation | Providing 400 nos Functional Household Tap Connection (FHTC) within the command area of RAJHAT & DHARAMPUR Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000441/2021-2022 | 459/Hug | 10/03/2022 | 04/04/2022 | MAHARAJA CONSTRUCTION CO. | 24.32 | 22.43 | 92.23 | 100
6 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF RAJHAT (Z-I & II) PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/13677 | Augmentation | Laying HDPE Pipeline From existing existing Distribution System for providing FHTC of Rajhat Zone-II W/S Scheme under Chinsurah Sub - Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000771/2023-2024 | 129/CH | 16/02/2024 | 02/03/2024 | BOSE ENTERPRISE (RATUL BOSE) | 4.94 | 2.47 | 50 | 15
7 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF RAJHAT (Z-I & II) PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/13677 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chinsurah Sub Division under Hooghly Division PHE Dte 1. Uttar Babnan Z-I PWSS 2.Uttar Babnan Z-II PWSS 3. Rajhat PWSS | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000778/2023-2024 | 147/CH | 20/02/2024 | 27/02/2024 | MAA BUNAMATA ENTERPRISE | 0.48 | 0.24 | 50 | 30
8 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF RAJHAT (Z-I & II) PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/13677 | Augmentation | Diversion of Laying of Distribution Pipeline for Re-construction of Bridge by I & W Dept. at Chatimtala under Rajhat W/S Scheme under Chinsurah Sub Division Of Hooghly Division PHE Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000791/2023-2024 | 541/HUG | 20/02/2024 | 06/03/2024 | MINTU CHAKRABORTY | 3.41 | 0 | 0 | 0
9 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF RAJHAT (Z-I & II) PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/13677 | Augmentation | Restoration & repairing of village road damaged due to laying of pipeline of piped water supply schemes under JJM in RAJHAT GP of POLBA-DADPUR Block. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000913/2023-2024 | 246/CH | 12/03/2024 | 11/04/2024 | M/S BIMAL DAS AND CO. | 4.98 | 0 | 0 | 0
10 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF RAJHAT (Z-I & II) PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/13677 | Augmentation | Quotation bill for new service connection at Rajhat w/s scheme |  |  | BILL/00841/2022-2023 | 173 | 28/02/2023 |  | WBSEDCL | 7.44 | 0 | 0 | 0
11 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF RAJHAT (Z-I & II) PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/13677 | Augmentation | Quotation bill for New service connection at Rajhat W/S. Sch Z-I, PH-IV |  |  | BILL/00851/2022-2023 | 173 | 28/02/2023 |  | WBSEDCL | 19.98 | 0 | 0 | 0
12 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF RAJHAT (Z-I & II) PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/13677 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Rajhat water supply scheme, Zone-I, T.W. No.- IV, Block: Polba Dadpur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000234/2022-2023 | 865/ED | 14/02/2023 | 15/05/2023 | DIPA CHHETRI | 10.17 | 10.02 | 98.6 | 100
13 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF RAJHAT (Z-I & II) PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/13677 | Augmentation | Hiring of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer, Howrah Mechanical Sub Division, PHE Dte. |  |  | ORD/000835/2023-2024 | 959/HMSD | 20/04/2023 | 20/05/2023 | SANJIB PRADHAN | 0.39 | 0.39 | 100 | 1
14 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF RAJHAT (Z-I & II) PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/13677 | Augmentation | Car hiring and fuel bill for car no. WB02AB3954 from 01.07.2023 to 31.07.2023. |  |  | ORD/000836/2023-2024 | 363//AE-I/ED | 29/05/2023 | 29/06/2023 | TRIDIP SARKAR | 0.38 | 0.36 | 94.45 | 1
Total | [13 empty] | 151.01 | 93.69 | 62.05